## Tender Summary
PROJECT: 136 – 238 Levita House and New Horizon Youth Centre Heritage Surveys Ltd
Ref | TENDER SUMMARY | £p
7.1 | Section 1 – Preliminaries INC Prov Sums A54 | 441490
7.2 | Section 2 – Materials and Workmanship Performance Requirements
7.3 | Section 3 – Scaffolding and Access Performance Requirements | 640391
7.4 | Section 4 – Schedule of Works 136 – 180 Levita | 1218121.06
7.5 | Section 5 – Schedule of Works 181 – 203 Levita | 914279.54
7.6 | Section 6 – Schedule of Works 204 – 238 Levita and New Horizon Youth Centre | 1128155.99
| Total Carried to Form of Tender | 4342437.6
Signed A. RANSCOMBE
Name (Print) ALAN RANSCOMBE
Date 29/04/19
Contractor MITRE CONSTRUCTION CO. LTD
Address 1e HALL LANE, CHINGFORD
LONDON, E4 8HH
Tel ……………………………………………………………………………. | 020 85277270
e-mail ……………………………………………………………………………. | alanranscombe@mitreconstruction.co.uk
JOB REF: 267 – Levita House
CLIENT: London Borough of Camden

## Section 1 Preliminaries
Section 1 Preliminaries (Rev B March 2019)
Table of Contents
A10 PROJECT PARTICULARS 3
A11 TENDER AND CONTRACT DOCUMENTS 6
A12 THE SITE/ EXISTING BUILDINGS 7
A13 DESCRIPTION OF THE WORK 10
A20 JCT STANDARD BUILDING CONTRACT (SFB) 11
A30 TENDERING/ SUBLETTING/ SUPPLY 17
A31 PROVISION, CONTENT AND USE OF DOCUMENTS 22
A32 MANAGEMENT OF THE WORKS 27
A33 QUALITY STANDARDS/ CONTROL 31
A34 SECURITY/ SAFETY/ PROTECTION 37
A35 SPECIFIC LIMITATIONS ON METHOD/ SEQUENCE/TIMING 44
A36 FACILITIES/ TEMPORARY WORK/ SERVICES 45
A37 OPERATION/ MAINTENANCE OF THE FINISHED WORKS 47
A40 CONTRACTOR’S GENERAL COST ITEMS: MANAGEMENT AND STAFF 52
A41 CONTRACTOR’S GENERAL COST ITEMS: SITE ACCOMMODATION 53
A42 CONTRACTOR’S GENERAL COST ITEMS: SERVICES AND FACILITIES 54
A43 CONTRACTOR’S GENERAL COST ITEMS: MECHANICAL PLANT 56
A44 CONTRACTOR’S GENERAL COST ITEMS: TEMPORARY WORKS 57
A50 WORK/ PRODUCTS BY/ ON BEHALF OF THE EMPLOYER 58
A53 WORK BY STATUTORY AUTHORITIES/ UNDERTAKERS 59
A54 PROVISIONAL WORK/ ITEMS 59
A55 DAYWORKS 61
COLLECTION PAGE 62
3 of 64 | A10 PROJECT PARTICULARS
110 THE PROJECT
 Name: 136 - 238 Levita House, and New Horizon Youth Centre, 68 Chalton Street
 Nature: External envelope refurbishment including re-roofing, windows and doors, fabric repairs and redecorations.
 Location: Kings Cross, Camden, London NW1.
 Length of contract: 75 calendar weeks, on a Sectional Completion basis.
120 EMPLOYER (CLIENT)
 Name: Mayor and Burgesses of The London Borough of Camden.
 Address: 33/35 Jamestown Road, Camden, London, NW1 7DB.
 Contact: Shamsul Alam.
 Telephone: 020 7974 3349.
 Email: Shamsul.Alam@camden.gov.uk
130 PRINCIPAL CONTRACTOR (CDM)
 Name: The Contractor.
 Address: TBA.
 Contact: TBA.
 Telephone: TBA.
 E-mail: TBA.
132 PRINCIPAL CONTRACTOR (SWMP)
 Name: The Contractor as A10:130
140 CONTRACT ADMINISTRATOR
 Name: Heritage Surveys Limited.
 Address: Unit 11H, Capital Business Centre, 22 Carlton Road, South Croydon, Surrey CR2 0BS.
 Contact: Steve Brewer.
 Telephone: +44 7961 214724.
 E-mail: steve.brewer@heritage-surveys.com
150 CDM PRINCIPAL DESIGNER
 Name: 3cRisk Limited
 Address: 10 Greycoat Place, London, SW1P 1SB
 Contact: Martin Perrett
 Telephone: +44 20 7510 2485/ +44 7909 684 214
 E-mail: Martin.Perrett@3cRisk.com
160 QUANTITY SURVEYOR
 Name: As A10:140.
170 STRUCTURAL ENGINEER
 Name: Contractor’s design.
 Address: TBA
 Contact:
 Telephone:
 E-mail:
4 of 64 | 175 MECHANICAL AND ELECTRICAL ENGINEER
 Name: Contractor’s design.
 Address: TBA
 Contact:
 Telephone:
 E-mail –
200A SAFETY OFFICERS:
The Contractor shall appoint and notify the name of a Member of Staff (hereinafter called
the ‘Contractor’s Safety Officer’) who is or will be employed full time on the works to oversee and carry out the Contractor’s obligations in relation to health and safety, including the Employer’s General Policy for Health and Safety (herein called ‘the Safety Requirements’).
The Employer shall be entitled to appoint a person (hereinafter called the ‘Employer’s
Safety Officer’) who shall (either by himself/herself or by his/her authorised representatives) at all times be given access to the works and workshops of other places under the control of the Contractor connected with the works where work is prepared for the contract and when work is to be so prepared in workshops or other places of a sub- contractor the Contractor shall by a term in the sub-contract so far as possible secure a similar right of access to those workshops or places for the Employer’s Safety Officer (either by himself/herself or by his/her authorised representatives) and shall do all things reasonably necessary to make such rights effective.
The Contractor’s Safety Officer shall owe to the Employer the following specific duties and
obligations:-
(i) To make himself/herself available for consultation at the Employer’s Safety
Officer’s request;
(ii) To provide details of any activity upon which the Contractor shall be engaged for
performance of the works or at any place of work including any workshop or other place;
(iii) To provide information as to safety measures taken by the Contractor or any sub-
contractor any measure taken in recognition and compliance with the Safety Requirements from the Employer’s Safety Officer and in particular as to scaffolding plant temporary works and other matters as the Employer’s Safety Officer may require;
5 of 64 | In the event of the Employer’s Safety Officer being of the opinion that any activity being
carried out on or about to be carried out on (whether by or under control of the Contractor, his/her servant or agent, or otherwise) contrary to the safety requirements and constitutes an immediate hazard or threat to life, or is likely to cause injury to any person, the Employer’s Safety Officer may serve a Notice requiring the immediate cessation of such activity (hereinafter called a ‘Prohibition Notice’) and the Contractor shall forthwith stop and said activity or that part identified in the ‘Prohibition Notice’ until such time as the said hazard, threat or likelihood thereof is to the reasonable satisfaction of the Employer’s Safety Officer abated or removed. The Employer’s Safety Officer may issue and serve a ‘Withdrawal of Prohibition Notice’ which shall have the effect of permitting the Contractor to continue with the said activity or such part thereof identified in the ‘Withdrawal of Prohibition Notice’.
The Employer shall be under no liability in respect of any loss, damage or other
consequence resulting from the service of a ‘Prohibition Notice’ in accordance with the
contract.
6 of 64 | A11 TENDER AND CONTRACT DOCUMENTS
110 TENDER DRAWINGS
 The tender drawings are: representative of the areas of the building in which the work is to be carried out and, when read in conjunction with the other tender documents, provide information for tendering purposes. However the contractor will need to develop and fully design some aspects of the works. Tender Drawings are as listed in Tender drawing issue sheet.
120 CONTRACT DRAWINGS
 The Contract Drawings: The same as the tender drawings.
130 QUANTITIES DRAWINGS
 The drawings from which the tender documents were prepared are the tender drawings.
 Exceptions: - None.
160 PRECONSTRUCTION INFORMATION
 Format: The Preconstruction information is a separate document that forms part of the tender invitation pack and will also form a contract document described in these preliminaries in Section A34. It refers to information given elsewhere in the preliminaries and other tender documents.
180 OTHER DOCUMENTS
 Inspection: Drawings and other documents relating to the Contract but not included in the tender documents may be seen by appointment during normal office hours at the office of LB Camden insofar as such documents have been made available to them or exist.
7 of 64 | A12 THE SITE/ EXISTING BUILDINGS
110 THE SITE
 Description: The site is as shown on the block plan drawing. The block is a Grade II Listed building built in the early 1930s, forming part of the Ossulston Estate. The block is a part attached residential block of flats with retails units on part of the ground storey. Part of the block incorporates the New Horizon Youth Centre, and part abuts the Somerstown Coffee House public house on Chalton Street.
120 EXISTING BUILDINGS ON/ ADJACENT TO THE SITE
 Description: The existing flats, retail units, youth centre, public house, estate pathways and roads will remain in use throughout the progress of the contract.
140 EXISTING UTILITIES AND SERVICES
 Drawings: (Information shown is indicative only): The Contractor's particular attention is drawn to the existing services that serve the buildings. The block is currently served by gas, water, electrical, drainage, and communication services. These will all remain in use during the contract.
 Other information: The Contractor is required to carry out a visual site inspection of the existing services, to ascertain the location, entry and extent of those services that will cause interference with the proposed works and are reasonably apparent and identifiable at the time of tendering. All existing building services affected by the works, shall be maintained during the progress of the works.
200 ACCESS TO THE SITE
 Description: The access to the Site is via Chalton Street and Ossulston Street into a hard standing communal area. The Contractor shall make due allowance for this together with the cost of protection of all trees and hard landscaping features. Trees are also provided close by on the Chalton Street public footway, close to where scaffolding will be required, and will need protecting.
 Limitations: The Contractor shall be aware of local schools and avoid deliveries and construction traffic between the key children drop off and pick up hours of 8am and 9.15am and between 3pm and 4.30pm. All roads and pavements will remain in use, therefore, the Contractor will be required to implement and manage a regime, including warning signage, safety lighting and speed restrictions to ensure the safety of all users of all access routes.
 The contractor’s attention is drawn to the low head heights to the arch/drive/tunnel from Ossulston Street which will limit vehicle size for delivery.
210 PARKING
 Restrictions on parking of the Contractor's and employees' vehicles: There is no parking available on site for Contractor's vehicles other than the site compound plant, an area(s) for which will be designated in the central courtyard.
220 USE OF THE SITE
 General: Do not use the site for any purpose other than carrying out the Works.
 Limitations: The Contractor shall confine his operations, including the storage of materials, plant and any other equipment, within these boundaries. The Contractor must keep all workmen, including those employed by sub-contractors, under his control and within the boundaries of the site of the Works. Workmen employed on the Contract who require to proceed beyond the defined limits for the execution of the Works shall do so only after the Contractor has obtained permission from the Employer and any relevant authority.
8 of 64 | 230 SURROUNDING LAND/ BUILDING USES
 General: Adjacent or nearby uses or activities are as follows: - The contractor shall use his best endeavours to minimise disturbance to adjoining residents and retail tenants at all times during the contract period.
 The contractor should note that the Chalton Street market operates at least every Friday with stalls taking up space in the immediate vicinity.
 The Contractor shall ascertain and comply with all police and traffic regulations and directions particularly those relating to access to and exit from the site, loading and unloading of vehicles, skips, etc. and ensure that his sub- contractors are notified of, and comply with such regulations throughout the Contract Period. Any costs or third party claims resulting from non-compliance will not be permitted.
240 HEALTH AND SAFETY HAZARDS
 General: The nature and condition of the site/ building cannot be fully and certainly ascertained before it is opened up. However the following hazards are or may be present:
o Roof areas. An asbestos survey to previously inaccessible parts of the block is included as part of the contract.
o Lift shafts.
o Mains and piped services.
 Information: The accuracy and sufficiency of this information is not guaranteed by the Employer or the Employer's representative. Ascertain if any additional information is required to ensure the safety of all persons and the Works.
 Site staff: Draw to the attention of all personnel working on the site the nature of any possible contamination and the need to take appropriate precautionary measures.
250 SITE VISIT
 Assessment: Ascertain the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the Works.
 Arrangements for visit: As A10:140, although externally the site is available at all times.
 The Contractor shall not allow any person or persons access to the Site for any reason other than activities necessary for performance of the Works under this contract without prior consent in writing by the Employer first having been obtained and such consent shall be at the sole discretion of the Employer. The Employer may require the person(s) granted consent to access the Site to indemnify the Employer against any expense, liability, loss claim or proceedings whatsoever arising under any statute or at common law in respect of personal injury to or the death of any person whatsoever arising out of or in the course of or caused by the activities under this contract for which the said person or persons are present on the site and an assurance given by the person(s) accessing the Site to the Employer that his/her presence on site will in no way affect the peaceable or quiet enjoyment of the occupiers of adjacent or neighbouring property.
 The Contractor will be required to exercise great care when entering or leaving the Site and to take all necessary precautions to safeguard all persons using the access road, footpaths and paved areas from injury by reason of the Contractor's vehicles using the Site.
 The Contractor shall maintain boundary walls, fences and paved areas in their present condition and on completion make good any damage arising from the Works and reinstate to the satisfaction of the Employer.
 Vehicles or plant are not to be driven over footpaths or hard or soft landscaped areas and any areas in or adjacent to this site. Any damage caused by the Contractor to these surfaces shall be repaired by the Contractor at the Contractor's own expense.
9 of 64 |  The Contractor shall use the site only for the carrying out of the Works and take all
necessary precautions to prevent nuisance from water, smoke, dust, rubbish and other causes.
 All reasonable means shall be used to avoid inconveniencing adjoining owners and occupiers. The Contractor shall not be allowed to trespass upon adjoining properties.
 If the execution of the Works requires that the Contractor must enter upon adjoining property, the necessary permission shall be first obtained by the Contractor from the owner, and occupier if different, who shall see that these instructions are carried out and the Contractor shall indemnify the Employer against any claim or action for damages on account of any trespass or other misconduct of his/her agents, servants or employees.
 The Contractor will not be permitted to park cars or other vehicles on any estates within the ownership of the Employer. Vehicles belonging to the Contractor, or the Contractor's employee’s servants or agents must be parked on the public roads or car parks at the Contractor's own expense.
 The Contractor shall not obstruct any public way or otherwise do or suffer to be done anything which may amount to a nuisance or annoyance and shall not interfere with any right of way or light to adjoining property and any notice received by the Contractor or left upon the site and the Contractor's registered address requiring the discontinuance or suspension of any part of the Works shall at once be forwarded to the Employer or is given orally shall at once be communicated, by the Contractor to the Employer in writing, and the Contractor shall keep the Employer indemnified against any claim or loss consequent upon any act, neglect or omission of the Contractor or the Contractor's employees agents, or servants.
 The Contractor shall not display or permit advertisements to be displayed on site without consent of the Employer.
10 of 64 | A13 DESCRIPTION OF THE WORK
120 THE WORKS
 Description: In brief these comprise the design, supply and installation of a scheme of external envelope refurbishment including re-roofing, window and door replacement, and external redecorations.
 Further works include; repairs of existing asphalt walkways and overcoating parapet gutters with liquid plastic solution; re-cladding of dormer windows; repair/renewal of damaged render and associated redecorations; cleaning brickwork and concrete; repair/replacement of rain water goods; concrete repairs to main structure and internal concrete stairwells, redecoration of external fabric and communal areas. fabric.
 Improvement of communal area lighting to certain parts.
 Mechanical ventilation is to be designed and installed to some kitchens and bathrooms which are located on the internal courtyard elevations, and which do not have such ventilation currently or where is it beyond repair. Fans are to be through walls and not window mounted unless otherwise agreed with the Employer.
 The contractor is to design and construct for all associated works with the existing building including scaffolding, temporary roof and temporary weather protection.
 The works will be undertaken on a Sectional Completion basis, broadly divided into three blocks. Section 3 will follow PC of Section 1, Section 2 start as described in A20.
130 WORK BY OTHERS CONCURRENT WITH THE CONTRACT
 Description: External works are likely to be undertaken during the contract period to the estate areas and in the flats and communal areas in this block of a regular and reactive maintenance nature.
Across the estate the Council may be undertaking a Better Homes contract which will be undertaken inside the flats and should not impact on this project particularly.
 Allow for full co-ordination between all contractors as required under the CDM– Regulations including meetings, co-ordinated inductions, workshops and general site and health and safety management in this regard.
11 of 64 | A20 JCT STANDARD BUILDING CONTRACT (SBC)
JCT DESIGN AND BUILD CONTRACT
 The Contract: JCT Standard Building Contract Without Quantities (SBC XQ), 2016 Edition incorporating LB Camden amendments as contained in Appendix B.
 Requirement: Allow for the obligations, liabilities and services described.
THE RECITALS
First - THE WORKS
Comprise: Construction of external envelope refurbishment works as described in the
Schedule of Works, specification and drawings. Completion of design of elements as scheduled.
 Location: 136 – 238 Levita House, and New Horizon Youth Centre, 68 Chalton Street, Camden, London NW1 1HN.
Second - CONTRACT DRAWINGS
• The contract drawings: As listed in clause A11/120.
Third B - PRICING BY THE CONTRACTOR
 Option: Pricing Option B will apply, Pricing Option A will be deleted.
 Priced document: The following words will be deleted “or a Schedule of Rates”. Activity Schedule: The words 'and has provided the Employer with the priced schedule of activities annexed to this Contract (the Activity Schedule)' will be deleted.
Fifth - INFORMATION RELEASE SCHEDULE
• The Fifth Recital will be deleted.
Sixth - DIVISION OF THE WORKS INTO SECTIONS
 Section 1 – 136 – 180 Levita House.
 Section 2 – 181 – 203 Levita House.
 Section 3 – 204 – 238 Levita House including New Horizon Youth Centre.
Ninth, Tenth, Eleventh, and Twelfth - CONTRACTOR'S DESIGNED PORTION
 Ninth Recital: The works include the design and construction of:
o Scaffolding and Temporary roofs
o Completion of detailed window design
o Fire Rated door sets
o Mechanical ventilation to kitchens, bathrooms and WCs
o Complete design of communal area lighting and emergency lighting
THE ARTICLES
3 – ARCHITECT/CONTRACT ADNMINISTRATOR
 Contract Administrator: See clause A10/140.
5 - CDM PRINCIPAL DESIGNER (PD)
 CDM Principal Designer: See clause A10/150.
6 - PRINCIPAL CONTRACTOR (CDM AND SWMP)
 Principal Contractor: See clause A10/130 and A10/132.
8 - ARBITRATION
 Does not apply and will be deleted.
12 of 64 | 9 - LEGAL PROCEEDINGS
 Amendments: - None.
10 - SCHEDULE OF AMENDMENTS
 Refer: to Appendix B for incorporation of amendments.
CONTRACT PARTICULARS
PART 1: GENERAL
Fourth recital and clause 4.5 - CONSTRUCTION INDUSTRY SCHEME (CIS)
 Employer at the Base Date is not a 'contractor' for the purposes of the CIS.
Sixth Recital - DESCRIPTION OF SECTIONS
Description of Sections:
 Section 1 – 136 – 180 Levita House – all works.
 Section 2 – 181 – 203 Levita House - all works.
 Section 3 – 204 – 238 Levita House including New Horizon Youth Centre– all works.
Seventh Recital - FRAMEWORK AGREEMENT
 Framework agreement: N/A.
Eighth Recital and Schedule 8 - SUPPLEMENTAL PROVISIONS
 Collaborative working: applies.
 Health and safety: applies.
 Cost savings and value improvements: applies.
 Sustainable developments and environmental considerations: applies.
 Performance indicators and monitoring: applies.
 Notification and negotiation of disputes: applies.
 Where provision 6 applies, the respective nominees of the parties are:
Employer's nominee: Assistant director to be advised
Contractor's nominee: to be advised
Or such replacement as each party may notify to the other from time to time.
 Named Specialists: does not apply.
Tenth Recital - EMPLOYER'S REQUIREMENTS
• Comprise: As specifically detailed in the Tender documents.
Eleventh Recital - CONTRACTOR'S PROPOSALS, CDP ANALYSIS
• Contractor's Proposals: To be completed by the Contractor.
• CDP Analysis: To be completed by the Contractor.
• Specific Requirements: As invitation to tender documents.
Article 8 – ARBITRATION - Article 8 and clauses 9.3 to 9.8 (arbitration) do not apply.
13 of 64 | Clause 1.1 - BASE DATE - Base Date: 10 days before tender return date stated in ITT.
Clause 1.1 - DATE FOR COMPLETION OF THE SECTIONS - Date for completion of the Works
where completion by sections applies:
 Section 1 – 136 – 180 Levita House – 40 calendar weeks after date of possession.
 Section 2 – 181 – 203 Levita House – 28 calendar weeks after date of possession of that section.
 Section 3 – 204 – 238 Levita House including New Horizon Youth Centre - 35 calendar weeks after date of completion of Section 1.
Clause 1.7 - ADDRESSES FOR SERVICE OF NOTICES
 Employer: Address: London Borough of Camden, 33 – 35 Jamestown Road, Camden, London, NW1 7BD.
 Fax number/Email: Notices will not be accepted by fax or e-mail - Submit by recorded or special delivery and obtain receipt.
 Contractor: TO BE COMPLETED BY CONTRACTOR.
 Fax number: TO BE COMPLETED BY CONTRACTOR.
Clause 2.4 - DATE OF POSSESSION OF THE SITE – (where sectional completion applies)
Date of Possession of the site: To be advised - Circa September 2019 with design period commencing beforehand.
 Section 1 – 136 – 180 Levita House – Date of possession.
 Section 2 – 181 – 203 Levita House – 12 calendar weeks after date of Possession of Section 1.
 Section 3 – 204 – 238 Levita House including New Horizon Youth Centre – One working day after Practical Completion of Section 1.
Clause 2.5 - DEFERMENT OF POSSESSION OF THE SITE - Clause 2.5 applies.
Where clause 2.5 applies, maximum period of deferment is 6 weeks per Section.
Clause 2.9.1.2 - MASTER PROGRAMME
• Critical paths: are required to be shown.
Clause 2.19.3 - LIMIT OF CONTRACTOR'S LIABILITY FOR LOSS OF USE, ETC. - Limit of
Contractor's liability for loss of use: Not applicable.
Clause 2.32.2 - LIQUIDATED DAMAGES - Damages: Sections 1, 2 and 3 - At the rate of
£2,093 per section per calendar week or part thereof.
Clause 2.37 - SECTION SUMS - Section sums:
o Section 1: Sum: TBC. o Section 2: Sum: TBC. o Section 3: Sum: TBC
Clause 2.38 - RECTIFICATION PERIOD - Twelve months from the date of practical
completion of the all the sections of the Works, i.e. after Section 3 completion.
CLAUSE 4.3 AND 4.14 - FLUCTUATIONS PROVISION
• Fluctuations Provision: No Fluctuations Option applies.
14 of 64 | Clause 4.7 - ADVANCE PAYMENT AND ADVANCE PAYMENT BOND - Advance payment:
Clause 4.7 does not apply.
Clause 4.8 - INTERIM PAYMENTS – INTERIM VALUATION DATES
The first Interim Valuation Date is: One Month after the date of possession of Section 1
and thereafter the same date in each month or the nearest Business Day in that month.
Clause 4.16.4 - LISTED ITEMS - UNIQUELY IDENTIFIED - Listed items: Clause 4.16.4 will be
deleted.
Clause 4.16.5 - LISTED ITEMS - NOT UNIQUELY IDENTIFIED - Listed items: Clause 4.15.5 will
be deleted.
Clause 4.18 - CONTRACTOR'S RETENTION BOND - Clause 4.18 does not apply.
Clause 4.19.1 - RETENTION PERCENTAGE - Retention: 3% per cent.
Clause 5.7 – DAYWORK - Percentage additions to each section of the prime cost or, if they
apply in respect of labour, the All-Inclusive Rates, are set out in the following document: Preliminaries - A55.
Clause 6.4.1 - CONTRACTOR'S PUBLIC LIABILITY INSURANCE - INJURY TO PERSONS OR
PROPERTY - Insurance cover (for any one occurrence or series of occurrences arising out of one event): £10,000,000.
Clause 6.5.1 - INSURANCE - LIABILITY OF EMPLOYER - Minimum amount of indemnity for
any one occurrence or series of occurrences arising out of one event: Is not required.
Clause 6.7 and Schedule 3 - INSURANCE OF THE WORKS - INSURANCE OPTIONS
 Schedule 3: Insurance option C applies.
 Percentage to cover professional fees: 15 per cent.
Clause 6.10 and Schedule 3 - TERRORISM COVER
 Details of the required cover: Not required.
Clause 6.15 - CONTRACTOR'S DESIGNED PORTION PROFESSIONAL INDEMNITY INSURANCE
 Level of cover: Amount of indemnity required: Relates to claims or series of claims arising out of one event and is £ 2,000,000.
 Cover for pollution and contamination claims: Is required, with a sub-limit of £2,000,000
 Expiry of required period of CDP Professional Indemnity Insurance: 12 years.
Clause 6.17 - JOINT FIRE CODE
 The Joint Fire Code: Applies.
 Application: State whether the insurer under Schedule 3, Insurance Option A, B or C (paragraph C.2) has specified that the works are a 'Large Project': Yes
Clause 6.20 - JOINT FIRE CODE - AMENDMENTS AND REVISIONS
 Joint Fire Code - Amendments/ revisions: The cost, if any, of compliance with amendments or revisions to the Joint Fire Code shall be borne by the Contractor.
Clause 7.2 - ASSIGNMENT/ GRANT BY EMPLOYER OF RIGHTS UNDER CLAUSE 7.2
15 of 64 |  Clause 7.2 does not apply.
CLAUSE 7.3.1 - PERFORMANCE BOND OR GUARANTEE
 Bond or guarantee from bank or other approved surety: is required.
 - Required form: As included in Camden's contract amendments document.
 - Initial value (percentage of the Contract Sum): 10%.
 - Period of validity: the date of Practical Completion of the Works
Clause 7.4 - THIRD PARTY RIGHTS AND COLLATERAL WARRANTIES
 Details: As set out in the following documents: Refer to Camden's contract amendments document. Camden require collateral warranties from all specialist subcontractors with design responsibility.
Clause 8.9.2 - PERIOD OF SUSPENSION (TERMINATION BY CONTRACTOR)
 Period of suspension: Two months.
Clauses 8.11.1.1 to 8.11.1.5 - PERIOD OF SUSPENSION (TERMINATION BY EITHER PARTY)
 Period of suspension: Two months.
Clause 9.2.1 – ADJUDICATION
 The Adjudicator is: to be advised.
 Nominating body: Where no Adjudicator is named or where the named Adjudicator is unwilling or unable to act (whenever that is established): The Royal Institution of Chartered Surveyors.
Clause 9.4.1 – ARBITRATION
• This clause will be deleted.
PART 2: COLLATERAL WARRANTIES Part 2(E) - COLLATERAL WARRANTIES FROM
SUBCONTRACTORS
 Part 2(E)
 Conditions: Clauses 3.3 and 3.4 of the Contract.
 Collateral warranties may be required from the following subcontractors or categories of subcontractor.
 Name or category:
o Window design and installation
o Fire Rated door sets.
 Types of warranty: SCWa/P&T.
 Professional Indemnity Insurance: Level: -, Amount: £2,000,000, Period: Six years.
THE CONDITIONS
SECTION 1: DEFINITIONS AND INTERPRETATION
1.5 - RECKONING PERIODS OF DAYS - Amendments: None.
1.12 - APPLICABLE LAW - Amendments: None.
SECTION 2: CARRYING OUT THE WORKS
SECTION 3: CONTROL OF THE WORKS
16 of 64 | SECTION 4: PAYMENT
SECTION 5: VARIATIONS
SECTION 6: INJURY, DAMAGE AND INSURANCE
SECTION 7: ASSIGNMENT, THIRD PARTY RIGHTS AND COLLATERAL WARRANTIES
SECTION 8: TERMINATION
SECTION 9: SETTLEMENT OF DISPUTES
EXECUTION: The Contract: Will be executed as a deed.
CONTRACT GUARANTEE BOND
Contract Guarantee Bond: May be required. The contractor must allow cost of bond in
tender and indicate the cost here, carried forward to the pricing column.
Refer also to London Borough of Camden ITT documents.
17 of 64 | A30 TENDERING/ SUBLETTING/ SUPPLY
MAIN CONTRACT TENDERING
110 SCOPE
 General: These conditions are supplementary to those stated in the Invitation to Tender and on the form of tender.
145 TENDERING PROCEDURE
 General: In accordance with NBS Guide to Tendering for Construction Projects.
 Errors: Alternative 2 is to apply.
160 EXCLUSIONS
 Inability to tender: Immediately inform if any parts of the work as defined in the tender documents cannot be tendered.
 Relevant parts of the work: Define those parts, stating reasons for the inability to tender.
170 ACCEPTANCE OF TENDER
 Acceptance: No guarantee is offered that any tender will be recommended for acceptance or be accepted, or that reasons for non-acceptance will be given.
 Costs: No liability is accepted for any cost incurred in the preparation of any tender.
190 PERIOD OF VALIDITY
 Period: After submission or lodgement, keep tender open for consideration (unless previously withdrawn) for not less than 120 days.
 Date for possession/ commencement: See section A20.
PRICING/ SUBMISSION OF DOCUMENTS
210 PRELIMINARIES IN THE SPECIFICATION
 Measurement rules: Preliminaries/ General Conditions (A10-A56 inclusive) have been prepared in accordance with NRM2.
220 PRICING OF PRELIMINARIES
 Abbreviations: The following have been used:
 F = Fixed charge item.
 TR = Time related charge item.
250 PRICED DOCUMENTS
 Alterations: Do not alter or qualify the priced documents without written consent. Tenders containing unauthorised alterations or qualifications may be rejected.
 Measurements: Where not stated, ascertain from the drawings.
 Deemed included: Costs relating to items, which are not priced, will be deemed to have been included elsewhere in the tender.
 Submit: With tender.
310 TENDER
 General: Tenders must include for all work shown or described in the tender documents as a whole or clearly apparent as being necessary for the complete and proper execution of the Works.
18 of 64 | 440 CONTRACT SUM ANALYSIS
Content of the Analysis: A breakdown of the Contract Sum into at least the following
categories:
 As per schedule of works and full preliminaries breakdown.
 Form: Schedule of works breakdown.
 Fully priced copy: Submit with tender
480 PROGRAMME
 Programme of work: Prepare a summary showing the sequence and timing of the principal parts of the Works and periods for planning and design. Itemize any work which is excluded.
 Submit: With tender.
500 TENDER STAGE METHOD STATEMENTS
Method statements: Refer to Camden Instructions to Tenderers document for details.
• Statements: Submit with the tender.
510 ALTERNATIVE METHOD TENDERS
 Not used.
500 CONTRACTOR’S PROPOSALS
Proposals: Include the following: please refer to ITT documentation and items required
with tender return.
515 ALTERNATIVE TIME TENDERS
 Not used
530 SUBSTITUTE PRODUCTS
 Details: If products of different manufacture to those specified are proposed, submit details with the tender giving reasons for each proposed substitution. Substitutions, which have not been notified at tender stage and which are not equivalent, may not be considered.
 Compliance: Substitutions accepted will be subject to the verification requirements of clause A31/200.
540 QUALITY CONTROL RESOURCES
 Statement: Describe the organisation and resources to control the quality of the Works, including the work of subcontractors.
 QA staff: Identify in the statement the number and type of staff responsible for quality control, with details of their qualifications and duties.
 Submit: With the Tender.
550 HEALTH AND SAFETY INFORMATION
 Content: Describe the organisation and resources to safeguard the health and safety of operatives, including those of subcontractors, and of any person whom the Works may affect.
 Include:
 A copy of the contractor's health and safety policy document, including risk assessment procedures.
19 of 64 |  Accident and sickness records for the past five years.
 Records of previous Health and Safety Executive enforcement action.
 Records of training and training policy.
 The number and type of staff responsible for health and safety on this project with details of their qualifications and duties.
 Submit: With the Tender. Please refer to Quality Question in Camden's Instructions for Tenderers
570 OUTLINE CONSTRUCTION PHASE HEALTH AND SAFETY PLAN
 Content: Submit the following information within one week of request:
 Method statements on how risks from hazards identified in the pre- construction information and other hazards identified by the contractor will be addressed.
 Details of the management structure and responsibilities.
 Arrangements for issuing health and safety directions.
 Procedures for informing other contractors and employees of health and safety hazards.
 Selection procedures for ensuring competency of other contractors, the self- employed and designers.
 Procedures for communications between the project team, other contractors and site operatives.
 Arrangements for cooperation and coordination between contractors.
 Procedures for carrying out risk assessment and for managing and controlling the risk.
 Emergency procedures including those for fire prevention and escape.
 Arrangements for ensuring that all accidents, illness and dangerous occurrences are recorded.
 Arrangements for welfare facilities.
 Procedures for ensuring that all persons on site have received relevant health and safety information and training.
 Arrangements for consulting with and taking the views of people on site.
 Arrangements for preparing site rules and drawing them to the attention of those affected and ensuring their compliance.
 Monitoring procedures to ensure compliance with site rules, selection and management procedures, health and safety standards and statutory requirements.
 Review procedures to obtain feedback.
20 of 64 | 590 SITE WASTE MANAGEMENT PLAN
 Person responsible for developing the Plan: The Contractor.
 Content: Include details of:
 Principal Contractor for the purposes of the regulations.
 Location of the site.
 Description of the project.
 Estimated project cost.
 Types and quantities of waste that will be generated.
 Resource management options for these wastes including proposals for minimization/ reuse/ recycling.
 The use of appropriate and licensed waste management contractors.
 Record keeping procedures.
 Waste auditing protocols.
 Additional requirements: -.
 Submit with tender.
599 FREEDOM OF INFORMATION
 Records: Retain, make available for inspection and supply on request information reasonably required to allow response to requests made under the provisions of the Freedom of Information Act.
 Determination: Submit requests received. Do not supply information outside the project participants without express written permission.
 Confidentiality: Maintain at all times.
SUBLETTING/ SUPPLY
630 DOMESTIC SUBCONTRACTS
 General: Comply with the Construction Industry Board 'Code of Practice for the selection of subcontractors'.
 List: Provide details of all subcontractors and the work for which they will be responsible.
 Submit: With tender.
640 'LISTED' DOMESTIC SUBCONTRACTORS
 General: The work listed below and described in the Contract Documents must be carried out by persons identified in a list as provided for in clause A30/645:
 The work: Windows and Flat Entrance Doors – design, removal of existing and installation of new.
 Enter into a contract with one of the following:
 NOT USED – Contractor must submit detailed proposal with their tender on this key element of the works. Refer to method statement requirements in the Invitation to Tender pack.
645 'LISTED' DOMESTIC SUBCONTRACTORS
 General: Contract Documents provide that certain work must be carried out by a person of the Contractor's choice selected from a list of not less than three persons given therein.
 The selected person: Will become a subcontractor as provided for in the Contract Condition for Subletting.
 Additions to lists:
 The Employer or Employer's representative may, but only with the consent of the Contractor which shall not be unreasonably withheld, add additional person(s) to the list at any time prior to the execution of a binding subcontract agreement.
21 of 64 |  The Contractor may, but only with consent, which will not be unreasonably
withheld, add additional persons to the list and must, if requested, submit (in an approved form) evidence of the suitability of such additional person(s). Wherever possible, submissions for addition of person(s) must be made, and consent obtained, before return of the tender. When any submission for addition of person(s) is made with the tender the consequences, if any, to the tender price compared to the use of the listed persons are to be made clear or the tender will be treated as qualified.
 Shortage of names: If at any time prior to execution of a binding subcontract agreement less than three persons named in the list (including any persons added as provided above) are able and willing to carry out the relevant work, give notice without delay. The Employer will then forthwith add the names of other persons as provided above so that the list comprises not less than three such persons, or confirm that no names will be added. If the Employer fails to do either within one week of the Contractor's notification the Contractor, who may subcontract in accordance with the Contract, must carry out the work.
 Agreement: Before the start of work to which the list relates enter into a binding subcontract agreement and confirm that this has been done, giving the name of the selected subcontractor.
22 of 64 | A31 PROVISION, CONTENT AND USE OF DOCUMENTS
DEFINITIONS AND INTERPRETATIONS
110 DEFINITIONS
 Meaning: Terms, derived terms and synonyms used in the preliminaries/ general conditions and specification are as stated therein or in the appropriate British Standard or British Standard glossary.
120 COMMUNICATION
 Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek or obtain information, consent or instructions, or make arrangements.
 Format: In writing to the person named in clause A10/140 unless specified otherwise.
 Response: Do not proceed until response has been received.
130 PRODUCTS
 Definition: Materials, both manufactured and naturally occurring, and goods, including components, equipment and accessories, intended for the permanent incorporation in the Works.
 Includes: Goods, plant, materials, site materials and things for incorporation into the Works.
135 SITE EQUIPMENT
 Definition: All appliances or things of whatsoever nature required in or about the construction for completion of the Works but not materials or other things intended to form or forming part of the Permanent Works.
 Includes: Construction appliances, vehicles, consumables, tools, temporary works, scaffolding, cabins and other site facilities.
140 DRAWINGS
 Definitions: To BSRIA BG 6/2009 A design framework for building services. Design activities and drawing definitions.
 CAD data: In accordance with BS 1192.
145 CONTRACTOR'S CHOICE
 Meaning: Selection delegated to the Contractor, but liability to remain with the specifier.
150 CONTRACTOR'S DESIGN
 Meaning: Design to be carried out or completed by the Contractor and supported by appropriate contractual arrangements, to correspond with specified requirements.
155 SUBMIT PROPOSALS
 Meaning: Submit information in response to specified requirements.
160 TERMS USED IN SPECIFICATION
 Remove: Disconnect, dismantle as necessary and take out the designated products or work and associated accessories, fixings, supports, linings and bedding materials. Dispose of unwanted materials. Excludes taking out and disposing of associated pipework, wiring, ductwork or other services.
23 of 64 |  Fix: Receive, unload, handle, store, protect, place and fasten in position and disposal
of waste and surplus packaging including all labour, materials and site equipment for that purpose.
 Supply and fix: As above, but including supply of products to be fixed. All products to be supplied and fixed unless stated otherwise.
 Keep for reuse: Do not damage designated products or work. Clean off bedding and jointing materials. Stack neatly, adequately protect and store until required by the Employer/ Purchaser or for use in the Works as instructed.
 Make good: Execute local remedial work to designated work. Make secure, sound and neat. Excludes redecoration and/ or replacement.
 Replace: Supply and fix new products matching those removed. Execute work to match original new state of that removed.
 Repair: Execute remedial work to designated products. Make secure, sound and neat. Excludes redecoration and/ or replacement.
 Refix: Fix removed products.
 Ease: Adjust moving parts of designated products or work to achieve free movement and good fit in open and closed positions.
 Match existing: Provide products and work of the same appearance and features as the original, excluding ageing and weathering. Make joints between existing and new work as inconspicuous as possible.
 System: Equipment, accessories, controls, supports and ancillary items, including installation, necessary for that section of the work to function.
170 MANUFACTURER AND PRODUCT REFERENCE
 Definition: When used in this combination:
 Manufacturer: The firm under whose name the particular product is marketed.
 Product reference: The proprietary brand name and/ or reference by which the particular product is identified.
 Currency: References are to the particular product as specified in the manufacturer's technical literature current on the date of the invitation to tender. You may offer alternative equally suitable products, submit details with tender.
200 SUBSTITUTION OF PRODUCTS
 Products: If an alternative product to that specified is proposed, obtain approval before ordering the product.
 Reasons: Submit reasons for the proposed substitution.
 Documentation: Submit relevant information, including:
 manufacturer and product reference;
 cost;
 availability;
 relevant standards;
 performance;
 function;
 compatibility of accessories;
 proposed revisions to drawings and specification;
 compatibility with adjacent work;
 appearance;
 copy of warranty/ guarantee.
 Alterations to adjacent work: If needed, advise scope, nature and cost.
 Manufacturers' guarantees: If substitution is accepted, submit before ordering products.
24 of 64 | 210 CROSS REFERENCES
 Accuracy: Check remainder of the annotation or item description against the terminology used in the section or clause referred to.
 Related terminology: Where a numerical cross-reference is not given the relevant sections and clauses of the specification will apply.
 Relevant clauses: Clauses in the referred to specification section dealing with general matters, ancillary products and execution also apply.
 Discrepancy or ambiguity: Before proceeding, obtain clarification or instructions.
220 REFERENCED DOCUMENTS
 Conflicts: Specification prevails over referenced documents.
230 EQUIVALENT PRODUCTS
 Inadvertent omission: Wherever products are specified by proprietary name the phrase 'or equivalent' is to be deemed included.
240 SUBSTITUTION OF STANDARDS
 Specification to British Standard or European Standard: Substitution may be proposed complying with a grade or category within a national standard of another Member State of the European Community or an international standard recognised in the UK.
 Before ordering: Submit notification of all such substitutions.
 Documentary evidence: Submit for verification when requested as detailed in clause A31/200. Any submitted foreign language documents must be accompanied by certified translations into English.
250 CURRENCY OF DOCUMENTS
 Currency: References to published documents are to the editions, including amendments and revisions, current on the date of the Invitation to Tender.
260 SIZES
 General dimensions: Products are specified by their co-ordinating sizes.
 Timber: Cross section dimensions shown on drawings are:
 Target sizes as defined in BS EN 336 for structural s/wood and h/wood sections.
 Finished sizes for non-structural softwood or hardwood sawn and further processed sections.
DOCUMENTS PROVIDED ON BEHALF OF EMPLOYER
410 ADDITIONAL COPIES OF DRAWINGS/ DOCUMENTS
 Additional copies: Issued on request and charged to the Contractor.
440 DIMENSIONS
 Scaled dimensions: Do not rely on.
450 MEASURED QUANTITIES
 Ordering products and constructing the Works: The accuracy and sufficiency of the measured quantities is not guaranteed.
 Precedence: The specification and drawings shall override the measured quantities.
460 THE SPECIFICATION
 Coordination: All sections must be read in conjunction with Main Contract Preliminaries/ General conditions.
25 of 64 | DOCUMENTS PROVIDED BY CONTRACTOR/ SUBCONTRACTORS/SUPPLIERS
510 DESIGN AND PRODUCTION INFORMATION
 Master programme: Make reasonable allowance for completing design/ production information, submission (including to the CDM Principal Designer), comment, inspection, amendment, resubmission and re-inspection.
 Design/ production information: Submit two copies, one could be returned with comments and this will be deemed to be a direction, notice or instruction under the Contract. Ensure that any necessary amendments are made without delay and resubmit unless it is confirmed that it is not required.
 Contractor's changes to Schedule of Works and Specification: Support request for substitution or variation with all relevant information.
 Employer's amendments to Schedule of Works: If considered to involve a variation, which has not already been acknowledged as a variation, notify without delay (maximum period 7 days), and do not proceed until instructed. Claims for extra cost, if made after it has been carried out, may not be allowed.
 Final version of design/ production information: Submit three copies, one in PDF format.
550 NAMED SUBCONTRACTORS: DESIGN AND PRODUCTION INFORMATION
 General: Certain Subcontractors are/ will be required to provide design/ production information during the contract as described in the Conditions of Contract, clause 3.7.
 Master programme: Make reasonable allowance, based on information in section A30, for completing design/ production information, checking, submission (including to the CDM PD), comment, inspection, amendment, resubmission and re-inspection.
 Information from Subcontractors:
 Obtain in time to meet the programme and in accordance with NAM/T where applicable.
 Check dimensions are correct, account is taken of all related work, and construction is practicable. Note any comments on one copy of the design/ production information, then submit with the required number of additional unmarked copies. Such checking will not relieve the Employer or Employers professional team or the Subcontractors of their respective responsibilities for design, co- ordination and documentation.
 Inspection and comments: One copy will be marked and returned to Contractor. This will not relieve the Subcontractors of their responsibility for design and documentation. Ensure that any necessary amendments are made without delay and resubmit unless it is confirmed that it is not required.
 Final version of information: Distribute copies to all affected Subcontractors and others and keep one copy on site.
 Submit three copies.
600 CONTRACTOR'S DESIGN INFORMATION
 General: Complete the design and detailing of parts of the Works as specified.
 Provide:
 Production information based on the drawings, specification and other information.
 Liaison to ensure coordination of the work with related building elements and services.
 Master programme: Make reasonable allowance for completing design/ production information, submission (including to the CDM PD), comment, inspection, amendment, resubmission and re-inspection.
26 of 64 |  Information required: All design information set out in Schedules of Works for each
block.
 Format: Electronic.
 Number of copies: One.
 Submit: Within one week of request.
610 PRODUCTION INFORMATION
 Contractor/ Domestic subcontractor provide:
1. Shop drawings.
2. Fixing details
3. Services co-ordination drawings.
4. Services controls drawings.
5. Builder's work information for services. .
 Submit:
 For comment and make any necessary amendments.
 Sufficient copies of final version for distribution to all affected parties.
620 AS BUILT DRAWINGS AND INFORMATION
 Contractor designed work: Provide drawings/ information: - as 610.
 Submit: At least two weeks before date for completion.
630 TECHNICAL LITERATURE
 Information: Keep on site for reference by all supervisory personnel:
 Manufacturers' current literature relating to all products to be used in the Works.
 Relevant British, EN or ISO Standards.
640 MAINTENANCE INSTRUCTIONS AND GUARANTEES
 Components and equipment: Obtain or retain copies, register with manufacturer and hand over on or before completion of the Works.
 Information location: In Building Manual.
 Emergency call out services: Provide telephone numbers for use after completion. Extent of cover: twenty four hours week days only.
27 of 64 | A32 MANAGEMENT OF THE WORKS
GENERALLY
110 SUPERVISION
 General: Accept responsibility for coordination, supervision and administration of the Works, including subcontracts. The contractor shall provide a full time site manager whose duty will be part of the contractor’s management team but who will be responsible for site management and supervision in particular. The site manager shall not have any other duties (e.g.: as a working tradesman/ site operative). On this project the contractor shall also provide a separate resident liaison officer who may not be the same person as the site manager in this instance.
 Coordination: Arrange and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work.
112A CONSIDERATE CONSTRUCTORS SCHEME or EQUIVALENT
 Registration: Before starting work, register the site and pay the appropriate fee: Contact:
Address: Considerate Constructors Scheme Office, PO Box 75, Great Amwell, Ware, Hertfordshire, SG12 0YX.
Tel. 01920 485959.
Fax. 01920 485958.
Free phone 0800 7831423 Web. www.ccscheme.org.uk
E mail. enquiries@ccscheme.org.uk
Standard: Comply with the Scheme's Code of Considerate Practice. Minimum compliance level: basic compliance.
Evidence: Before starting work on site submit details, and/ or policies and receipts for the insurances required by the Conditions of Contract.
120 INSURANCE
 Documentary evidence: Before starting work on site submit details, and/ or policies and receipts for the insurances required by the Conditions of Contract.
130 INSURANCE CLAIMS
 Notice: If any event occurs which may give rise to any claim or proceeding in respect of loss or damage to the Works or injury or damage to persons or property arising out of the Works, immediately give notice to the Employer, the person named in clause A10/140 and the Insurers.
 Failure to notify: Indemnify the Employer against any loss, which may be caused by failure to give such notice.
140 CLIMATIC CONDITIONS
 Information: Record accurately and retain:
 Daily maximum and minimum air temperatures (including overnight).
 Delays due to adverse weather, including description of the weather, types of work affected and number of hours lost.
28 of 64 | 150 OWNERSHIP
 Alteration/ clearance work: Materials arising become the property of the Contractor except where otherwise stated. Remove from site as work proceeds.
PROGRAMME/ PROGRESS
210 PROGRAMME
 Master programme: When requested and before starting work on site, submit in an approved form a master programme for the Works, which must include details of:
 Design, production information and proposals provided by the Contractor/ Subcontractors/ Suppliers, including inspection and checking (see section A31).
 Planning and mobilization by the Contractor.
 Earliest and latest start and finish dates for each activity and identification of all critical activities.
 Running in, adjustment, commissioning and testing of all engineering services and installations
 Work resulting from instructions issued in regard to the expenditure of provisional sums (see section A54)
 Work by or on behalf of the Employer and concurrent with the Contract (see section A50). The nature and scope of which, the relationship with preceding and following work and any relevant limitations are suitably defined in the Contract Documents.
 Exclusions: Where and to the extent that the programme implications for work which is not so defined are impossible to assess, the Contractor should exclude it and confirm this when submitting the programme.
 Submit: three copies.
230 SUBMISSION OF PROGRAMME
 Further information: Submission of the programme will not relieve the Contractor of the responsibility to advise of the need for further drawings or details or instructions in accordance with the Contract.
240 COMMENCEMENT OF WORK
 Notice: Before the proposed date for commencement of work on site give minimum notice of two weeks.
250 MONITORING
 Progress: Record on a copy of the programme kept on site.
 Avoiding delays: If any circumstances arise which may affect the progress of the Works submit proposals or take other action as appropriate to minimize any delay and to recover any lost time.
 Key Performance Indicators:
 Details: Appointment kept with residents (100%), number of complaints from residents (Target zero).
 Record progress against each of the KPIs. If performance against KPI falls short of target, submit proposals for remediation.
260 SITE MEETINGS
 General: Site meetings will be held to review progress and other matters arising from administration of the Contract.
 Frequency: Every month.
 Location: On site.
 Accommodation: Ensure availability at the time of such meetings.
29 of 64 |  Attendees: Attend meetings and inform subcontractors and suppliers when their
presence is required.
 Chairperson (who will also take and distribute minutes): Employer’s appointed professional team.
265 CONTRACTOR'S PROGRESS REPORT
 General: Submit a progress report at least three days before the site meeting.
 Content: Notwithstanding the Contractor's obligations under the Contract the report must include:
 A progress statement by reference to the master programme for the Works.
 Details of any matters materially affecting the regular progress of the Works.
 Subcontractors' and suppliers' progress reports.
 Any requirements for further drawings or details or instructions to fulfil any obligations under the Conditions of Contract.
270 CONTRACTOR'S SITE MEETINGS
 General: Hold meetings with appropriate subcontractors and suppliers shortly before main site meetings to facilitate accurate reporting of progress.
285 PARTIAL POSSESSION BY EMPLOYER
 Clause 2.25 of Conditions of Contract: Ensure all necessary access, services and other associated facilities are also complete.
290 NOTICE OF COMPLETION
 Requirement: Give notice of the anticipated dates of completion of the whole or parts of the Works.
 Associated works: Ensure necessary access, services and facilities are complete.
 Period of notice (minimum): Two weeks.
310 EXTENSIONS OF TIME
 Notice: When a notice of the cause of any delay or likely delay in the progress of the works is given under the contract, written notice must also be given of all other causes which apply concurrently.
 Details: As soon as possible submit:
 Relevant particulars of the expected effects, if appropriate, related to the concurrent causes.
 An estimate of the extent, if any, of the expected delay in the completion of the Works beyond the date for completion.
 All other relevant information required.
CONTROL OF COST
410 CASH FLOW FORECAST
 Submission: Before starting work on site, submit a forecast showing the gross valuation of the Works at the date of each Interim Certificate throughout the Contract period. Base on the programme for the Works.
420 REMOVAL/ REPLACEMENT OF EXISTING WORK
 Extent and location: Agree before commencement.
 Execution: Carry out in ways that minimize the extent of work.
430 PROPOSED INSTRUCTIONS
30 of 64 |  Estimates: If a proposed instruction requests an estimate of cost, submit without delay
and in any case within seven days.
 Include:
 A detailed breakdown of the cost, including any allowance for direct loss and expense.
 Details of any additional resources required.
 Details of any adjustments to be made to the programme for the Works.
 Any other information as is reasonably necessary to fully assess the implications of issuing such an instruction.
 Inability to comply: Inform immediately if it is not possible to comply with any of the above requirements.
440 MEASUREMENT
 Covered work: Give notice before covering work required to be measured.
450 DAYWORK VOUCHERS
 Before commencing work: Give reasonable notice to person countersigning Daywork vouchers.
 Content: Before delivery each voucher must be:
 Referenced to the instruction under which the work is authorised.
 Signed by the Contractor's person in charge as evidence that the operatives' names, the time daily spent by each and the equipment and products employed are correct. Daywork will only be permitted with prior written approval of the CA. Daywork vouchers must be submitted contemporaneously. Failure to do so will render them invalid and the method of valuation/payment will be at the Employer’s discretion
 Submit: By the end of the week in which the work has been executed.
470 PRODUCTS NOT INCORPORATED INTO THE WORKS
 Ownership: At the time of each valuation, supply details of those products not incorporated into the Works which are subject to any reservation of title inconsistent with passing of property as required by the Conditions of Contract, together with their respective values.
 Evidence: When requested, provide evidence of freedom of reservation of title.
475 LISTED PRODUCTS STORED OFF SITE
 Note - For avoidance of doubt no payments will be made for any materials not delivered to site, and where delivered to site must be at an appropriate stage in the programme and thoroughly protected.
480 LABOUR AND EQUIPMENT RETURNS
 Records: Provide for verification at the beginning of each week in respect of each of the previous seven days.
 Records must show:
 The number and description of craftsmen, labourers and other persons directly or indirectly employed on or in connection with the Works or Services, including those employed by subcontractors.
 The number, type and capacity of all mechanical, electrical and power- operated equipment employed in connection with the Works or Services
31 of 64 | A33 QUALITY STANDARDS/ CONTROL
STANDARDS OF PRODUCTS AND EXECUTIONS
110 INCOMPLETE DOCUMENTATION
 General: Where and to the extent that products or work are not fully documented, they are to be:
 Of a kind and standard appropriate to the nature and character of that part of the Works where they will be used.
 Suitable for the purposes stated or reasonably to be inferred from the project documents. Contract documents: Omissions or errors in description and/ or quantity shall not vitiate the Contract nor release the Contractor from any obligations or liabilities under the Contract.
120 WORKMANSHIP SKILLS
 Operatives: Appropriately skilled and experienced for the type and quality of work.
 Registration: With Construction Skills Certification Scheme.
 Evidence: Operatives must produce evidence of skills/ qualifications when requested.
130 QUALITY OF PRODUCTS
 Generally: New. (Proposals for recycled products may be considered).
 Supply of each product: From the same source or manufacturer.
 Whole quantity of each product required to complete the Works: Consistent kind, size, quality and overall appearance.
 Tolerances: Where critical, measure a sufficient quantity to determine compliance.
 Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate sequence.
135 QUALITY OF EXECUTION
 Generally: Fix, apply, install or lay products securely, accurately, plumb, neatly and in alignment.
 Colour batching: Do not use different colour batches where they can be seen together.
 Dimensions: Check on-site dimensions.
 Finished work: Not defective, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance.
 Location and fixing of products: Adjust joints open to view so they are even and regular.
140 COMPLIANCE
 Compliance with proprietary specifications: Retain on site evidence that the proprietary product specified has been supplied.
 Compliance with performance specifications: Submit evidence of compliance, including test reports indicating:
 Properties tested.
 Pass/ fail criteria.
 Test methods and procedures.
 Test results.
 Identity of testing agency.
 Test dates and times.
 Identities of witnesses.
 Analysis of results.
32 of 64 | 150 INSPECTIONS
 Products and executions: Inspection or any other action must not be taken as approval unless confirmed in writing referring to:
 Date of inspection.
 Part of the work inspected.
 Respects or characteristics which are approved.
 Extent and purpose of the approval.
 Any associated conditions.
160 RELATED WORK
 Details: Provide all trades with necessary details of related types of work. Before starting each new type or section of work ensure previous related work is:
 Appropriately complete.
 In accordance with the project documents.
 To a suitable standard.
 In a suitable condition to receive the new work.
 Preparatory work: Ensure all necessary preparatory work has been carried out.
170 MANUFACTURER'S RECOMMENDATIONS/ INSTRUCTIONS
 General: Comply with manufacturer's printed recommendations and instructions current on the date of the Invitation to tender.
 Changes to recommendations or instructions: Submit details.
 Ancillary products and accessories: Use those supplied or recommended by main product manufacturer.
 Agrément certified products: Comply with limitations, recommendations and requirements of relevant valid certificates.
180 WATER FOR THE WORKS
 Mains supply: Clean and uncontaminated. Arrange for temporary supply and pay all fixed and ongoing charges in connection, remove on completion. Make good all surfaces.
 Other: Do not use until:
 Evidence of suitability is provided.
 Tested to BS EN 1008 if instructed.
SAMPLES/ APPROVALS
210 SAMPLES
 Products or executions: Comply with all other specification requirements and in respect of the stated or implied characteristics either:
 To an express approval.
 To match a sample expressly approved as a standard for the purpose.
220 APPROVAL OF PRODUCTS
 Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.
 Approval: Relates to a sample of the product and not to the product as used in the Works. Do not confirm orders or use the product until approval of the sample has been obtained.
 Complying sample: Retain in good, clean condition on site. Remove when no longer required.
33 of 64 | 230 APPROVAL OF EXECUTION
 Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.
 Approval: Relates to the stated characteristics of the sample. (If approval of the finished work as a whole is required this is specified separately). Do not conceal, or proceed with affected work until compliance with requirements is confirmed.
 Complying sample: Retain in good, clean condition on site. Remove when no longer required.
ACCURACY/ SETTING OUT GENERALLY
320 SETTING OUT
 General: Submit details of methods and equipment to be used in setting out the Works.
 Levels and dimensions: Check and record the results on a copy of drawings. Notify discrepancies and obtain instructions before proceeding.
 Inform: When complete and before commencing construction.
330 APPEARANCE AND FIT
 Tolerances and dimensions: If likely to be critical to execution or difficult to achieve, as early as possible either:
 Submit proposals; or
 Arrange for inspection of appearance of relevant aspects of partially finished work.
 General tolerances (maximum): To BS 5606, tables 1 and 2.
360 RECORD DRAWINGS
 Site setting out drawing: Record details of all grid lines, setting-out stations, benchmarks and profiles. Retain on site throughout the contract and hand over on completion in PDF format and one hard copy.
SERVICES GENERALLY
410 SERVICES REGULATIONS
 New or existing services: Comply with the Byelaws or Regulations of the relevant Statutory Authority.
420 WATER REGULATIONS/ BYELAWS NOTIFICATION
 Requirements: Notify Water Undertaker of any work carried out to or which affects new or existing services and submit any required plans, diagrams and details.
 Consent: Allow adequate time to receive Undertaker's consent before starting work. Inform immediately if consent is withheld or is granted subject to significant conditions.
435 ELECTRICAL INSTALLATION CERTIFICATE
 Submit: When relevant electrical work is completed.
 Original certificate: To be lodged in the Building Manual.
 NB Installation Certificates are required accepting responsibility for all aspects of the new works i.e. design, construction and inspection and test, as indicated in BS7671, and part P of the building Regulations.
 Provide details of the qualifications of each person signing the certificates e.g. Electrical apprenticeship, J.I.B. card (Electro technical Certification), City & Guilds 2391, etc. unless that person is a qualified supervisor for NICEIC, NAPIT or ECA etc.
34 of 64 | 440 GAS, OIL AND SOLID FUEL APPLIANCE INSTALLATION
CERTIFICATE
 Before the completion date stated in the Contract: Submit a certificate stating:
 The address of the premises.
 A brief description of the new installation and/ or work carried out to an existing installation.
 Any special recommendations or instructions for the safe use and operation of appliances and flues.
 The Contractor's name and address.
 A statement that the installation complies with the appropriate safety, installation and use regulations.
 The name, qualification and signature of the competent person responsible for checking compliance.
 The date on which the installation was checked.
 A CP12 certificate must be provided for each flat in addition to any installation and commissioning certificates. Pay all charges in connection with preparation and issue of these certificates.
 Certificate location: Health and Safety File. CP12, copied to H&S File, separately issued originals to CA.
445 SERVICE RUNS
 General: Provide adequate space and support for services, including unobstructed routes and fixings.
 Ducts, chases and holes: Form during construction rather than cut.
 Coordination with other works: Submit details of locations, types/ methods of fixing of services to fabric and identification of runs and fittings.
450 MECHANICAL AND ELECTRICAL SERVICES
 Final tests and commissioning: Carry out so that services are in full working order at completion of the Works.
 Building Regulations notice: Copy to be lodged in the Building Manual.
SUPERVISION/ INSPECTION/ DEFECTIVE WORK
510 SUPERVISION
 General: In addition to the constant management and supervision of the Works provided by the Contractor's person in charge, all significant types of work must be under the close control of competent trade supervisors to ensure maintenance of satisfactory quality and progress.
 Replacement: Give maximum possible notice before changing person in charge or site agent.
520 COORDINATION OF ENGINEERING SERVICES
 Suitability: Site organisation staff must include one or more persons with appropriate knowledge and experience of mechanical and electrical engineering services to ensure compatibility between engineering and the Works generally.
 Evidence: Submit when requested CVs or other documentary evidence relating to the staff concerned.
35 of 64 | 530 OVERTIME WORKING
 Notice: Prior to overtime being worked, submit details of times, types and locations of work to be done.
 Minimum period of notice: Two days.
 Concealed work: If executed during overtime for which notice has not been given, it may be required to be opened up for inspection and reinstated at the Contractor's expense.
540 DEFECTS IN EXISTING WORK
 Undocumented defects: When discovered, immediately give notice. Do not proceed with affected related work until response has been received.
 Documented remedial work: Do not execute work which may:
 Hinder access to defective products or work; or
 Be rendered abortive by remedial work.
550 ACCESS FOR INSPECTION
 Removal: Before removing scaffolding or other facilities for access, give notice of not less than two days.
560 TESTS AND INSPECTIONS
 Timing: Agree and record dates and times of tests and inspections to enable all affected parties to be represented.
 Confirmation: One working day prior to each such test or inspection. If sample or test is not ready, agree a new date and time.
 Records: Submit a copy of test certificates and retain copies on site.
610 PROPOSALS FOR RECTIFICATION OF DEFECTIVE PRODUCTS/EXECUTIONS
 Proposals: Immediately any work or product is known, or appears, to be not in accordance with the Contract, submit proposals for opening up, inspection, testing, making good, adjustment of the Contract Sum, or removal and re-execution.
 Acceptability: Such proposals may be unacceptable and contrary instructions may be issued.
620 MEASURES TO ESTABLISH ACCEPTABILITY
 General: Wherever inspection or testing shows that the work, materials or goods are not in accordance with the contract and measures (e.g. testing, opening up, experimental making good) are taken to help in establishing whether or not the work is acceptable, such measures:
 Will be at the expense of the Contractor.
 Will not be considered as grounds for revision of the completion date.
630 QUALITY CONTROL
 Procedures: Establish and maintain to ensure that the Works, including the work of subcontractors, comply with specified requirements.
 Records: Maintain full records, keep copies on site for inspection, and submit copies on request.
 Content of records:
 Identification of the element, item, batch or lot including location in the Works.
 Nature and dates of inspections, tests and approvals.
 Nature and extent of nonconforming work found.
 Details of corrective action.
36 of 64 | WORK AT OR AFTER COMPLETION
710 WORK BEFORE COMPLETION
 General: Make good all damage consequent upon the Works. Temporary markings, coverings and protective wrappings: Remove unless otherwise instructed.
 Cleaning: Clean the Works thoroughly inside and out, including all accessible ducts and voids. Remove all splashes, deposits, and efflorescence, rubbish and surplus materials.
 Cleaning materials and methods: As recommended by manufacturers of products being cleaned, and must not damage or disfigure other materials or construction.
 COSHH dated data sheets: Obtain for all materials used for cleaning and ensure they are used only as recommended by their manufacturers.
 Minor faults: Touch up in newly painted work, carefully matching colour and brushing out edges. Repaint badly marked areas back to suitable breaks or junctions.
 Moving parts of new work: Adjust, ease and lubricate as necessary to ensure easy and efficient operation, including doors, windows, drawers, ironmongery, appliances, valves and controls.
720 SECURITY AT COMPLETION
 General: Leave the Works secure with, where appropriate, all accesses closed and locked.
 Keys: Account for and adequately label all keys and hand over to Employer with itemized schedule, retaining duplicate schedule signed by Employer as a receipt.
730 MAKING GOOD DEFECTS
 Remedial work: Arrange access with Employer.
 Rectification: Give reasonable notice for access to the various parts of the Works.
 Completion: Notify when remedial works have been completed.
37 of 64 | A34 SECURITY/ SAFETY/ PROTECTION
SECURITY, HEALTH AND SAFETY
110 PRECONSTRUCTION INFORMATION
 Location: Integral with the project Preliminaries, including but not restricted to the following sections:
 Description of project: Sections A10 and A11.
 Client's consideration and management requirements: Sections A12, A13 and A36.
 Environmental restrictions and on-site risks: Section A12, A35 and A34.
 Significant design and construction hazards: Section A34.
 The Health and Safety File: Section A37.
140 CONSTRUCTION PHASE HEALTH AND SAFETY PLAN
 Submission: Present to the Employer/ Client no later than 2 weeks prior to commencement on site.
 Confirmation: Do not start construction work until the Employer has confirmed in writing that the Construction Phase Health and Safety Plan includes the procedures and arrangements required by the CDM Regulations.
 Content: Develop the plan from and draw on the Outline Construction Phase Health and Safety Plan, clause A30/570, and the Pre-tender Health and Safety Plan/ Preconstruction information.
150 SECURITY
 Protection: Safeguard the site, the Works, products, materials, and any existing buildings affected by the Works from damage and theft.
 Access: Take all reasonable precautions to prevent unauthorized access to the site, the Works and adjoining property.
 Special requirements: provision of security guards required over Bank holidays and any long term site closures.
160 STABILITY
 Responsibility: Maintain the stability and structural integrity of the Works and adjacent structures during the Contract.
 Design loads: Obtain details, support as necessary and prevent overloading.
170 OCCUPIED PREMISES
 Extent: Existing buildings will be occupied and/ or used during the Contract as follows: The remaining and adjacent blocks and retail units.
 Works: Carry out without undue inconvenience and nuisance and without danger to occupants and users.
 Overtime: If compliance with this clause requires certain operations to be carried out during overtime, and such overtime is not required for any other reason, the extra cost will be allowed, provided that such overtime is authorized in advance.
180 ACCESS CONTROL
 Controlled areas: The remainder of the block not forming part of the site.
 Control type: Access fob obtained from the Council.
 Authorised persons: Submit a list of the names of all persons requiring passes together with any other related information reasonably required.
 Return of control keys: When requested or on completion of the work to which the controlled area relates.
38 of 64 | 200 MOBILE TELEPHONES AND PORTABLE ELECTRONIC EQUIPMENT
 Restrictions on use: - None.
210 EMPLOYER'S REPRESENTATIVES SITE VISITS
 Safety: Submit details in advance, to the Employer or the person identified in clause A10/140, of safety provisions and procedures (including those relating to materials, which may be deleterious), which will require their compliance when visiting the site.
 Protective clothing and/ or equipment: Provide and maintain on site for the Employer and the person stated in clause A10/140 and other visitors to the site.
PROTECT AGAINST THE FOLLOWING
310 EXPLOSIVES
 Use: Not permitted
330 NOISE AND VIBRATION
 Standard: Comply with the recommendations of BS 5228-1, in particular clause 7.3, to minimize noise levels during the execution of the Works.
 Noise levels from the Works: Maximum level: 70 dB (A) when measured from 1m from site boundary.
 Equipment: Fit compressors, percussion tools and vehicles with effective silencers of a type recommended by manufacturers of the compressors, tools or vehicles.
 Restrictions: Do not use:
 Percussion tools and other noisy appliances without consent during the hours of Pneumatic drills and other noisy work only after 8.30am and before 4.30pm. Allow 1 hour no noisy works rest period between 12.30 – 1.30pm.
 Radios or other audio equipment or permit employees to use in ways or at times that may cause nuisance.
340 POLLUTION
 Prevention: Protect the site, the Works and the general environment including the atmosphere, land, streams and waterways against pollution.
 Contamination: If pollution occurs inform immediately, including to the appropriate Authorities and provide relevant information.
350 PESTICIDES
 Use: Not permitted.
360 NUISANCE
 Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes.
 Surface water: Prevent hazardous build-up on site, in excavations and to surrounding areas and roads.
370 ASBESTOS CONTAINING MATERIALS
 Duty: Report immediately any suspected materials discovered during execution of the Works.
 Do not disturb.
 Agree methods for safe removal or encapsulation.
371 DANGEROUS OR HAZARDOUS SUBSTANCES
 Duty: Report immediately suspected materials discovered during execution of the Works.
 Do not disturb.
39 of 64 |  Agree methods for safe removal or remediation.
380 FIRE PREVENTION
 Duty: Prevent personal injury or death, and damage to the Works or other property from fire.
 Standard: Comply with Joint Code of Practice 'Fire Prevention on Construction Sites', published by the Construction Confederation and The Fire Protection Association (The 'Joint Fire Code').
390 SMOKING ON SITE
 Smoking on site: Not permitted.
400 BURNING ON SITE
 Burning on site: Not permitted.
410 MOISTURE
 Wetness or dampness: Prevent, where this may cause damage to the Works.
 Drying out: Control humidity and the application of heat to prevent:
 Blistering and failure of adhesion.
 Damage due to trapped moisture.
 Excessive movement.
420 INFECTED TIMBER/ CONTAMINATED MATERIALS
 Removal: Where instructed to remove material affected by fungal/ insect attack from the building, minimize the risk of infecting other parts of the building.
 Testing: carry out and keep records of appropriate tests to demonstrate that hazards presented by concentrations of airborne particles, toxins and other micro-organisms are within acceptable levels.
430 WASTE
 Includes: Rubbish, debris, spoil, surplus material, containers and packaging.
 General: Minimize production. Prevent accumulations. Keep the site and Works clean and tidy.
 Handling: Collect and store in suitable containers. Remove frequently and dispose off site in a safe and competent manner:
 Non-hazardous material: In a manner approved by the Waste Regulation Authority.
 Hazardous material: As directed by the Waste Regulation Authority and in accordance with relevant regulations.
 Recyclable material: Sort and dispose at a Materials Recycling Facility approved by the Waste Regulation Authority.
 Voids and cavities in the construction: Remove rubbish, dirt and residues before closing in.
 Waste transfer documentation: Retain on site.
440 ELECTROMAGNETIC INTERFERENCE
 Duty: Prevent excessive electromagnetic disturbance to apparatus outside the site.
450 LASER EQUIPMENT
 Construction laser equipment: Install, use and store in accordance with BS EN 60825- 1 and the manufacturer's instructions.
 Class 1 or Class 2 laser equipment: Ensure laser beam is not set at eye level and is terminated at the end of its useful path.
40 of 64 |  Class 3A and Class 3B laser equipment: Do not use without approval and subject to
submission of a method statement on its safe use.
460 POWER ACTUATED FIXING SYSTEMS
 Use: Not permitted.
PROTECT THE FOLLOWING
510 EXISTING SERVICES
 Confirmation: Notify all service authorities, statutory undertakers and/ or adjacent owners of proposed works not less than one week before commencing site operations.
 Identification: Before starting work, check and mark positions of utilities/ services. Where positions are not shown on drawings obtain relevant details from service authorities, statutory undertakers or other owners.
 Work adjacent to services:
 Comply with service authority's/ statutory undertaker's recommendations.
 Adequately protect, and prevent damage to services: Do not interfere with their operation without consent of service authorities/ statutory undertakers or other owners.
 Identifying services:
 Below ground: Use signboards, giving type and depth;
 Overhead: Use headroom markers.
 Damage to services: If any results from execution of the Works:
 Immediately give notice and notify appropriate service authority/ statutory undertaker.
 Make arrangements for the work to be made good without delay to the satisfaction of service authority/ statutory undertaker or other owner as appropriate.
 Any measures taken to deal with an emergency will not affect the extent of the Contractor's liability.
 Marker tapes or protective covers: Replace, if disturbed during site operations, to service authority's/ statutory undertakers recommendations.
520 ROADS AND FOOTPATHS
 Duty: Maintain roads and footpaths within and adjacent to the site and keep clear of mud and debris.
 Damage caused by site traffic or otherwise consequent upon the Works: Make good to the satisfaction of the Employer, Local Authority or other owner.
540 RETAINED TREES/ SHRUBS/ GRASSED AREAS
 Protection: Preserve and prevent damage, except those not required.
 Replacement: Mature trees and shrubs if uprooted, destroyed, or damaged beyond reasonable chance of survival in their original shape, as a consequence of the Contractor's negligence, must be replaced with those of a similar type and age at the Contractor's expense.
550 RETAINED TREES
 Protected area: Unless agreed otherwise do not:
 Dump spoil or rubbish, excavate or disturb topsoil, park vehicles or plant, store materials or place temporary accommodation within an area which is the larger of the branch spread of the tree or an area with a radius of half the tree's height, measured from the trunk.
 Sever roots exceeding 25 mm in diameter. If unintentionally severed give notice and seek advice.
 Change level of ground within an area 3 m beyond branch spread.
41 of 64 | 570 EXISTING WORK
 Protection: Prevent damage to existing work, structures or other property during the course of the work.
 Removal: Minimum amount necessary.
 Replacement work: To match existing.
580 BUILDING INTERIORS
 Protection: Prevent damage from exposure to the environment, including weather, flora, fauna, and other causes of material degradation during the course of the work.
600 EXISTING FURNITURE, FITTINGS AND EQUIPMENT
 Protection: Prevent damage or move as necessary to enable the Works to be executed. Reinstate in original positions.
 Extent: Before work in each room starts the Employer will remove all items other than the following: - -.
625 ADJOINING PROPERTY RESTRICTIONS
 Precautions:
 Prevent trespass of workpeople and take precautions to prevent damage to adjoining property.
 Pay all charges.
 Remove and make good on completion or when directed.
 Damage: Bear cost of repairing damage arising from execution of the Works.
630 EXISTING STRUCTURES
 Duty: Check proposed methods of work for effects on adjacent structures inside and outside the site boundary.
 Supports: During execution of the Works:
 Provide and maintain all incidental shoring, strutting, needling and other supports as may be necessary to preserve stability of existing structures on the site or adjoining that may be endangered or affected by the Works.
 Do not remove until new work is strong enough to support existing structure.
 Prevent overstressing of completed work when removing supports.
 Adjacent structures: Monitor and immediately report excessive movement.
 Standard: Comply with BS 5975 and BS EN 12812.
640 MATERIALS FOR RECYCLING/ REUSE
 Duty: Sort and prevent damage to stated products or materials, clean off bedding and jointing materials and other contaminants.
 Storage: Stack neatly and protect until required by the Employer or for use in the Works as instructed.
650 CODE OF CONDUCT FOR SITE OPERATIVES WORKING ON CAMDEN PREMISES
 This Code has been prepared to promote reliability and efficiency, facilitate the confidence and trust of occupiers, ensure good practice and standards, and maintain a quality service to the occupiers to guarantee integrity with the occupiers. All Contractor's and subcontractor's operatives and employees must follow this Code when working on this Estate.
Identification
 The contractor must wear an identification card, which shows their name and photograph and the name and telephone number of the Contractor they work for. Contractor’s operatives must also have work wear displaying the contractor’s logo.
42 of 64 | Access to the Site
 All contractors must sign in at the site compound.
Access to flats and lobbies
 The Contractor must ensure that they adhere to the arrangements that have been made by the RLO and that they are punctual.
Movement of Materials
 All redundant/waste materials are to be moved off site via the scaffolding, hoists and balconies to place of disposal. New materials being installed are to be moved via the scaffolding, hoists and balconies to the place of work. Glazing units for new windows to be moved into position from the scaffolding and balconies and lifted through window openings to the interior prior to fixing with internal beads. The contractor must not use the lift/staircases for internal movement of materials, stores plant and equipment. All internal areas used or worked in by the contractor must be protected with clean dustsheets laid over any the carpets and other finishes, with Corex in addition where required.
Protection of Occupier's Property
 The Contractor must ensure that suitable protection is arranged for the occupier's property and that delicate or valuable items are removed from the work area. Always use clean dustsheets.
Disruption
 The Contractor must ensure there is minimum disruption to the occupiers. Ensure communal areas and entrances are left clear and tidy.
Damage to Occupier's Property
 Protecting the concerns of occupiers during the works, and ensure that any damage caused to occupier's property is dealt with expeditiously. It is a condition of contract that where damage is caused to occupier's property (which will include personal property such as furniture as well as the internal structure of the building), the Contractor must within 7 days report in writing to the Employer’s Agent with his proposed course of action for remedying the damage. Failure to do so could result in an instruction from the EA to compensate the occupier immediately.
Health & Safety
 The site must be kept safe at all times. Fire exits, lifts, staircases, corridors and doorways must be kept clear and not blocked by the Contractor's tools or materials.
Nuisance
 Noise dirt and other nuisances must be kept to a minimum so as not to inconvenience other residents. Flat entrance doors must be kept closed whilst works are in progress and dustsheets must be positioned in the communal hallways.
Removal of Contractor’s Waste
 All existing materials removed, glass, contractors rubbish, rubble and other waste materials must be removed to the contractor’s skip on a daily basis using the access scaffold where required. It must not be stored on the scaffold or balconies for removal later or removed through the common parts. All internal and external areas affected by the works are to be swept clean at the end of each working day. The use of the estate refuse area is strictly forbidden and the contractor shall only use the contractor’s designated waste area as agreed prior to the contract commencing.
43 of 64 | Damage
 Damage caused to walls, landing areas, lifts and/or lift well walls must be reinstated and/or cleaned by the Contractor. If the Contractor does not carry out reinstatement/cleaning within seven days of being requested to do so by the Council then the work will be carried out by the Council and charged to the Contractor.
Dress
 All Contractors’ operatives must have their torso fully covered at all times and use the correct PPE for the task that they are undertaking.
Radios or other musical equipment
 Not allowed
Eating
 All Contractor’s operatives must take their work breaks within the Contractor’s welfare facilities and away from the Common Areas including the garden areas. Contractor’s operatives are not allowed to smoke and/or eat in the Common Areas.
Absolute Respect
 The Contractor’s operatives must be polite and courteous to the occupiers and neighbours at all times. Racist or sexist remarks or innuendoes will result in the operative being removed from site immediately.
Parking
 Do not park in the resident’s parking spaces. Parking may be allocated to the contractor to be used for site set-up/storage purposes only. There is no provision on site for contractor’s parking. Operatives requiring vehicular access to offload tools, materials, etc. are required to remove vehicles from site and park in adjacent streets immediately after offloading/loading.
PAT Testing
 All Contractors must be able to produce certificates to show that any/all electrical equipment has been regularly checked and approved with PAT Certificates.
Dangerous Tools and Materials
 Keep sharp implements or materials and potentially dangerous tools close by the immediate area of work. Come to an arrangement with the occupier as to where such items can be safety kept out of harm's way and agree with the occupier how to keep children or pets away from the immediate vicinity of the works.
Awareness of Code of Conduct by Operatives
 The main contractor is to ensure that all his operatives and sub-contractor’s operatives are made aware of the above Code and have signed an acknowledgement to that effect. The Code must be provided to all operatives at site induction.
Contravention of Code of Conduct
 Any Contractor’s operatives contravening any of the above Code will be denied access to Estate to carry out work of any nature until the contravention has been rectified.
44 of 64 | A35 SPECIFIC LIMITATIONS ON METHOD/ SEQUENCE/TIMING
110 SCOPE
 General: The limitations described in this section are supplementary to limitations described or implicit in information given in other sections or on the drawings.
160 USE OR DISPOSAL OF MATERIALS
 Specific limitations: Areas for placement of skips are limited.
170 WORKING HOURS
 Specific limitations: Site work may commence at 7.30 am with the proviso that mechanical plant shall not be operated until 8.00 am. No work shall take place after
6.00 pm on weekdays, 1.00 pm on Saturdays and there shall be no work on Sundays unless by prior agreement of the Employer and providing no additional cost is incurred by the Employer. The only exception is where works have started in a flat and it is essential to complete an item of work to leave the premises secure and weathertight. However this is exceptional only and should be planned out. Any such occurrences will be at contractor’s expense. No work is permitted on Bank holidays.
180 COMPLETION IN SECTIONS OR IN PARTS
 General: Where the Employer is to take possession of any Section or part of the Works and such Section or part will, after its practical completion, depend for its adequate functioning on work located elsewhere on the site: Complete such other work in time to permit such possession to take place.
 Remainder of the Works: During execution, ensure that completed Sections or parts of the Works have continuous and adequate provision of services, fire precautions, means of escape and safe access.
45 of 64 | A36 FACILITIES/ TEMPORARY WORK/ SERVICES
GENERALLY
110 SPOIL HEAPS, TEMPORARY WORKS AND SERVICES
 Location: Give notice and details of intended siting.
 Maintenance: Alter, adapt and move as necessary. Remove when no longer required and make good.
ACCOMMODATION
210 ROOM FOR MEETINGS
 Facilities: Provide suitable temporary accommodation for site meetings, adequately heated and lit. The room may be part of the Contractor's own site offices.
 Furniture and Equipment: Provide table and chairs for 10 people.
230 TEMPORARY ACCOMMODATION
 Proposals for temporary accommodation and storage for the Works: Submit two weeks prior to starting on site.
 Details to be included: Type of accommodation and storage, its siting and the programme for site installation and removal.
260 SANITARY ACCOMMODATION
 Requirement: Provide sanitary accommodation for the Employer and other members of the consultant team, either separate or shared with the Contractor's supervisory staff. Maintain in clean condition and provide all consumables.
TEMPORARY WORKS
310 ROADS
 Permanent roads, hard standings and footpaths on the site: The following may be used, subject to clause A34/520:
 Details: Parking area for site compound, to north of main block only insofar as it does not disrupt day to day resident activities, refuse collection and emergency services.
 Restrictions on use: Use only for accessing site area for deliveries. No parking permitted. Do not block Fire Paths.
 Protective or remedial measures: Protect hard standing surfaces from damage where site accommodation is located. Remove all temporary protection at completion of works.
SERVICES AND FACILITIES
410 LIGHTING
 Finishing work and inspection: Provide temporary lighting, the intensity and direction of which closely resembles that delivered by the permanent installation.
440 TELEPHONES
 Temporary on site telephone: Provide as soon as practicable after the start on site for joint use by the Contractor and Subcontractors and pay all charges.
46 of 64 |  Responses: Make arrangements (e.g. an external bell) to ensure that incoming calls
are answered promptly.
530 BENEFICIAL USE OF INSTALLED SYSTEMS
 Permanent systems: Unless specific permission is given by the Employer and installer, do not use for any purpose other than running in, testing and commissioning.
 Other uses: If permission is given for any other use of a system before the Works are accepted as complete, it must be subject to a separate written agreement between the parties and in accordance with the recommended procedures given in NJCC Guidance Note 10.
540 METER READINGS
 Charges for service supplies: Where to be apportioned ensure that:
 Meter readings are taken by relevant authority at possession and/ or completion as appropriate.
 Copies of readings are supplied to interested parties.
550 THERMOMETERS
 General: Provide on-site and maintain in accurate condition a maximum and minimum thermometer for measuring atmospheric shade temperature, in an approved location.
570 PERSONAL PROTECTIVE EQUIPMENT
 General: Provide for the sole use of those acting on behalf of the Employer, in sizes to be specified:
 Safety helmets to BS EN 397, neither damaged nor time expired. Number required: 5.
 High visibility waistcoats to BS EN 471 Class 2. Number required: 5.
 Safety boots with steel insole and toecap to BS EN ISO 20345. Pairs required: 5.
 Disposable respirators to BS EN 149.FFP1S.
 Eye protection to BS EN 166.
 Ear protection - muffs to BS EN 352-1, plugs to BS EN 352-2
 Hand protection - to BS EN 388, 407, 420 or 511 as appropriate.
47 of 64 | A37 OPERATION/ MAINTENANCE OF THE FINISHED WORKS
GENERALLY
110 THE BUILDING MANUAL
 Purpose: The Manual is to be a comprehensive information source and guide for owners and users of the completed Works. It should provide an overview of the main design principles and describe key components and systems to enable proper understanding, efficient and safe operation and maintenance.
 Scope:
 Part 1: General: Content as clause 120.
 Part 2: Fabric: Content as clause 130.
 Part 3: Services: Content as clause 140.
 Part 4: The Health and Safety File: (prepared and supplied by the CDM PD). Content as clause 150.
 Part 5: Building User Guide: [Content as clause 151]
 Responsibility: The Building Manual is to be produced by Principal Contractor and must be complete no later than 2 weeks before the date of practical completion.
 Information provided by others: Details: None.
 Compilation:
 Prepare all information for Contractor designed or performance specified work including as-built drawings.
 Obtain or prepare all other information to be included in the Manual.
 Reviewing the Manual: Submit a complete draft. Amend in the light of any comments and resubmit. Do not proceed with production of the final copies until authorized.
 Final copies of the Manual:
 Number of copies: 3.
 Format: two paper and one digital pdf or similar format to be agreed with the CDM PD.
 Latest date for submission: 2 weeks before the date for completion stated in the contract.
 As-built drawings and schedules:
 Number of copies: 3.
 Format: two paper / one digital in AutoCAD. DWG (version 2004 or earlier) and pdf or similar format to be agreed with the CDM PD.
115 THE HEALTH AND SAFETY FILE
 Responsibility: the contractor.
 Content: Obtain and provide the following information: Included in Pre-Construction Information.
 Format: two ring binder copies and one electronic format in pdf or similar (agree format with CDM PD)
 Delivery to: CDM PD by: 2 weeks before practical completion of the Section.
120 CONTENT OF THE BUILDING MANUAL PART 1: GENERAL
 Content: Obtain and Provide the following, including all relevant details not included in other parts of the manual:
 Index: list the constituent parts of the manual, together with their location in the document.
 The Works:
 Description of the buildings and facilities.
 Ownership and tenancy, where relevant
48 of 64 |  Health and Safety information – other than that specifically required by the
Construction (Design and Management) Regulations.
 The Contract:
 Names and addresses and contact details of all significant consultants, contractors, subcontractors, suppliers and manufacturers.
 Overall design criteria.
 Environmental performance requirements
 Relevant authorities, consents and approvals.
 Third party certification, such as those made by competent persons in accordance with the Building Regulations
 Operational requirements and constraints of a general nature:
 Maintenance contracts and contractors.
 Fire safety strategy for the buildings and the site. Include drawings showing emergency escape and fire appliance routes, fire resisting doors location of emergency alarm and firefighting systems, services, shut off valves switches, etc.
 Emergency procedures and contact details in case of emergency.
 Other specific requirements: refer to CDM-PD.
 Description and location of other key documents.
 Timescale for completion: 2 weeks prior to practical completion of the Section.
130 CONTENT OF THE BUILDING MANUAL PART 2: BUILDING FABRIC
 Content: Obtain and Provide the following, including all relevant details not included in other parts of the manual:
 Detailed design criteria, including as appropriate and for example:
 Floor and roof loadings.
 Durability of individual components and elements.
 Loading restrictions.
 Insulation values.
 Fire ratings.
 Other relevant performance requirements.
 Construction of the building:
 A detailed description of methods and materials used.
 As-built drawings recording the construction, together with an index.
 Information and guidance concerning repair, renovation or demolition/ deconstruction.
 Periodic building maintenance guide chart.
 Inspection reports.
 Manufacturer's instructions index, including relevant COSHH data sheets and recommendations for cleaning, repair and maintenance of components.
 Fixtures, fittings and components schedule and index.
 Guarantees, warranties and maintenance agreements – obtain from manufacturers, suppliers and subcontractors.
 Test certificates and reports required in the specification or in accordance with legislation, including as appropriate to scope of works:
 Air permeability.
 Resistance to passage of sound.
 Continuity of insulation.
 Electricity and Gas safety. - -.
 Other specific requirements: None.
 Timescale for completion: 2 weeks prior to practical completion of the Section.
49 of 64 | 140 CONTENT OF THE BUILDING MANUAL PART 3: BUILDING SERVICES
 Content: Obtain and Provide the following, including all relevant details not included in other parts of the manual:
 Detailed design criteria and description of the systems, including:
 Services capacity, loadings and restrictions
 Services instructions.
 Services log sheets.
 Manufacturers' instruction manuals and leaflets index.
 Fixtures, fittings and component schedule index.
 Detailed description of methods and materials used.
 As-built drawings for each system recording the construction, together with an index, including:
 Diagrammatic drawings indicating principal items of plant, equipment and fittings
 Record drawings showing overall installation
 Schedules of plant, equipment, valves, etc. describing location, design performance and unique identification cross referenced to the record drawings.
 Identification of services – a legend for colour coded services.
 Product details, including for each item of plant and equipment:
 Name, address and contact details of the manufacturer.
 Catalogue number or reference
 Manufacturer's technical literature, including detailed operating and maintenance instructions.
 Information and guidance concerning dismantling, repair, renovation or decommissioning.
 Operation: A description of the operation of each system, including:
 Starting up, operation and shutting down
 Control sequences
 Procedures for seasonal changeover
 Procedures for diagnostics, troubleshooting and fault finding.
 Guarantees, warranties and maintenance agreements – obtain from manufacturers, suppliers and subcontractors.
 Commissioning records and test certificates list for each item of plant, equipment, valves, etc. used in the installations – including:
 Electrical circuit tests.
 Corrosion tests.
 Type tests.
 Work tests.
 Start and commissioning tests.
 Equipment settings: Schedules of fixed and variable equipment settings established during commissioning.
 Preventative maintenance: Recommendations for frequency and procedures to be adopted to ensure efficient operation of the systems
 Lubrication: Schedules of all lubricated items
 Consumables: A list of all consumable items and their source.
 Spares: A list of recommended spares to be kept in stock, being those items subject to wear and tear or deterioration and which may involve an extended delivery time when replacements are required.
 Emergency procedures for all systems, significant items of plant and equipment.
 Annual maintenance summary chart.
 Other specific requirements: -.
 Timescale for completion: 2 weeks prior to practical completion of the Section.
50 of 64 | 150 CONTENT OF THE BUILDING MANUAL PART 4: THE HEALTH AND SAFETY FILE
 Content: obtain and provide the following, including all relevant details not included in other parts of the manual, including:
 residual hazards and how they have been dealt with
 hazardous materials used
 information regarding the removal or dismantling of installed plant and equipment
 health and safety information about equipment provided for cleaning or maintaining the structure;
 the nature, location and markings of significant services,
 Information and as-built drawings of the structure, its plant and equipment - -.
 Information prepared by others: Details: -.
 Timescale for completion: 2 weeks prior to practical completion of the Section.
 Submit to: CDM PD.
151 CONTENT OF THE BUILDING MANUAL PART 5: THE BUILDING USER GUIDE
 Content: Obtain and provide the following:
 Building services information.
 Emergency information.
 Energy & environmental strategy.
 Water use.
 Transport facilities.
 Materials & waste policy.
 Re-fit/ re-arrangement considerations.
 Reporting provision.
 Training. -Links & references.
 Other specific requirements: - None
 Timescale for completion: 2 weeks prior to practical completion.
160 PRESENTATION OF BUILDING MANUAL
 Format: A4 size, plastics covered, loose leaf, four ring binders with hard covers, each indexed, divided and appropriately cover titled.
 Selected drawings needed to illustrate or locate items mentioned in the Manual: Where larger than A4, to be folded and accommodated in the binders so that they may be unfolded without being detached from the rings.
 As-built drawings: The main sets may form annexes to the Manual.
220 TRAINING
 Objective: Before Completion, explain and demonstrate to designate maintenance staff the purpose, function and operation of the installations including items and procedures listed in the Building Manual.
 Level of training -.
 Time allowance: Include a minimum of two days.
230 SPARE PARTS
 General: Before Completion submit a priced schedule of spare parts that the Contractor recommends should be obtained and kept in stock for maintenance of the services installations.
 Content: Include in the priced schedule for:
 Manufacturers' current prices, including packaging and delivery to site.
 Checking receipts, marking and numbering in accordance with the schedule of spare parts.
 Referencing to the plant and equipment list in Part 3 of the Building Manual.
 Painting, greasing, etc. and packing to prevent deterioration during storage.
51 of 64 |  Latest date for submission: Two weeks before completion.
250 TOOLS
 General: Provide tools and portable indicating instruments for the operation and maintenance of all services plant and equipment (except any installed under Named Subcontracts) together with suitable means of identifying, storing and securing.
 Quantity: Two complete sets.
 Time of submission: At completion.
52 of 64 | A40 CONTRACTOR’S GENERAL COST ITEMS: MANAGEMENT AND STAFF
110 MANAGEMENT AND STAFF
i. Cost significant items:
ii. Directors/Management
iii. Other Head Office Staff
iv. Contract Manager
v. Cost Manager (QS)
vi. Site Agent
| vii. Other Site based staff. | 43400
110A SITE ADMINISTRATION
 Provide a full time Project Manager on site who shall have charge of no other works. He should be a competent member of the Contractor's organisation able to fully organise the personnel and work on site. He is to be authorised to receive instructions from the Employer’s professional team as appropriate and implement them on behalf of the Contractor. Once designated this person is not to be removed without the consent of the Employer.
 Full time dedicated resident liaison officer.
 Provide an adequate site staff including, as necessary, resident engineers, project managers, agents, co-ordinators, setting out and services engineers, services co- ordinators, general, sectional and finishing foremen, site surveyors etc.
 Do not remove or replace key personnel without the express permission of the Employer. In the event of personnel impending complete termination of employment notify the Employer as soon as the fact is known and introduce a replacement on the Works at least one full month prior to the departure from the Works of the terminee.
 Submit with this tender a detailed staffing proposal identifying all key personnel including co-ordinators.
|  The Contractor will be responsible for keeping all persons under his control including men employed by sub-contractors within bounds and will be responsible for safety of the existing buildings, materials, plant, etc., and for all damage to premises and property, roads, footpaths, fences and gates workmen, lorries or from any other causes whatsoever | 136500
110B EMPLOYMENT OF LABOUR/INDUSTRIAL RELATIONS
 Provide an agent or foreman and a sufficient number of operatives for the proper, complete and expeditious execution of the Works and supply any cartage, workmanship and materials which, although not specifically mentioned, may be nevertheless incidentally necessary to the proper completion of the work described herein.
 Ensure that only trained, experienced and competent labour is used at all stages of work.
|  Ensure that the workforce conduct themselves in such a manner so as to avoid offence to third parties. The Employer shall have the right to require the removal of any workmen or supervisory staff that fail to achieve that level of conduct, whether employed directly by the Contractor or by his sub-contractors. | 35000
| To Collection | 214900
53 of 64 | A41 CONTRACTOR’S GENERAL COST ITEMS: SITE ACCOMMODATION
110 SITE ACCOMMODATION
 Details: Site accommodation required or made/ not made available by the Employer: See section A36.
 Cost significant items: See Section A36.
110B TEMPORARY ACCOMODATION AND FACILITIES
 Provide suitable and approved offices for all site staff and all other necessary temporary office and similar accommodation for site storage for materials, including those of specialist suppliers, which may be required and pay all charges connected therewith including all fees to Local Authorities.
 Allow for moving the temporary accommodation as necessary to meet the needs of the Works.
 Remove all temporary buildings on completion, reinstate the ground etc., and make good all works disturbed.
|  All accommodation and facilities shall be kept in good order, be clean and presentable and shall comply with the latest fire safety codes and other regulations | 25550
110C TOILET AND CANTEEN FACILITIES
|  SANITARY ACCOMMODATION: Provide and maintain in a clean condition sanitary accommodation for the Employer's representatives, either separate or shared with the Contractor's supervisory staff. | 6340
| To Collection | 31890
54 of 64 | A42 CONTRACTOR’S GENERAL COST ITEMS: SERVICES AND FACILITIES
110 SERVICES AND FACILITIES
 Details: Services or facilities required or made/ not made available by the Employer: See section A36.
 Cost significant items: List cost of significant items including but not limited to;
111A POWER
|  Cost significant items: Contractor to indicate build-up of costs with tender. | 2250
120 LIGHTING
 Cost significant items: Contractor to indicate build-up of costs with tender.
130 FUELS
 Cost significant items: Contractor to indicate build-up of costs with tender.
140 WATER
|  Cost significant items: Contractor to indicate build-up of costs with tender. | 1550
150 TELEPHONE AND ADMINISTRATION
|  Cost significant items: Contractor to indicate build-up of costs with tender. | 1750
160 SAFETY, HEALTH AND WELFARE
|  See clause A34/210. | 11750
 Cost significant items: Contractor to indicate build-up of costs with tender.
170 STORAGE OF MATERIALS
|  Cost significant items: Contractor to indicate build-up of costs with tender. | 6750
180 RUBBISH DISPOSAL
|  See clause A34/430. | 4200
 Cost significant items: Contractor to indicate build-up of costs with tender.
190 CLEANING
 See clause A33/710.
 Cost significant items: Contractor to indicate build-up of costs with tender.
| To Collection | 28250
55 of 64 | 200 DRYING OUT
 See clause A34/410.
 Cost significant items: Contractor to indicate build-up of costs with tender.
210 PROTECTION OF WORK IN ALL SECTIONS
|  Cost significant items: Contractor to indicate build-up of costs with tender. | 1500
220 SECURITY
 See clause A34/150.
 Cost significant items: Contractor to indicate build-up of costs with tender.
230 MAINTAIN PUBLIC AND PRIVATE ROADS
 See clause A34/520.
 Cost significant items: Contractor to indicate build-up of costs with tender
240 SMALL PLANT AND TOOLS
|  Cost significant items: Contractor to indicate build-up of costs with tender. | 2100
| To Collection | 3600
56 of 64 | A43 CONTRACTOR’S GENERAL COST ITEMS: MECHANICAL PLANT
110 MECHANICAL PLANT
 Cost significant items: List cost significant items including but limited to;
115A CRANES
 Cost significant items: Contractor to indicate build-up of costs with tender.
120 HOISTS
 Cost significant items: Contractor to indicate build-up of costs with tender.
140 TRANSPORT
 Cost significant items: Contractor to indicate build-up of costs with tender. Note:
| Contractor is to include all parking, congestion and other charges associated with transport. | 15750
200 ADDITIONAL MECHANICAL PLANT
 Cost significant items: Contractor to indicate build-up of costs with tender.
| To Collection | 15750
57 of 64 | A44 CONTRACTOR’S GENERAL COST ITEMS: TEMPORARY WORKS
110 TEMPORARY WORKS
 Details: Temporary works required or made/ not made available by the Employer: See section A36.
 Cost significant items: List cost significant.
115A TEMPORARY ROADS
 Cost significant items: Contractor to indicate build-up of costs with tender.
120 TEMPORARY WALKWAYS
|  Cost significant items: Contractor to indicate build-up of costs with tender. | 4500
130 ACCESS SCAFFOLDING
 Cost significant items: Contractor to indicate build-up of costs with tender.
140 SUPPORT SCAFFOLDING AND PROPPING
 Cost significant items: Contractor to indicate build-up of costs with tender.
150 HOARDINGS, FANS, FENCING, ETC.
 Cost significant items: Contractor to indicate build-up of costs with tender.
160 HARDSTANDING
 Cost significant items: Contractor to indicate build-up of costs with tender.
170 TRAFFIC REGULATIONS
 Cost significant items: Contractor to indicate build-up of costs with tender.
200 ADDITIONAL TEMPORARY WORKS
 Cost significant items: Contractor to indicate build-up of costs with tender.
| To Collection | 4500
58 of 64 | A50 WORK/ PRODUCTS BY/ ON BEHALF OF THE EMPLOYER
120 PRODUCTS PROVIDED BY/ ON BEHALF OF EMPLOYER
 General: Details of such products are given in the work sections, for fixing as part of the contract. Use for no other purpose than the Works.
 Handling: Accept delivery, check against receipts and take into appropriate storage.
 Surplus products: Keep safe and obtain instructions.
| To Collection | 0
59 of 64 | A53 WORK BY STATUTORY AUTHORITIES/ UNDERTAKERS
120 WORK BY LOCAL AUTHORITY - None anticipated.
120 WORK BY STATUTORY UNDERTAKERS - None anticipated.
A54 PROVISIONAL WORK/ ITEMS
110 PROVISIONAL SUM FOR DEFINED WORKS – SMM7 COMPLIANCE IS NOT REQUIRED
|  Allow the provisional sum of £15,000 for removal and reinstatement of additional | 15000
rendering found to be defective after testing.
|  Allow for general attendance to include but not limited to provision of all necessary power, lighting, access, temporary site accommodation, storage and welfare facilitate. | 750
111 PROVISIONAL SUM FOR DEFINED WORKS – SMM7 COMPLIANCE IS NOT REQUIRED
|  Allow the provisional sum of £15,000 for additional concrete repairs found to be | 15000
necessary after testing.
|  Allow for general attendance to include but not limited to provision of all necessary power, lighting, access, temporary site accommodation, storage and welfare facilitate | 750
112 PROVISIONAL SUM FOR DEFINED WORK, SMM7 COMPLIANCE IS NOT REQUIRED
|  Allow the provisional sum of £15,000 for plastering and making good beyond window | 15000
reveals.
| • Allow for general attendance to include but not limited to provision of all necessary power, lighting, access, temporary site accommodation, storage and welfare facilitate. | 750
310 WORK WHERE COMPLIANCE WITH SMM7 IS NOT REQUIRED
 Item: Additional works to above ground drainage installation.
 Description of work: Works that may be required to the above ground drainage installation that can only be ascertained once access is available and testing has commenced, and the installation can be fully inspected.
|  Provisional Sum: £4,000 | 4000
|  Allow for general attendance as above. | 200
311 WORK WHERE COMPLIANCE WITH SMM7 IS NOT REQUIRED
 Item: Fire Testing a door set.
 Description of work: Arrange for fire testing of a sample of the door sets being used at Levita for flat entrance doors and side window by BRE or other appointed fire testing authority.
|  Provisional Sum: £10,000 | 10000
|  Allow for general attendance as above and transport of samples to BRE. | 500
| To Collection | 61950
60 of 64 | 312 SATTELITE DISHES
 Item: Temporary removal of satellite dishes
|  Description of work: Arrange for specialist tracing/identification and removal of satellite dishes and temporary location on scaffolding. On completion reinstate and test, obtain resident sign off. | 3750
 Provisionally; Allow 25 No dishes.
550 PROVISIONAL SUMS NOT SPECIFICALLY FOR WORK – EXTRA COST OF AUTHORISED
OVERTIME
|  Provisional sum: Include: £9,000 | 9000
 Basis for calculating such extra cost: Rates of basic pay, allowances and additional payments, for use with the Working Rule Agreement for the Construction Industry, published by the Construction Industry Joint Council, current when the work is carried out, together with additional payments for continuous extra skill or responsibility or intermittent responsibility, as appropriate.
 Percentage addition: Add to cover the cost of the non-productive element only of overtime, incidental costs, overheads and profit,
|  At time and one half: %. Carry forward to pricing column. | 13500
|  At double time: %. Carry forward to pricing column. | 18000
560 PROVISIONAL SUMS COMPLIANCE WITH SMM7 NOT REQUIRED
 Item: Asbestos removal for ACMs identified during the course of the works.
|  Provisional sum: Include: £10,000 | 10000
| To Collection | 54250
61 of 64 | A55 DAYWORKS
110 LABOUR
|  Provisional sum: Include prime cost of £9,000 labour incurred before the Final | 9000
Completion Date: (Carry forward to collection)
 Percentage adjustment: Add to cover incidental costs, overheads and profit:
| %. Carry forward to collection. | 1350
|  Provisional sum: Include prime cost of £750 labour incurred after the Final Completion Date: | 750
 Percentage adjustment: Add to cover incidental costs, overheads and profit:
| %. Carry forward to collection. | 187.5
120 PRODUCTS
|  Provisional sum: Include prime cost incurred at any time during the Contract £6,750 | 6750
|  Percentage adjustment to cover incidental costs, overheads and profit: %. Carry forward to collection. | 1012.5
130 EQUIPMENT
 Provisional sum: Include prime cost of plant (equipment) incurred before the Final
| Completion Date: £3,000 | 3000 | 3000
|  Percentage adjustment to cover incidental costs, overheads and profit: %. Carry forward to collection. | 750
|  Provisional sum: Include prime cost of plant (equipment) incurred after the Final Completion Date: £3,000 | 3000
|  Percentage adjustment to cover incidental costs, overheads and profit %. Carry forward to collection. | 600
 Plant (equipment) costs: Rates set out in the Schedule of Basic Plant Charges published by the RICS current at the Date of Tender.
| To Collection | 26400
62 of 64 | Levita House, London Borough of Camden
PRELIMINARIES
COLLECTION PAGE
Page 1
Page 2
Page 3
Page 4
Page 5
Page 6
Page 7
Page 8
Page 9
Page 10
Page 11
Page 12
Page 13
Page 14
Page 15
Page 16
Page 17
Page 18
Page 19
Page 20
Page 21
Page 22
Page 23
Page 24
Page 25
Page 26
63 of 64 | Levita House, London Borough of Camden
PRELIMINARIES
Page 28
Page 29
Page 30
Page 31
Page 32
Page 33
Page 34
Page 35
Page 36
Page 37
Page 38
Page 39
Page 40
Page 41
Page 42
Page 43
Page 44
Page 45
Page 46
Page 47
Page 48
Page 49
Page 50
Page 51
| Page 52 | 214900
| Page 53 | 31890
246790
64 of 64 | Levita House, London Borough of Camden
PRELIMINARIES
246790
| Page 54 | 28250
| Page 55 | 3600
| Page 56 | 15750
| Page 57 | 4500
| Page 58 | 0
| Page 59 | 61950
| Page 60 | 54250
| Page 61 | 26400
| Total to main Tender Summary | 441490

## Section 3 Scaffolding
Ref | Item (Works) | Unit/ Qty | Rate | £p
SCAFFOLDING AND ACCESS – PERFORMANCE REQUIREMENTS
S.1 | SPECIFIC APPROACH TO THIS PROJECT
A | The contractor shall design, supply, erect, maintain and dismantle on completion all necessary scaffolding and access towers for the works in accordance with this section of the tender documents. |  |  | 9405
B | The scaffolding must be capable of carrying the loads imposed by hoisting and supporting new and existing materials, notably roofing and windows, labour and other sundry materials necessary for the works. It shall also withstand all wind, snow and any other live and dead loads imposed.
C | The contractor’s engineer’s scaffolding design should establish the dead and live loads for the entire project.
D | The contractor is asked to submit a method statement with his tender as to the anticipated solution to these access and protection problems, so tenders can be evaluated on a like-for-like basis.
E | Whatever methods are chosen they should comply as a minimum with the following clauses in this section.
S.2 | GENERAL
A | The Contractor is to provide all access for the works, to include full scaffolding to each elevation, mobile access platforms, or towers, cradles, or a combination thereof, as he considers appropriate to carry out the specified works including all provisional repairs. The access will also be required for installation works, inspections of the work by the Employer and throughout the progress of the Contract. It will also be required for snagging inspections by the Employer’s professional team and re-inspections thereafter if appropriate.
B | No claims will be entertained for the Contractor’s failure to allow for sufficient access, nor for any scaffold or other access that may need to be re-erected for the purposes of the Employer’s inspections/re-inspections.
C | Provide access in good time to allow the Employer to carry out inspections etc. to enable him to issue final instructions regarding the scope of the works and also time for snagging inspections and re-inspections prior to final strike.
| Scaffolding - Page: 2 |  | To Collection | 9405
Ref | Item (Works) | Unit/ Qty | Rate | £
D | Scaffolding, platforms and/or towers shall be provided in accordance with the following general items. Reference should also be made to, but not limited to the following: TG20:13 Good Practice Guidance for Tube and Fitting Scaffolding
BS 1139-1.2:1990 – Metal Scaffolding. Tubes. Specification for aluminium tube. BS 1139-2.1:1991, EN 74:1998 – Metal Scaffolding. Couplers. Specification for steel couplers, loose spigots and base-plates for use in working scaffolds and falsework made of steel tubes. BS 1139-2.2:1991 – Metal Scaffolding. Couplers. Specification for steel and aluminium couplers, fittings and accessories for use in tubular scaffolding. BS 1139-3:1994 – Metal Scaffolding. Specification for prefabricated mobile access and working towers. BS 1139-4:1982 – Metal Scaffolding. Specification for prefabricated steel splitheads and trestles. BS 2482:1981 – Specification for timber scaffold boards. BS: 6399-2 Wind loading. BS EN 12810-1:2003 – Façade scaffolds made of prefabricated components products specifications. BS EN 12810-2:2003 – Façade scaffolds made of prefabricated components. Particular methods of structural design. BS EN 12811-1:2003 – Temporary works equipment. Scaffolds. Performance requirements and general design. Note – Wind loads in scaffolding design are to be calculated in accordance with Eurocode 1 (BS EN 1991-1- 4) However advisory note to the UK National Annex of Eurocode, the BSI states:
“Calibration of BS EN 1991-1-4 against BS 6399-2 has
shown that there are differences in the values of pressure
coefficients and in some cases the EN values are
significantly different to those currently used in the UK.
National choice is not allowed for the external pressure
coefficients. It is therefore recommended that the external
pressure coefficients in BS 6399-2 continue to be used to
maintain the current levels of safety and economy of
construction.”
So external pressure coefficients are to be calculated using BS 6399, all other aspects of wind load are to be carried out using the Eurocode.
E | NASC In addition to the above Scaffolders should have NASC membership.
| Scaffolding - Page: 3 |  | To Collection | 0
Ref | Item (Works) | Unit/ Qty | Rate | £p
S.3 | PROJECT SPECIFIC REQUIREMENTS
A | The Contractor must obtain approval from the Police Crime Prevention Office for the proposals before a scaffolding license will be issued.
B | The Contractor is to allow for obtaining all scaffold licenses and approvals in connection with the scaffolding and any associated temporary supports for the structure including but not limited to:  London Borough of Camden  Transport for London  Metropolitan Police
C | Outline method statement required with tender. All the terms and conditions of the license must be met, including the payment of the requested deposit, before the structure is erected. Applications should be made to the Highways Licensing Team. An application fee must be submitted with the form to validate the application. Include for parking bay suspension. Take responsibility for any damage to street furniture.
D | The Contractor is to allow for full liaison with the Client and sufficient notice is required prior to the commencement of the works.
E | Full netting will be required to the entire scaffold to protect pedestrians / visitors / staff during the works.
F | Shops/Retail Units and Public House The scaffolding to Chalton Street is to be designed and built to clear span all shop fronts and the public house to maintain full access to the units and pub which will remain in occupation and use throughout the project. The Chalton Street elevation in particular is to include for a continuous fan and protection to retail customers, Youth Centre pupils and staff, retail and Council staff, and public throughout.
G | Temporary Shop fascia Signs The contractor shall allow for sign written fascia signs to all retail units and set on the face of the scaffolding. In addition, each unit is to be provided with a sign written “Open as Usual” notice. On double fronted shops this to be repeated in duplicate.
H | Adjacent Parts of Levita House and New Horizon Youth Centre The scaffolding shall be designed and built to span over the adjacent block to allow access to end elevation chimnies. The scaffolding bearing in gardens of adjoining block should be minimised/avoided if there is a cantilever solution.
| Scaffolding - Page: 4 |  | To Collection | 0
Ref | Item (Works) | Unit/ Qty | Rate | £p
J | Scaffolding lifts and lift heights The contractor should consider carefully the works involved in this project and design scaffold lift heights accordingly to avoid, for example, scaffold lifts interfering with window openings and concrete repairs. Higher lifts are encouraged. Allow third handrail as required. Consider also items that need to be moved around the scaffolding, avoid diagonal bracing across scaffold lifts, design out using locking transoms and other design solutions to keep scaffolding clear for easier access and moving aground large items such as new windows.
S.4 | GENERAL REQUIREMENTS
A | Scaffolding must comply with the following conditions:
B | After the scaffolding has been erected, any diagonal cross- bracing used at ground level must be removed at once to allow unobstructed resident access. A width of at least 1.5 metre and a headroom clearance of at least 2.44 metres are required for pedestrians to pass, unless other arrangements are agreed by the Council.
C | While a scaffold is being erected, signs should be prominently displayed saying 'Scaffold is incomplete'.
D | Scaffolding must be lit from half an hour after sunset to half an hour before sunrise.
E | On the inside of the structure, white bulkhead lights must be set at each end of the structure 2.44 metres high and at 3 metre intervals. Similarly, on the outside of the structure, red bulkhead lights must be set at each end of the structure 2.44 metres high and at 3 metre intervals. |  |  | 1980
F | Where a scaffold is longer than 3 metres, provide 'escape routes' for pedestrians at 3 metre intervals. The Crime Prevention Officer at the local Metropolitan Police Station may request more onerous requirements. You must obtain approval in principle for any such structure before a license is issued.
G | Standards must be either painted white or fitted with red and white plastic sleeving up to a height of at least 2.44 metres.
H | Any couplings below 2.44 metres must be fixed so that any projection, or threaded or clamp fixing, is on the opposite side to residents.
I | Horizontal scaffold poles, such as handrails, must be fitted with plastic end caps or otherwise made safe, as directed by the Council.
J | Scaffolding, scaffold boards, temporary roofs and sheeted scaffolds must be properly secured to resist high winds. Sheeted scaffolds are particularly vulnerable to wind damage from the 'sail effect'.
| Scaffolding - Page: 5 |  | To Collection | 1980
Ref | Item (Works) | Unit/ Qty | Rate | £
K | Scaffolding must not obstruct access by emergency services vehicles and personnel.
L | If there is any risk of falling material injuring passing pedestrians or hitting vehicles, you must erect a protective scaffold fan. For instance, a scaffold fan is needed when operating cradles or carrying out masonry repair work.
M | Fans or screens must be wide enough to provide complete protection to the public, and to prevent material of any kind from falling onto the public highway.
S.5 | SCAFFOLDING - GENERALLY
A | Provide and erect tubular scaffolding to the full height of the building and internally as necessary to provide safe and proper access to all windows and cladded areas, for the purpose of carrying out all work detailed in the Schedule of Works. |  |  | 251394
B | Provide and erect vertical sheeting to all scaffold lifts. Provide secure fencing/hoarding around the base of all scaffolding that might be accessed by those unauthorised to do so. |  |  | 2290
C | Provide and erect all fans and other temporary protection to ensure the complete safety of the public at large during the works. Double boarding and sheeting to be provided to 1m to each side of entrance doors and fire escape routes.
F | Temporary Roof NB A temporary roof will be required to all blocks on this project as the entire roof covering will be removed and re-covered including parapet gutters. Temporary roofs shall be TG 9:12 compliant. See also clause S.1D of this section. Temporary roofs shall have a minimum pitch of 12.5 degrees is required on both apex and single pitch roofs to allow adequate run off. Prior to the fixing of Shrink Wrap to a roof structure the Scaffold Company / Contractor must ensure that side sheeting is complete to all elevations down to eaves level at least. Good quality scaffold boards must be fixed to the roof using clips at no more than 500mm apart, these must run in the sloping direction of the roof. |  |  | 277666
G | Completion Certificate On completion of the shrink wrap installation an inspection must be carried out with a Completion Sheet issued. Under normal circumstances the shrink wrap installation should be guaranteed for a maximum period of 3 months from the completion date subject to the wind not exceeding force 7 during this period.
H | Provide all necessary work staging including boards, toe boards, weld mesh protection etc.
| Scaffolding - Page: 6 |  | To Collection | 531350
Ref | Item (Works) | Unit/ Qty | Rate | £p
I | Paint all poles at ground floor level white. Provide all necessary lighting and security whilst the site is not manned. |  |  | 1193
J | Provide and install, at ground floor level, all necessary protection to existing paved, grassed or planted areas from which scaffolding will be supported. |  |  | 1435
K | Strike scaffolding on completion as directed and clear from site. Scaffolding shall not be dismantled until snagging and de-snagging have been carried out by the Employer’s Agent.
L | Make good all damage to chases, holes, mortices etc., formed to facilitate erection of scaffold to match existing and to the satisfaction of the Employer. Remove all ties on completion (e.g. Hilti ties) and make good.
M | Reinstate all grassed, paved, planted areas affected by the erection of the scaffold to the satisfaction of the Employer and Local Authority upon completion to match existing.
N | The scaffolding shall be erected so as not to obstruct any door or window openings.
O | All necessary protection to the buildings during the erection of the scaffolding shall be provided. Similarly, adequate protection to all members of the public, pedestrians and building operatives shall be provided.
P | The Contractor will be required to submit an Engineer’s Design to the Employer before the commencement of the works, and when the scaffolding etc., has been erected, he shall supply the Employer with a Certificate from a member of the Institute of Structural Engineers indicating that the works are in good condition and comply in all respects with all relevant Codes of Practice. Scaffold registers shall be kept on site and will be inspected at site meetings.
Q | All materials and workmanship are to be in accordance with the latest relevant British Standards and/or Codes of Practice.
R | The scaffolding shall be constructed in accordance with all prevailing Regulations and to the entire satisfaction of the EMPLOYER.
S | Include for the provision, installation, adaptation, maintenance and removal of all necessary electric hoists, ladders, staging, tarpaulins, tools and other plant, mechanical or otherwise which may be considered necessary for the proper execution of the works.
| Scaffolding - Page: 7 |  | To Collection | 2628
Ref | Item (Works) | Unit/ Qty | Rate | £p
T | An electrical platform or other mechanical hoist(s) may be required to lift materials and the Contractor should investigate and make provision for this. Note on this project in particular difficulty of accessing opposite elevations, it is anticipated a number of hoists may be required. |  |  | 87516
U | The Contractor shall allow for a cost for temporary lighting to be provided to the scaffolding by the Contractor particularly to public access and staff building access areas, where directed by the Employer and as necessary, in compliance with all regulations. Test Certificates shall be provided as appropriate. |  |  | 1980
V | Proper access to all external doors and walkway must be afforded to the users of the properties with any vehicular access being maintained at all times.
W | Unauthorised Access: - The Contractor shall take down and safely store at the conclusion of each day’s work all ladders used in conjunction with the work and shall render scaffolding, plant etc., inaccessible to unauthorised persons during non-working hours. Ladders to upper lifts are to be boarded over securely, e.g. with padlocks and chains to prevent unauthorised use.
X | The Contractor must provide fans and/or covered walkways over all paved areas with the vicinity of the scaffold and adjacent to all roads, parking areas, and porches etc. or similar locations which may be used by the workers within the buildings or the public, to include entrances to the building. Note – It is a particular requirement of this project that the bottom lift is double boarded with polythene sheet between to protect all pavements, access ways and rear gardens.
Y | Provide Youngmans or similar bridging as necessary to carry out the scheduled works.
Z | Important Note: The scaffold must be designed and constructed without the use of raking props unless otherwise instructed by the Employer.
| Scaffolding - Page: 8 |  | To Collection | 89496
Ref | Item (Works) | Unit/ Qty | Rate | £
AA | The Contractor is to allow for the erection of a display board on site in a location to be agreed which is to be supplied by the Employer and Consultant. The Contractor is to ensure that the boards are clearly visible at all times and maintained in position for the duration of the Contract Period. At hand-over, the boards are to be returned to the EMPLOYER in a clean and serviceable condition. The Contractor may, at his own discretion, erect a suitable display board to a maximum size of 1000mm x 1000mm. Should the Contractor wish to erect a board larger than this maximum permitted size he must obtain the consent in writing from the EMPLOYER. (Refer also to contract preliminaries). |  |  | 619
S.6 | SCAFFOLD ALARMS
A | The Contractor is to allow for an alarm system. The installing company must be NACOSS Gold approved by theNational Security Inspectorate (NSI) and must have been audited and approved to install to the NCP115 Code of Practice for the Design, Installation & Maintenance of Scaffolding Alarm Systems. ‘Enhanced Silver System Scaffold Alarm’ that must be arranged through an NSI approved security installer; e.g. PANTHERA SECURITY 0845165 1234 or equivalent.
B | The system shall be designed and installed to detect human intrusion via climbing, crawling or walking up or through the invisible pattern. The system shall provide intrusion detection to scaffold ends, small returns, short scaffold runs, ladders to next lift, alcoves, bays and other similar locations within the installed environment.
C | Alarm system must be installed/dismantled as soon as the scaffold lift which it will be fixed to is erected/dismantled. Ensure the lift where the alarm is to be installed/dismantled is fully boarded, hand railed and with no one working overhead so the alarm engineer can work safely.
D | The monitored system must be routed through an ARC for verification using a Unique Reference Number (URN) before being passed to the relevant security service for response. Call out response times are to comply with the Met Police intruder alarm policy, British Standards 4737 and the NSI Standards.
E | The alarm installing company must provide proof of their accreditation which should be submitted with your tender. Upon full completion of the system being installed the installing company must issue an NSI certificate of conformity to site and an electronic copy to the contractor’s head office. |  |  | 4620
| Scaffolding - Page: 9 |  | To Collection | 5239
Ref | Item (Works) | Unit/ Qty | Rate | £
F | The sensor technology used shall be MW (microwave electromagnetic), PIR (passive infrared), or AIR (active infrared) or a combination of any of the aforesaid, to provide the best possible field of detection. AIR sensor and MW/PIR and AIR combination technologies will incorporate the facility to indicate an alarm condition should there be any tampering of sensors, removal of lids or covers, cutting/linking out of cable - day or night, whether the system is set or unset.
G | The sensor technologies used are to be specifically manufactured for external applications and designed, installed and programmed to ignore birds, small animals, pedestrians, roadside traffic, rubbish chutes, scaffold safety netting, any form of movement from within adjacent open or closed windows and extreme weather conditions such as falling snow, heavy rain or fog. The sensor technology includes further design and circuitry safety features for the immunity of white, ultra violet and fluorescent light sources, radio and electrical energy sources such as mains surge and RF interference protection.
H | All alarm cables, junction boxes, alarm detectors and other security devices fitted shall incorporate a 24-hour tamper protection circuit and shall and be installed within the field of detection, where possible, thus providing improved security to such devices and complying to the relevant NSI codes of installation and requirements.
I | The system shall provide the option for remote up/downloading capabilities, designed to conform to the BSIA remote service COP (PSTN telephone line required) provided by the built-in 2400/300 baud CCITT V21 full duplex communications modem. This is to provide instant remote diagnostics, testing, security and operating functions using a secure call back programmed to access the system.
J | The system must provide full English text zone and area descriptions and carry a 500 event log memory on a true LCD display for low light conditions providing the customer and engineer with a full diagnostic display of time, date and event record of the systems functions.
K | The control panel must be designed to accept Point ID wiring as this is the preferred method of wiring when installing a scaffold alarm system. A diagram of the zone layout must be provided to the Alarm Response Company and to the site manager in order to provide the exact sensors location that has been triggered.
| Scaffolding - Page: 10 |  | To Collection | 0
Ref | Item (Works) | Unit/ Qty | Rate | £
L | Power should be provided by means of an internal 240V socket, supplied within 10 meters of the scaffold structure. In the event of mains failure/disconnection, the control unit technology will incorporate a 12V/7A Ni-Cad rechargeable battery back-up system for a minimum of 8 hours. A mains failure signal should then be sent to the Monitoring Company who should then inform the site manager or installing company. |  |  | 293
M | Provide visual warning signs to all elevations, which shall normally be fitted at a height greater than 4m above the pavement level at intervals no greater than 10m apart to all elevations where scaffold is erected, and security signs are required.
N | Allow for 24-hour call out service. In the event of an engineer required to attend site for emergency breakdowns and repairs, response must be within 2 hours from notification.
O | Upon activation of the alarm the monitoring company must contact the Town Hall security desk immediately.
S.7 | TOWERS
A | Where the Contractor opts to use towers for minor low level works only within ground storey or internally, these shall be provided with stabilisers, outriggers, bracing, guardrails, stairways and all other safety components required having regard to the height and width of the tower, and the proposed use. Provide all necessary ties. Towers shall be removed at the end of each working day, shall be headed at all times during use and shall not be left unattended.
S.8 | CRADLES
A | Cradles will not be the preferred option on this project. However, if the contractor proposes to use cradles for specific items of work they should state this with their tender.
B | Where the contractor opts to use cradles, these should be entirely in accordance with BS 2830:1994 specification for suspended access equipment etc. BS 5974:1990 Code of Practice for temporary installed suspended scaffolding and access equipment, BS 6037-1:2003 suspended access equipment and BS EN 1808. Particular attention should be given to safe entry and egress from the cradle, and procedures put in place to ensure no tipping occurs when the suspended access equipment snags on something protruding from the building.
| Scaffolding - Page: 11 |  | To Collection | 293
Ref | Item (Works) | Unit/ Qty | Rate | £
C | Suspended access equipment is only to be operated by trained personnel and installed by a member of the Specialist Access Engineering and Maintenance Association (SAEMA).
S.9 | LIGHTNING PROTECTION AND EARTHING
A | All means of access such as scaffolding, platforms etc., shall be provided with temporary lightning protection as necessary, which shall be tested and certified by an Electrical Engineer at commencement and at monthly or more frequent intervals to ensure compliance with current regulations and recommendations.
B | Earth bond all scaffolding etc., to comply with current IEE Regulations.
C | Generally – important notes Scaffolder to note that design will need to accommodate the fact that the adjacent properties will be in occupation and scaffolding will need to be constructed in residential areas. The proposed works include replacement windows that are very large non-standard sizes that will need to be hoisted up and onto the scaffolding as will all other building materials and components.
| Scaffolding - Page: 12 |  | To Collection | 0
| SCAFFOLDING - COLLECTION PAGE |  |  | £ p
| Scaffolding Page 1 |  |  | N/A
| Scaffolding Page 2 |  |  | 9405
| Scaffolding Page 3 |  |  | 0
| Scaffolding Page 4 |  |  | 0
| Scaffolding Page 5 |  |  | 1980
| Scaffolding Page 6 |  |  | 531350
| Scaffolding Page 7 |  |  | 2628
| Scaffolding Page 8 |  |  | 89496
| Scaffolding Page 9 |  |  | 5239
| Scaffolding Page 10 |  |  | 0
| Scaffolding Page 11 |  |  | 293
| Scaffolding Page 12 |  |  | 0
|  |  | Total to Main Tender Summary | 640391
Scaffolding, temporary roof and all associated costs to be apportioned by block as follows;
136 – 180 Levita House
181 – 203 Levita House
204 – 236 Levita house including low rise 60 and 67 Chalton Street (New Horizon Youth Centre).
Indicate weekly hire cost per block in event of an agreed extension of time;
| 136 – 180 Levita House | 4958 | per/week
| 181 – 203 Levita House | 4967 | per/week
| 204 – 236 Levita House, including low rise 60 and 67 Chalton Street (New Horizon Youth Centre). | 5901 | per/week
Scaffolding - Page: 13

## Section 4 Sch of Works
Ref | Item (Works) | Q | Unit | Rate | £ | p
BLOCK 136 - 180
4.01 | SURVEY C10/ SCHEDULING / EXEMPLARS / TRIALS – ALL SECTIONS OF WORK
Survey for new components
4.01.1 | The Contractor is to carry out a full survey of all the works to all elements of construction as required for the design and installation of the new works. Ensure that each area and building element is treated on a bespoke basis as one size fits all is not acceptable. |  |  |  | 450
Control Samples / Exemplars
4.01.2 | The Contractor is to carry out control samples of various items of works to agree standard with the CA prior to commencing the remainder of the project. These works are set out in the various sections that follow where applicable, e.g. pilot window installation, render etc. Allow for all necessary cost incurred in out of sequence procurement and working in this regard.
All trials to be undertaken at appropriate time ahead of the programme and may be part of the completed works provided standards are achieved.
Allow for all temporary access and protection in connection with the trials/samples.
Hoardings
4.01.3 | The contractor shall erect secure hoardings, Class O rated and dust proof, at the entrance to the designated site area. Maintain and adapt as required for the duration, remove on completion and make good all surfaces. |  |  |  | 8663
4.01.4 | Access is to be maintained at all times to adjoining Somers Town Coffee House public house, shops, and estate external areas. Under no circumstances shall works interrupt the function of any mains supplies without written notification min 21 days in advance and agreement of methodology with the Council. |  |  |  | inc
4.01.5 | Roofing - Carry out a full photographic internal schedule of condition of all internal areas under roofs and parapet gutters recording condition of finishes and decorations and agree with resident. Notify CA of any significant defects before proceeding. Provide full annotated USB copy to the CA for each flat. |  | Item |  | 234
Windows and Doors
4.01.6 | Before removal of any window or door prepare a schedule of condition of each and every window and door opening, recording condition of finishes and decorations and agree with resident. Include for a photograph of every window and door. Notify CA of any significant defects before proceeding. Provide full annotated USB copy to the CA. |  |  |  | 1137
4.02 | C20 Demolitions and Spot Items - Refer to Section 2
Asbestos Survey
4.02.1 | A number of pre refurbishment surveys have been carried out to date and are available with the Pre-Construction Information, Council and CA. Some areas were inaccessible (roof externally, and voids, windows and doors at upper levels not accessible from access balconies) and require scaffolding. On completion and handover of scaffolding engage an accredited asbestos survey company to complete a Pre Refurbishment survey of the external areas not previously accessible and provide a copy of the report to the CA and Employer in PDF format. For your information the company that carried out a number of the existing surveys to date is O C Consulting (UK) Ltd t/a Manestream INSPECTION BODY Tel: 01992 780300 enquiries@manestream.co.uk. |  |  |  | 2532
Asbestos Removal
4.02.2 | Refer to prelims A54 for Provisional Sum.
4.03 | C40 CLEANING MASONRY/CONCRETE
Brickwork Access Balcony Elevations 12, 13, 14, 15, 16 and 16A
4.03.1 | Allow to clean all facing brickwork with DOFF, or equal approved system at all access balcony and ground storey levels, entire elevations and inside face of access balcony/communal walkway parapet walls. |  |  |  | 8877
4.03.2 | Allow pilot sample area of 2m2 each to yellow stock and red brickwork to be trialled and agreed with Council and conservation officer prior to full application described above. | 4 | m² |  | 394
4.03.3 | Remove and refix all signs in conjunction with these works to allow cleaning behind. |  |  |  | inc
4.03.4 | Provide all necessary attendances on specialist cleaner and safe temporary electrical supply system, NB may need 240 Volts. |  |  |  | inc
Ground Storey “Stonework” Courtyard Elevations 12, 13, 14, 15, 16, and Splay elevation (for splay see drawing L(0)002). Garden elevations 17, 18 and 1.
4.03.5 | Allow to steam clean external ground storey stone/exposed aggregate with DOFF, or equal approved system. Area to include courtyard facing ring beams etc. above ground storey access way up to and including first floor access balcony parapet wall. |  |  |  | 3148
4.03.6 | Allow pilot sample area of 2m2 to be trialled and agreed with Council representative and conservation officer prior to full application. See specification item C40:232. | 2 | m² |  | 394
Quarry Tiled floors and Grano Stairs
4.03.7 | Deep clean quarry tiles floors to ground storey access stair lobbies (2No). Deep clean all stair flights and landings. Deep clean lift lobby at each level. |  |  |  | 305
4.04 | C41 REPAIRING/RENOVATING/CONSERVING MASONRY - Refer to Section 2
Ground Storey “Stonework” – Courtyard Elevations 12, 13, 14, 15, 16, and Splay elevation (for splay see drawing L(0)002), and rear garden elevations 1, 17 and 18.
4.04.1 | Allow to take samples of original mortar to stonework/exposed aggregate bed joints in locations agreed with Council representative, min 2 No per elevation. Analyse samples through a competent testing house (e.g. Sandberg) and establish original mix. Provide written report to Council representative. |  | Item |  | 507
4.04.2 | Allow to rake out min depth 19mm and repoint all lose and defective and non-matching joints to stonework in assumed lime mortar, mix to be designed by contractor and agreed with CA subject to test results from item above. Allow Provisional Quantity 20 lin metres. | 20 | m |  | 338
Repointing Brickwork
Rake out to 19mm depth and repoint brickwork in random locations as below, to match original style and colour;
4.04.3 | No 149 - Parapet wall to access balcony, inside face opposite No 149 - 1 sqm. | 1 | m² |  | 62
4.04.4 | No 152/153 - Parapet wall to access balcony, inside face - 2 sqm. | 2 | m² |  | 124
4.04.5 | No 154/155 - Parapet wall to access balcony, inside face - 10 sqm. Leave ready for redecoration of previously painted brickwork. | 10 | m² |  | 619
4.04.6 | Flat 169 - Curved parapet wall to access balcony, inside face - 4 sqm. (NB Crack stitching taken later in F10). | 4 | m² |  | 248
4.04.7 | Flat 170 - curved parapet - rake out and repoint vertical crack, 800mm. | 0.8 | m |  | 17
4.04.8 | 4th Floor level - rake out and repoint top two courses of parapet wall opposite stairs. Flat 175 end. | 6 | m |  | 124
4.04.9 | Flat 175 - curved parapet wall - remove all vegetation. Rake out and repoint wall compete between columns. | 2.6 | m² |  | 161
4.04.10 | Flat 176 - curved parapet wall - remove all vegetation. Rake out and repoint wall compete between columns. | 2.6 | m² |  | 186
4.04.11 | Opposite lift lobby near 177/178 - Projecting triangular brick parapet - remove all moss and other vegetation. Rake out and repoint wall complete. | 1.5 | m² |  | 124
Brick Repairs –
4.04.12 | Survey all existing face brick work after cleaning and report all defects to Council representative. See F10 for repairs later. |  | Item |  | 282
4.05 | C42 REPAIRING/RENOVATING/CONSERVING CONCRETE - Refer to Section 2
Extent of Surfaces to be Repaired and re- coated
4.05.1 | The contractor is to carry out repairs and recoating to all existing external exposed concrete at all levels to all elevations of the block, including but not limited to;
4.05.2 | · Ring beams, communal access balconies soffits and edges, and all other concrete features.
4.05.3 | · Lower ground floor level exposed concrete including soffits to ground storey units.
4.05.4 | · Communal area staircases - 2No.
4.05.5 | · Exposed aggregate face “stonework” to lower stories all elevations.
Survey
4.05.6 | Undertake a detailed survey of all the concrete surfaces as described in C42 and present findings to the Council's representative by way of a written report, photographs, annotated drawings and approximate quantities of repairs required. |  | Item |  | 550
Preparation
4.05.7 | Allow to thoroughly REMOVE ALL existing concrete coatings to;
4.05.8 | • Access balcony ceilings/soffits and downstand beams/edges/soffits. |  | Item
4.05.9 | • Stairs soffits and landing ceilings including lift landings and lobbies. |  | Item
4.05.10 | Check condition of all other coatings and remove locally any lose material to a smooth edge. |  | Item
4.05.11 | Prepare all existing concrete surfaces ready to receive repairs and new coatings, as C42. In the event existing coatings are found to be sound and well adhered, proven by adhesion and pull off tests, existing coatings may remain subject to formal instruction from the Council's representative to this effect. Coating removals to be designed to extract dust and arisings at source, and to include for all temporary protection and sealing of windows, vents, doors and any other apertures that may permit dust penetration into the building. |  | Item
Control Samples/Exemplars
4.05.12 | Carry out samples of the following for Employer approval before proceeding with the main works;
| · General concrete repairs – 10 No | 10 | No |  | 253.88
| · Fairing coat 5 sq.m | 5 | m² |  | 110
| · EXPOSED AGGREGATE wall repairs – 5 No | 5 | No |  | 275
These may be part of the completed works provided they are of acceptable quality.
Concrete Repairs – PROVISIONAL QUANTITIES – TO BE REMEASURED
4.05.13 | Break out defective concrete, prepare and prime steel exposed, make good reinforcement bars and bases of staircase balustrades as described in C42, and carry out concrete repairs as C42 to all concrete surfaces allowing the following provisional quantities;
WALL OR COLUMN FACES
Repair as described in C42: items 105 – 165A
4.05.14 | Depth not exceeding 25mm
A | area not exceeding 0.01m² | 10 | No |  | 55
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 88
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 137.5
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 258.5
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 478.5
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 682
G | area exceeding 1.00m² | 2 | m² |  | 171.6
4.05.14 | Depth exceeding 25mm but not exceeding 50mm
A | area not exceeding 0.01m² | 10 | No |  | 88
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 176
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 264
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 561
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 924
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1210
G | area exceeding 1.00m² | 2 | m² |  | 332.2
4.05.15 | Depth exceeding 50mm but not exceeding 75mm
A | area not exceeding 0.01m² | 10 | No |  | 110
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 313.5
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 528
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 924
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 1518
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1674.2
G | area exceeding 1.00m² | 1 | m² |  | 213.4
SIDES & SOFFITS OF BEAMS & LINTELS
4.05.16 | Depth not exceeding 25mm - Side & soffit
A | area not exceeding 0.01m² | 10 | No |  | 55
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 88
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 137.5
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 258.5
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 478.5
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 682
G | area exceeding 1.00m² | 2 | m² |  | 171.6
4.05.17 | Depth exceeding 25mm but not exceeding 50mm - Side & soffit
A | area not exceeding 0.01m² | 10 | No |  | 88
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 176
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 264
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 561
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 924
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1210
G | area exceeding 1.00m² | 2 | m² |  | 332.2
4.05.18 | Depth exceeding 50mm but not exceeding 75mm - Side & soffit
A | area not exceeding 0.01m² | 10 | No |  | 110
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 313.5
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 528
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 924
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 1518
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1674.2
G | area exceeding 1.00m² | 1 | m² |  | 213.4
SINGLE ARRIS OF WALLS AND COLUMNS
4.05.19 | Depth not exceeding 25mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 79.75
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 143
C | length exceeding 600mm | 2 | m |  | 96.8
4.05.20 | Depth not exceeding 25mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 136.345
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 263.175
C | length exceeding 600mm | 2 | m |  | 164.384
Depth not exceeding 25mm
4.05.21 | Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 263.175
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 410.96
C | length exceeding 600mm | 1 | m |  | 112.519
4.05.22 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 176
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 280.5
C | length exceeding 600mm | 1 | m |  | 79.2
4.05.23 | Depth exceeding 25mm but not exceeding 50mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 317.46
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 515.35
C | length exceeding 600mm | 1 | m |  | 145.728
4.05.24 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 515.35
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 728.64
C | length exceeding 600mm | 1 | m |  | 192.049
4.05.25 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 317.515
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 452.76
C | length exceeding 600mm | 1 | m |  | 147.972
4.05.26 | Depth exceeding 50mm but not exceeding 75mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 452.76
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 739.86
C | length exceeding 600mm | 1 | m |  | 211.134
4.05.27 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 739.86
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1055.12
C | length exceeding 600mm | 1 | m |  | 246.092
SINGLE ARRIS OF BEAMS AND LINTELS
4.05.28 | Depth not exceeding 25mm
Girth 0 -150mm
A | length not exceeding 300mm | 10 | No |  | 187
B | length exceeding 300mm but not exceeding 600mm | 10 | No |  | 330
C | length exceeding 600mm | 1 | m |  | 53.35
4.05.29 | Depth not exceeding 25mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 159.17
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 295.845
C | length exceeding 600mm | 1 | m |  | 94.281
4.05.30 | Depth not exceeding 25mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 295.845
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 471.405
C | length exceeding 600mm | 1 | m |  | 127.446
4.05.31 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 214.5
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 341
C | length exceeding 600mm | 1 | m |  | 94.6
4.05.32 | Depth exceeding 25mm but not exceeding 50mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 372.02
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 602.69
C | length exceeding 600mm | 1 | m |  | 162.415
4.05.33 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 602.69
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 812.075
C | length exceeding 600mm | 1 | m |  | 219.692
4.05.34 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 372.02
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 525.47
C | length exceeding 600mm | 1 | m |  | 169.059
4.05.35 | Depth exceeding 50mm but not exceeding 75mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 525.47
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 845.295
C | length exceeding 600mm | 1 | m |  | 242.385
4.05.36 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 845.295
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1211.925
C | length exceeding 600mm | 1 | m |  | 279.609
TWO ARRIS REPAIR OF BEAMS AND LINTELS
4.05.37 | Depth not exceeding 25mm
Girth 0 -300mm
A | length not exceeding 300mm | 5 | No |  | 131.45
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 195.25
C | length exceeding 600mm | 1 | m |  | 73.073
4.05.38 | Depth not exceeding 25mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 195.25
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 365.365
C | length exceeding 600mm | 1 | m |  | 111.672
4.05.39 | Depth not exceeding 25mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 365.365
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 558.36
C | length exceeding 600mm | 1 | m |  | 150.601
4.05.40 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 - 300mm
A | length not exceeding 300mm | 5 | No |  | 224.675
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 449.35
C | length exceeding 600mm | 1 | m |  | 146.157
4.05.41 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 449.35
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 730.785
C | length exceeding 600mm | 1 | m |  | 197.285
4.05.42 | Depth exceeding 25mm but not exceeding 50mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 730.785
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 986.425
C | length exceeding 600mm | 1 | m |  | 262.713
4.05.43 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 - 300mm
A | length not exceeding 300mm | 5 | No |  | 454.96
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 636.625
C | length exceeding 600mm | 1 | m |  | 198.484
4.05.44 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 636.625
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 992.42
C | length exceeding 600mm | 1 | m |  | 277.574
4.05.45 | Depth exceeding 50mm but not exceeding 75mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 992.42
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1387.87
C | length exceeding 600mm | 1 | m |  | 325.6
CRACK REPAIRS IN SURFACES OF WALLS, COLUMNS, ETC.
Repair cracks C42:items 105 – 165A
4.05.46 | After preparation width not exceeding 5mm, depth not exceeding 10mm
A | crack length 0 to 150mm | 10 | No |  | 44
B | crack length 150mm to 300mm | 20 | No |  | 121
C | crack length 300mm to 450mm | 20 | No |  | 145.2
D | crack length 450mm to 600mm | 10 | No |  | 101.2
E | crack length 600 to 750mm | 10 | No |  | 126.5
F | crack length exceeding 0.75m | 2 | m |  | 33.22
4.05.47 | After preparation width 10mm, depth not exceeding 20mm
A | crack length 0 to 150mm | 10 | No |  | 74.8
B | crack length 150mm to 300mm | 20 | No |  | 202.4
C | crack length 300mm to 450mm | 20 | No |  | 246.4
D | crack length 450mm to 600mm | 10 | No |  | 165
E | crack length 600 to 750mm | 10 | No |  | 198
F | crack length exceeding 0.75m | 2 | m |  | 54.12
4.05.48 | After preparation width 15mm, depth not exceeding 30mm
A | crack length 0 to 150mm | 10 | No |  | 121
B | crack length 150mm to 300mm | 20 | No |  | 330
C | crack length 300mm to 450mm | 20 | No |  | 396
D | crack length 450mm to 600mm | 10 | No |  | 269.5
E | crack length 600 to 750mm | 10 | No |  | 365.2
F | crack length exceeding 0.75m | 2 | m |  | 94.6
Large Repairs - Balcony Beams – Straight Sections, render finish
4.05.49 | Cut away concrete to expose balcony edge steel beam as indicated on sketch drawing 5675-A(2)002. Install suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 20 No beams approx. 3.1m clear span between columns/walls | 20 | No |  | 27962
4.05.50 | Cut away concrete to expose balcony edge steel beam as indicated on sketch drawing 5675-A(2)002. Install suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 2 No beams approx. 4.1 m clear span between columns/walls. Elevation 16. | 2 | No |  | 3698.2
Large Repairs – Balcony Beams - Straight section, exposed aggregate finish.
4.05.51 | Carry out works as above item but to ground storey balcony beam with exposed aggregate finish.
| Allow Provisionally – 3 No beams n/e 3.1 metres long. | 3 | No |  | 5061.177
Large Repairs - Balcony Beams – Curved Sections to communal access balconies, render finish.
4.05.52 | Cut away concrete to expose balcony edge beam (assumed steel angle). Provide suitable reinforcement armature and fix to existing steels and concrete as described for above items. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 4 No radius beams @ approx. 3.2 linear metres each. | 4 | No |  | 6965.904
4.04.53 | Curved beam as above item, public house end, 4.2 linear metres. | 1 | No |  | 2285.69
Large Repairs - Stairwell lintels – Straight Sections, render finish
4.05.54 | Cut away concrete to expose assumed steel beam as indicated on sketch drawing 5675-A(2)002. Provide suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 2 No lintels approx. 650mm clear span between columns/walls | 2 | No |  | 707.476
4.05.55 | Cut away concrete to expose assumed steel beam as indicated on sketch drawing 5675-A(2)002. Provide suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 7 No beams approx. 1.7 m clear span between columns/walls | 7 | No |  | 6476.085
4.05.56 | Cut away concrete to expose assumed steel beam as indicated on sketch drawing 5675-A (2)002. Design suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 4 No beams approx. 2.13 m clear span between columns/walls. Elevation 16, e.g. flats 174/173. | 4 | No |  | 4636.676
Miscellaneous Large Repairs - Requiring Further Investigation
4.05.57 | Third Floor Ceiling/Soffit near Refuse Chute/Flats 166 & 167 - Cut out crack to soffit to expose structure.
4.05.58 | Allow Provisional Sum of £250 for repair to structural soffit prior to application of fairing coat taken later. |  | Prov Sum |  | 250
4.05.59 | Third Floor Ceiling/Soffit near Flat 170 - Cut out crack to soffit to expose structure.
4.05.60 | Allow Provisional Sum of £250 for repair to structural soffit prior to application of fairing coat taken later. |  | Prov Sum |  | 250
4.05.61 | Third Floor Ceiling/Soffit near Flat 175 - Cut out crack to soffit to expose structure.
4.05.62 | Allow Provisional Sum of £500 for repair to structural soffit prior to application of fairing coat taken later. |  | Prov Sum |  | 500
LEVELLING MORTAR/FAIRING COAT
4.05.63 | Supply and apply a single component polymer modified cementitious fairing coat/overall levelling coat to ALL concrete surfaces, repaired and sound, on completion of repairs as C42:166A prior to application of anti-carbonation coatings. Include;
| - Communal access balcony beams and lintels, soffits and edges – do not extend over any movement joints |  | Item |  | 1775.4
| - Communal access balcony soffits/ceilings. |  | Item |  | 4438.5
| - Stairs and landings soffits. |  | Item |  | 3329.04
COATINGS
4.05.64 | Prepare, prime and apply anti-carbonation decorative coatings to all concrete surfaces as C42, repaired and existing, comprising silane-siloxane primer and acrylic co-polymer pigmented top coat as C42:167A onwards. Colours to be confirmed with Employer. |  | Item |  | 5728.8
| NB Stairs and communal balcony soffits to be Class O standard. |  | Item |  | Noted
EXPOSED AGGREGATE REPAIRS - GROUND STOREY
WALL OR COLUMN FACES
4.05.65 | Repair as described in C42:105 – 165A
Depth not exceeding 25mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 16.06
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 27.5
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 33.462
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 68.464
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 107.03
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 135.3
G | area exceeding 1.00m² | 1 | m² |  | 86.9
4.05.66 | Depth exceeding 25mm but not exceeding 50mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 18.59
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 43.12
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 66
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 94.6
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 139.48
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 174.9
G | area exceeding 1.00m² | 1 | m² |  | 109.78
4.05.67 | Depth exceeding 50mm but not exceeding 75mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 33.88
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 48.84
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 77.88
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 114.4
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 169.62
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 215.6
G | area exceeding 1.00m² | 1 | m² |  | 133.1
SIDES & SOFFITS OF EXPOSED AGGREGATE FINISH BEAMS & LINTELS
4.05.68 | Depth not exceeding 25mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 16.06
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 27.5
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 33.462
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 68.464
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 107.03
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 135.3
G | area exceeding 1.00m² | 1 | m² |  | 86.9
4.05.69 | Depth exceeding 25mm but not exceeding 50mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 18.59
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 43.12
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 66
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 94.6
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 139.48
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 174.9
G | area exceeding 1.00m² | 1 | m² |  | 109.78
4.05.70 | Depth exceeding 50mm but not exceeding 75mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 33.88
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 48.84
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 77.88
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 114.4
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 169.62
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 215.6
G | area exceeding 1.00m² | 1 | m² |  | 133.1
STAIR REPAIRS
Repair as described in C42:105 – 165A, but with granolithic finish to match existing
Right Hand Stairs (Viewed from Courtyard)
4.05.71 | Half landing level 3 and 4 - top tread riser - repair full width, approx. 1060mx 100mm. Typical example below. Reform nosing. | 1 | No |  | 103.554
4.05.72 | Level 3 down to half landing from level 2 - Top riser full width as above. | 1 | No |  | 103.554
4.05.73 | Level 2 - last riser on half landing up to level 3 - full width repair as above. | 1 | No |  | 103.554
4.05.74 | Half Landing level 1 to level 2 - full width riser repair as above items. | 1 | No |  | 103.554
4.05.75 | Level 1 - riser on half landing up to level 2 - full width repair as above. | 1 | No |  | 103.554
4.05.76 | Level 1 - tread corner repairs approx. 100, x 120 x 100mm, typical photo below. Reform nosing. | 1 | No |  | 103.554
4.05.77 | Level 1 - Top riser on flight down to ground floor - full width repair as described previously. | 1 | No |  | 103.554
4.05.78 | Level 1 - Repair tread approx. 250 x 100 x 100mm including nosing. | 1 | No |  | 103.554
4.05.79 | Level 1 Half Landing - Corner repair as described above. | 1 | No |  | 103.554
4.05.80 | Ground floor flight - full width repair as described at half landing. | 1 | No |  | 103.554
4.05.81 | Ground floor flight up from half landing - 3 No corner repairs as described. | 3 | No |  | 310.662
Left Hand Stairs (Viewed from courtyard)
4.05.82 | Ground Floor - bottom nosing - repair approx. 300 x 150 x 100mm as described. | 1 | No |  | 103.554
4.05.83 | Ground Floor - second riser - repair 100 x 150 x 100mm approx. | 1 | No |  | 103.554
4.05.84 | Ground floor flight adjacent to electrical riser - repair continuous stepped crack to string. | 3.1 | m |  | 321.0174
4.05.85 | Ground floor flight - tread repair (previous failed) approx. 300 x 100 x 75mm. | 1 | No |  | 103.554
4.05.86 | Half Landing - full width riser repair as previously described. | 1 | No |  | 103.554
4.05.87 | Half Landing flight to first floor - Tread and riser repair, approx. 250 x 150 x 100mm. | 1 | No |  | 103.554
4.05.88 | Fourth tread - repair 280 x 70 x 70 mm. | 1 | No |  | 103.554
4.05.89 | First floor - full width riser repair as described before. | 1 | No |  | 103.554
4.05.90 | First floor - Tread repair 150 x 190 x 150 approx. | 1 | No |  | 103.554
4.05.91 | First Floor - 3 No tread repairs , approx. 140 x 130 x 150mm | 3 | No |  | 310.662
4.05.92 | Half Landing flight to second floor - 3 corner repairs as described above. | 3 | No |  | 310.662
4.05.93 | Top riser - second floor - full width riser repair as described. | 1 | No |  | 103.554
4.05.94 | First Floor - soffit repair to stair flight, approx. 1 m long, assume depth n/e 50mm. | 1 | m |  | 103.554
4.05.95 | Second floor up - Full width repair as described | 1 | No |  | 103.554
4.05.96 | Second Floor Up - Repair to first tread, approx. 140 x 1430 x 150mm. | 1 | No |  | 103.554
4.05.97 | Half Landing Up - 2no Tread repairs as above item. | 2 | No |  | 207.108
4.05.98 | Half Landing Up - Top riser (i.e. level 3) full width repair as described. | 1 | No |  | 103.554
4.05.99 | Third Floor Level - Cut out poor quality repair to top tread approx. 400mm long x 35mm wide and reform in grano to match adjacent original surfaces. | 1 | No |  | 103.554
4.05.100 | Third floor level - repair as above 500mm long diagonal crack at access balcony level at bottom of flight to 4th floor level. | 1 | No |  | 103.554
4.05.101 | Level 3 Up - Full width riser repair to half landing as described but extends into soffit of the landing continuing to the flight up to fourth floor level. | 1 | No |  | 103.554
4.05.102 | Half Landing up to level 4 - Top tread repair adjacent to half landing, approx. 200 long x 60 x 100mm deep. | 1 | No |  | 103.554
Left Entrance Stair Externally
4.05.103 | Cut out defective bottom riser and nosing and repair as described, approx. 1.5 metres long. | 1 | No |  | 103.554
4.06 | F10 AND F30/F31 BRICK WALLING AND COPINGS - Refer to Section 2 Specification
Brick Repairs following Render Removal – Walls and Chimnies
4.06.1 | On completion of render removal (taken later in M20) survey all walls and chimnies and provide a quantified report and marked up drawing to the Employer for instructions on repairs and renewals required. |  |  |  | 282
4.06.2 | Allow for brickwork patch repair, stitching, replacement and repointing to damaged masonry following removal of render.
| Allow Provisionally 20 sq. metres in small patches n/e 0.5 sq.m. | 20 | m² |  | 4739
Main Roof Parapet Copings
4.06.3 | Remove existing coping stones to entire length of all parapet walls, to entire main roof as indicated on roof plan and clear away from site. |  |  |  | inc
4.06.4 | Supply and install new once weathered top, twice throated coping stones, with suitable expansion joints and neatly pointed and jointed in position. Note coping projections are to suit the new thicker parapet wall design, ply cladding and weatherproofing to achieve clear projection and clear drip throatings on both faces. Refer to drawing No 5675-A(2)001. |  |  |  | 14081
4.06.5 | Provide sample of the above copings for approval prior to ordering all. | 1 | No |  | inc
4.06.6 | Expansion joints in copings - to be provided within 1.5 metres of all internal and external corners and generally at not exceeding 12 metres. Joints min 12mm wide, primed and sealed with silicone sealant on polyethylene backing rods. |  |  |  | 345
Miscellaneous Brickwork alterations and spot items
4.06.7 | Flat 169 - Cut out diagonal crack to brick parapet near flat 169 and stitch in second hand bricks to match existing. Repoint on completion. Allow 1 linear metre. | 1 | m |  | 339
4.06.8 | Provisional Quantity - Allow to cut out and stitch in replacement yellow stock bricks to access balcony elevation or parapet, to match existing, fully bedded and pointed in mortar to match original. Allow 30 No individual bricks provisional quantity. | 30 | No |  | 339
4.06.9 | Flat 171 - Cut out and make good redundant service pipe core holes in brickwork, stitch in in second hand stock bricks to match existing. Allow 2 No n/e 150mm diameter holes. | 2 | No |  | 91
4.06.10 | 4th Floor 175 end - Cut out and repair stepped crack in brickwork from window facing roof, n/e 0.5 lm | 0.5 | m |  | 98
4.07 | H65 SINGLE LAP ROOF TILING - Refer to Section 2 Specification
Strip Existing roofs 136 - 180 Levita House
Elevations - 1, part 6, part 12, 13, 14, 15, 16, 17 and 18
4.07.1 | Carefully strip up entire tiled roof covering including flashings and accessories. Clear away all redundant tiling complete, along with all battens, accessories and any underlay. |  |  |  | 101294.601
4.07.2 | Allow review of existing "eaves"/parapet detail, ridge and hip details and suitability for new tiling before proceeding. |  |  |  | inc
Additional first fix carpentry - PROVISIONAL
4.07.3 | Tilting fillet - Remove rotten tilting fillet, supply and install new to match existing, assume 125mm wide x 25mm thick. Allow provisional quantity 128 linear metres. | 128 | m |  | 1264
4.07.4 | Close Boarding - Remove & renew rotten & damaged roof close boarding (100mm) in various locations - total 200 linear metres, Provisional Quantity | 200 | m |  | 2151
4.07.5 | Ridges and Hips - build up ridge board or hip rafter height, allow 50 x 125mm tanalised timber fixed to existing, Provisional quantity 90 linear metres. | 90 | m |  | 1310
Tiling
4.07.8 | Upon completion of insulation works (taken elsewhere) retile the slopes using vapour permeable breathable sarking underlay laid horizontally over boarding as H65. Re-tile using new 38 x 12mm counter battens and 50 x 25mm tile battens and with, ensuring underside of tiles are ventilated as per manufacturer’s written recommendations. |  |  |  | inc
| Tiles to be Sandtoft BRIDGEWATER fixed entirely in accordance with manufacturer’s written recommendations and H65. |  |  |  | inc
Colour - SOMERSET
Detailing
4.07.8 | Ridge, hips, verges to Sandtoft/Wienerberger specification – Note allow for new matching half round mechanically fixed ridges and hips. Complete the design of and supply and fit all flashings and other weathering details. All flashings and weatherings to be in lead as Specification section H71 to meet listed building requirements to minimum Code and details as Lead Sheet Association. |  |  |  | inc
To include but not limited to;
· abutments;
· flashings;
· Valleys;
· secret gutters to dormers and gables;
· Chimney aprons, side flashings and back gutters;
· Dormer flat roof abutments
· pipe, fan and flue penetrations;
· Verges;
· Junctions and saddles;
and all other details as required to complete the installation.
Velux Roof Windows
4.07.9 | Existing Velux type roof windows (approx. 600 x 1200mm) to be retained. Carefully remove flashing kits and clear away. Supply and fix replacement Velux EDZ/EDW flashing kits entirely in accordance with manufacturer's written recommendations. | 7 | No |  | inc
Soil Vent Pipes
4.07.10 | Support all soil vent pipes and other pipe penetrations, removing and refixing as necessary. Provide Code 4 lead slates and weatherings, dressed under tiling on upper side min 100mm and dressed over and to tiles mon 150mm apron, and 150mm each side of pipe/penetration. |  |  |  | inc
Fan Terminals
4.07.11 | Replace all extract fan terminals currently discharging through the roof with new colour matched to tiles, to achieve minimum free air flow as existing. |  |  |  | 612
Fire Breaks
4.07.12 | Supply and install fire breaks over all party walls and communal areas. Fill the space over the wall with layers of mineral fibre quilt so that when the underlay and battens are laid it is lightly compressed. Tuck the edges of quilt between edges of wall and adjoining rafters. Lay 300 mm wide pads of mineral fibre quilt thick enough to seal all gaps and cut to fit snugly between the tile battens. At boxed eaves, completely seal all air paths with compressed mineral fibre quilt to completely fill void on line of party walls. |  |  |  | 912
Roof Insulation - Sloping ceilings/flats with dormers
4.07.13 | Refer to drawing 5675 – A(2)003 and 005. Carefully remove section of sarking boarding without disturbing internal finishes. Supply and install insulation system between rafters, in each rafter void, to "lap" parapet gutter insulation as detail drawings. Insulation to be as specified in Section 2 - P10 and as indicated on drawings. |  |  |  | 14024
4.07.14 | Reinstate sarking boarding with existing and make up quantity with matching new as required, to be screw fixed, not nailed, twice on each rafter |  |  |  | 8048
Remove existing insulation - sloping areas PROVISIONAL
4.07.15 | Allow Provisionally to remove assumed existing inadequate mineral wool and chicken wire insulation and clear from site. |  | Prov Item |  | 1992
Roof Insulation - Horizontal areas
4.07.16 | Allow Provisionally to remove assumed existing inadequate mineral wool and chicken wire insulation and clear from site. |  | Prov Item |  | 1587
4.07.17 | Supply and lay two layers 150mm mineral wool insulation as specification P10, 150mm laid between ceiling joist, 150mm laid over first layer at 90 degrees. Ensuring “eaves” ventilation to sloping parts is maintained. Sarking board removal taken with sloping insulation item |  |  |  | 9743
4.07.18 | Roof Access Hatches - Allow provisionally to carefully cut out ceiling, trim joists and install proprietary loft access hatch, fully insulated and draft proofed, U Value 0.35, 30 mins fire resistance, Class O spared of flame Push-Up Loft Access Door Matt White 630 x 630mm approx. Make good ceiling and adjacent decorations disturbed, assuming two coats white emulsion to entire room or landing affected. | 8 | No |  | 1216
4.08 | H71 LEAD SHEET COVERINGS/FLASHINGS - Refer to Section 2 Specification
Dormers
4.08.1 | Carefully remove and cart away for recycling all dormer window cladding and roof coverings. |  |  |  | 912
Dormer Cheeks - insulation
4.08.2 | Carefully remove timber boarding to cheeks and supply and install insulation system between studs to be non combustible mineral wool and vapour permeable breather membrane on outer side. Leave 25mm air gap with insect screen, and reinstate new 12mm WBP ply boarding ready for cladding, making up quantity as necessary. Provide full details of selected materials for comment prior to proceeding. Refer to drawings 5675 – A (2) 003 and 004. 25 No dormers this block. | 26 | No |  | 43575
Dormer Roofs - insulation
4.08.3 | Supply and install insulation system to all dormer roofs carefully removing and replacing timber decking as required, assumed 100mm rigid mineral wool vapour permeable system. Provide 50mm ventilation gap as detailed and 18mm WBP ply deck to falls and cross falls. Provide full details for comment prior to proceeding. Leave ready for cladding. Refer to drawings 5675 – A (2) 003 and 004. | 26 | No |  | inc
Dormer Cladding and Roofing
4.08.4 | Supply and install Code 5 lead cladding and roofing to dormers ensuring all lead work to Lead Sheet Association recommendations, thickness Codes etc. Form all detailing, drips rolls, splash laps, clips, and joints similar to existing (note Listed Building) taking care to ensure falls are correct. Dormer roofs to fall to each side and not discharge over the windows to avoid dripping on widow cills. Include insect mesh as detailed. Form min 150mm effective vertical height sloping upstand and fillet to underside of tiled roof abutments at top of dormer including welted edge. See drawing No 5675-A(2)004. | 26 | No |  | inc
4.08.5 | Supply and fit new s.w. PAR fascias to dormers and leave ready for decorations. Ensure all surfaces including back of fascia primed and undercoated before installation. Assume 25mm x 150mm. | 26 | No |  | inc
Pilot Cladding and Roofing.
4.08.6 | Construct 1 pilot dormer for comment prior to proceeding with all others. Allow out of sequence working to achieve this. | 1 | No |  | 1743
Louvre dormers – 1No.
4.08.7 | Carefully strip, re-roof and re-clad in Code 5 lead 1No lead louvred dormer structure located over main entrance , top level, all as items above. Refer also to photo below and roof plan L (0)011 for location. | 1 | No |  | 844
4.08.8 | Elevation 14 Main Entrance Projecting Canopy Structure - Clean off all surfaces. Supply and fit geotextile underlay and Code 5 lead sheet covering to Lead Sheet Association recommendations, and welted drip to edge, and complete with 150mm min upstand, Cover flashing, and welted drip to edge. Photo below. Approx. 3.75lm. | 1 | Item |  | 317
4.09 | J21 COMMUNAL ACCESS BALCONIES - ASPHALT REPAIRS
Carry out asphalt repairs to communal access balconies using hot poultice method as J21 as follows;
4.09.1 | Parapet wall near flat 148 - cut out and renew approx. 5 linear metres asphalt fillet/upstand including internal and external angles. | 5 | m |  | 140.63
4.09.2 | Gas Pipe - Flat 149 - cut out and renew n/e o.5 sqm damaged asphalt around gas riser pipe. | 0.5 | m² |  | 32.07
4.09.3 | Inside face Parapet wall flat 148 - Cut out and replace fillet/upstand full length of this section, approx. 5 linear metres. | 5 | m |  | 140.63
4.09.4 | Flat 150 - Cut out crack full width of access balcony and replace in two coat work, to include old gas pipe sleeve adjacent. Allow 1 sqm. | 1 | m² |  | 73.13
4.09.5 | Lift lobby Area first floor - take up asphalt complete and relay to correct falls, reforming drainage channel and dressing into outlet. Reform fillet/upstand to parapet. Allow approx. 5 sq.m | 5 | m² |  | 478.13
4.09.6 | Parapet - 152 - 153 - Cut out and reform fillet/upstand. Allow 15 linear metres. | 15 | m |  | 379.69
4.09.7 | Flat 157 - Cut out asphalt and reform to correct falls to gully, redressing into gully. Allow 2 sqm. | 2 | m |  | 191.25
4.09.8 | Flat 157 and 158 - Cut out and repairs cracks in asphalt near column and also near refuse chute. Allow 1 linear metre total. | 1 | m |  | 36
4.09.9 | Flat 159 - cut out and renew n/e o.5 sqm damaged asphalt around gas riser pipe. | 0.5 | m² |  | 32.07
4.09.10 | Flat 160 - take up asphalt complete and relay to correct falls, reforming drainage channel and dressing into outlet. Reform fillet/upstand to parapet. Allow approx. 5 sq.m | 4 | m |  | 382.5
4.09.11 | Flat 162 - 163 Parapet Wall - Cut out and reform fillet/upstand. Allow 15 linear metres. | 15 | m |  | 379.69
4.09.12 | Flat 164 -165 - take up asphalt complete and relay to correct falls, reforming drainage channel and dressing into outlet. Reform fillet/upstand to parapet. Allow approx. 5 sq.m |  |  |  | 478.13
4.09.13 | Flats 166, 167 and 168 - Cut out and reform access balcony fillet/upstand. Allow 15 linear metres. | 15 | m |  | 379.69
4.09.14 | 4th Floor Access balcony - cut out and replace asphalt upstand to main wall, allow 5 linear metres. | 5 | m |  | 140.63
4.09.15 | Flat 177 - Cut out and repair minor splits to asphalt, allow 0.25 sqm | 0.25 | m² |  | 19.69
4.1 | J31 PARAPET GUTTER AND ASSOCIATED FLAT ROOFS - LIQUID APPLIED WATERPROOFING - Refer Section 2 Specification
Introduction
4.10.1 | The refurbishment of the internal parapet gutters is to be carried out in conjunction with the replacement of the main pitched tiled roofs. Works will need to be designed and programmed to ensure that the installation works co-ordinate satisfactorily and any finished areas of gutters are protected from other trades.
NB in addition to the gutters the wider gutter extensions/roofs areas are to be treated similarly , on this block (3 No locations elevations 13, 14 and 15 (over each stair and main entrance) and 6 No bay roofs to elevations 16 and 17. See roof plan.
4.10.2 | The gutter lining system shall not be a hot works solution, no hot works are permitted at roof level. Please refer to drawing 5675 – A (2) 001 for existing detail. For the contractor's information Block 1-21 incorporated the use of Moy Materials Ltd ENKOPUR system, Tel 07917 896307 or 012435 707449.
4.10.3 | Cores - In conjunction with the selected Liquid system supplier who will be guaranteeing the installation take cores samples through parapet gutter and roofs over sufficient areas to establish the existing roof/covering build up. |  | Item |  | 330
4.10.4 | Adhesion tests - carry out adhesion test of waterproofing to parapet gutters base and sides, and allow to cure for 1 week before proceeding. |  | Item |  | inc
Waterproofing and Insulation
4.10.5 | Supply and install complete cold poured polyester resin fleece reinforced waterproofing and thermal insulation lining system to the parapet gutters. Ensure insulation proposals link with pitched roof insulation. Selected solution is to be provided and installed to achieve a minimum 15 year BBA certified single point guarantee for labour, materials and workmanship and as such will need to be a proprietary system installed by a system approved specialist. |  |  |  | 43893.208
4.10.6 | Preparation - Power wash all surfaces. Remove existing localised repairs. Remove all moss, dirt and debris. Inspect and repair the existing surface. Blisters in the asphalt should be carefully warmed, pierced and smoothed down to a level surface to receive the overlay system.
4.10.7 | Copings – see F10/31, and schedule of works section 4.06. |  |  |  | inc
4.10.8 | Parapet Walls - Make good any localised damage to existing parapet walls, as required, and board out the internal face of parapet with 12mm plywood (mechanically fixed), to allow the new waterproofing to be dressed up and over. Refer to drawing detail 5675-A(2)005 for change in wall thickness on inside face of parapet. |  |  |  | 14692
4.10.9 | Cut new chases in rendered abutments at increased height (staircase walls and chimney stacks), to receive new lead flashing (upstand 150mm min). |  |  |  | inc
4.10.10 | Supply and fit a lay-board to allow dressing of the new waterproofing below the pitched tiled roof as drawing No 5675-A(2)005. |  |  |  | inc
4.10.11 | Coordinate gutter lining with replacement lead cladding to dormers. Remove lead flashings and lead cheeks from dormer windows to allow access for waterproofing. Surfaces to receive waterproofing must be clean, smooth and dry. |  |  |  | inc
Priming
4.10.12 | Supply and apply suitable substrate Primer to existing asphalt. Carry out adhesion test and record results. Allow to dry. |  |  |  | 8744
Vapour Control Layer
4.10.13 | Supply and install suitable vapour control layer under insulation, self-adhesive. |  |  |  | inc
Insulation
4.10.14 | Supply and lay suitable insulation e.g. 140mm rigid Insulation (bonded in suitable Insulation Bonding Adhesive). U Value 0.18W/m²K (compliant with Building Regulations Part L 2010) as indicated on the drawing 5675-A(2)005. |  |  |  | inc
Insulation Priming and Preparation
4.10.15 | Prime upper face of insulation with Bonding Agent and allow to dry. Apply preparation Layer self-adhesive. |  |  |  | inc
Waterproofing - gutters, roofs and details
4.10.16 | Supply and lay cold pour resin waterproofing including primer to detailing, finish colour Dark Grey, all to coverage rates specified by manufacturer to achieve guarantee. Ensure bridging tape used at junction of dissimilar materials. Use MC Primer at all metal outlets, lead chute and pipes. Ensure all upstands are min 150mm. |  |  |  | inc
Cover Flashings - chimnies 1, 2, 5 and 11 and walls (excluding parapets as these are coated full height and under copings)
4.10.17 | Except where waterproofing is dressed over parapet under coping and up adjacent roof slopes all abutments to be provided with Code 4 lead cover flashings as recommended by the Lead Sheet Association. |  |  |  | inc
Rainwater Outlets
4.10.18 | Locate and renew all rainwater outlets. Form sumps to all outlets and leave clear and free flowing on completion. |  |  |  | 2419
Cables
4.10.19 | Throughout the works carefully support all data and communications cabling, noting there are large bundles of cables running along the parapet and copings, as well as some in the parapet gutter itself. All lose cables in parapet gutter to be re-supported on suitable galvanised tray support on re-fixed copings to Employers approval. |  |  |  | inc
Railings
4.10.20 | Carefully unbolt, label, set aside and ultimately refix railings fixed to parapet walls and copings, all elevations. |  |  |  | inc
4.11 | J31 FLAT ROOFS – NON RESIDENTIAL
Flat Roofs
4.11.1 | Flat roofs are provided to this block the ground storey bin store near flat 138 (elevation 12) and near rear of pub, (elevation 16). Refer to roof plan L (0)011. All are to be overlaid. |  |  |  | inc
Waterproofing
4.11.2 | Supply and install complete waterproofing system to the flat roofs. No insulation required. Design solution is to be provided and installed to achieve a minimum 15 year guarantee for labour, materials and workmanship and as such will need to be a proprietary system installed by an approved specialist. |  |  |  | inc
Preparation
4.11.3 | Remove existing localised repairs. Remove all moss, dirt and debris. Inspect and repair the existing surface. Blisters in the asphalt should be carefully warmed, pierced and smoothed down to a level surface to receive the overlay system. |  |  |  | inc
4.11.4 | Security Spikes – Carefully remove existing security spikes to both roofs, sequentially number and set aside for re-use. Refix on completion. |  |  |  | 237
Waterproofing
4.11.5 | Supply and lay cold pour resin waterproofing including primer to detailing, finish colour Dark Grey, all to coverage rates specified by manufacturer to achieve guarantee. Ensure bridging tape used at junction of dissimilar materials. Use MC Primer at all metal outlets, lead chute and pipes. Ensure all upstands are min 150mm. |  |  |  | inc
Cover Flashings
4.11.6 | All abutments to be provided with non lead flashings. Cut new chases in rendered abutments at increased height (staircase walls), to receive new Ubiflex B3 or equivalent Lead Alternative Grey 3.5mm thick flashing (upstand 150mm min). Lead alternative. Seal with suitable Gap Seal and Fixing wedges. |  |  |  | 246
Perimeter Trims and detailing
4.11.7 | Supply and install all necessary GRP trims and other detailing to roof edges, forming upstands, water checks and kerbs as required. |  |  |  | inc
Rainwater Outlets
4.11.8 | Locate, design and renew all rainwater outlets, design and form sumps to all outlets and leave clear and free flowing on completion. |  |  |  | inc
4.12 | L10 WINDOWS
New Windows
Design and Listed Building Consent
4.12.1 | Complete the detailed design of the new replacement windows and provide drawings as specification item L10:210A.
4.12.2 | Considerable effort has gone into achieving a design acceptable for listed building consent, window details and frame dimensions shall not be varied against the approved drawings. An approved sample sash window Type K and a tilt window Type J have been fitted in flat 182 which can be inspected externally. The type K window is to be the minimum standard acceptable on this project for a sash window but will need to be replaced to allow for installation of external architrave and head flashing details. The type J tilt/hopper window needs to be replaced, it is broadly acceptable but improved detailing is shown on the tender drawings.
Supply and Installation
4.12.3 | NB it is a specific requirement of the Employer that the window manufacturer shall supply and fit the windows, not just supply for installation by others.
Pilot Flat
4.12.4 | Windows - Allow to complete the removal and replacement of windows in 1No. Flat including all window types in full, including all making good, prior to progressing the fabrication and installation of further windows, all to the satisfaction of the Employer. Allow out of sequence working ahead of main programme. |  |  |  | 1250
Surveys
4.12.5 | Every window shall be surveyed and manufactured to suit the specific opening. The contractor should allow to remove and dispose of the external architraves fitted to vertically sliding sash windows to enable the actual structural opening size to be established. Allow for any temporary seals to windows once architraves are removed. Similarly turn back lead head flashings as required to allow accurate survey. |  |  |  | inc
Remove Existing Windows – all flats
4.12.6 | Carefully remove existing timber windows, fanlight and side lights and ensure units are only removed if they are to be replaced the same working day. See clause 4.12.12 below which will be strictly enforced. |  |  |  | 13028
4.12.7 | Notes from pilot window installation;
- Vertically sliding sash windows are not original, they are fixed with lugs/straps back into the plaster reveals.
- The new sash window frames are deeper than existing, the contractor must allow to carefully cut away internal plaster to allow the windows to be set into the reveals to achieve an external reveal suitable for sealant.
- Tilt windows do appear to be original and are built in, bedded on mortar with frame ties. The mortar bedding will need removing from brickwork, the ties need cutting.
4.12.8 | Remove windows as below: (Approx. Quantities - contractor to verify and confirm with tender. All windows to be replaced and to the entire block unless indicated otherwise on drawings).
| Bring forward total cost of windows to this block from window schedule here. |  |  |  | 384765.623
Generally
4.12.9 | Allow for ensuring all timber framing materials and glass is recycled once removed from site. Allow for removal of any debris from existing units and thoroughly clean the working area.
4.12.10 | Allow for all reveal surfaces of the openings to be cleaned to remove all existing frame sealant, mastic, bedding mortar etc. ready for the installation of the new units.
4.12.11 | Security fittings - many windows have security bars and fittings attached on a "DIY" basis. Allow to remove and discard but option to return fittings to residents.
4.12.12 | Under no circumstances shall a window be removed unless the replacement window is ready, checked and suitable for installation, with sufficient time that day to complete the installation. Appointments with residents should not be made until the replacement window or door is manufactured and quality checked in the factory, delivered to site and re-checked, ensuring it is clearly labelled for the given flat and all components are available and undamaged. Allow for all necessary on site storage.
Replacement Windows – all flats
4.12.13 | Complete the design, manufacture, supply and installation of engineered timber windows systems together with glazing as required in Section L10 of Section 2 – Materials and Workmanship and as detailed on drawings to meet Secured by Design PAS 24 standards. Windows to comprises high performance double glazed;
· Vertical sliding sash with semi concealed balances, NO tilt facility, and
· Casements, outward opening,
· Inward opening hopper/tilt inwards windows (Accepted not Secured by Design)
· Fixed lights
and combinations thereof as indicated on the approved listed building consent and planning drawings.
4.12.14 | Contractor to allow for and design all associated ironmongery and necessary fixings to create a fully operational, safe and user friendly window system. Refer to L10 specification.
4.12.15 | Tilt/hopper and casement window frames on access balconies are to be positioned level with the existing external window line wherever possible. Sliding sash windows to be set back into the reveals as described earlier. Ensure all frames are plumb, and level and without bow. Window positioning in the reveals is key to the listed Building Consents as well as retention of sight lines and glazing bar profiles.
4.12.16 | Provide fully detailed drawings and ironmongery specifications period to manufacture for comment by Employer.
4.12.17 | Windows to include trickle vents. External vent canopies are not permitted by the listed building consent, all vents to be concealed externally. Design to minimum Exposure Category B and Window Energy Rating A/whole window U value n/e 0.6, Secured by Design (except tilt windows where Employer accepts not achievable).
1. Air permeability 600 PA
2. Water tightness 300 PA
3. Wind resistance 2000 PA
Sealants
4.12.18 | Prime and Seal all external joints between framing and structure with low modulus neutral cure silicone sealant to BS5889 (1989). Sealant backing to be provided and detailed in drawings. |  |  |  | 9720
Making Good
4.12.19 | The contractor shall be responsible for and allow for all making good work to window openings, both internally and externally, including external rough cast render margin around all sash windows, masonry, plaster, all cills, reveals, jambs, heads, tiling, decorations etc. cladding and decorative finishes to reveals.
| Note - External reveals to sliding sash windows in rendered elevations to include making good perimeter with roughcast render finish to M20 specification to allow for setting windows back into the reveals. Tilt windows to be made good with mortar collar joint externally, raked out to min depth 15mm before pointing. Collar joint works to be by experienced bricklayers. |  |  |  | 51891
Internal trims to be min 30 x 10mm painted timber (PVC not permitted).
4.12.20 | No additional allowance will be made for costs associated with making good unless identified as pre-existing damage in the schedule of condition (item 4.0 J earlier) and prior instructions obtained from the CA.
Electrical and Other Services
4.12.21 | Allow for unclipping all existing telephone cables, aerial cables and the like from existing windows frames, and re-clip to surround in a suitable location using new cable clips of appropriate size and colour. Any cables passing through a frame/structure joint shall be routed through a plastic sleeve, the inner end of which is to be higher than the outer to prevent water penetration along or through the sleeve. |  |  |  | 7341
4.12.22 | Disconnect and reconnect to appliances as required and leave in full working order on completion to resident's satisfaction. |  |  |  | inc
Curtain Tracks, Net Curtain Hooks and Furnishings
4.12.23 | Remove and re-fit existing curtain tracks and other soft furnishings as applicable. Curtain rods to be plugged and screw fixed with new hooks to window reveal soffit, not frame head where it would obstruct trickle vents and ironmongery. Inform Employer of any tracks and soft furnishings not suitable for re-instatement. |  |  |  | inc
Completion
4.12.24 | Upon completion of and on the same day of the installation of each replacement window/door, all glazing, window frames, handles and all other surfaces are to be cleaned with a mild detergent. All components are to be checked for security of fixings, adequacy of clearances, adjustment of hinges, locks etc. as may be necessary to leave the window/door units in good working order.
4.12.25 | On completion of window installation on the same day the contractor shall:
- Snag his own work and make good.
- Remove all debris, dirt etc.
- Clean the window inside and out.
- Demonstrate the operation of the window to the resident and ensure the resident confirms that they understand the methods of window operation, notably any ironmongery operation, cleaning facilities, restrictors and locks.
- Obtain a signed sheet from the resident confirming:
1. They are satisfied with installation.
2. Making good is complete.
3. Cleaning completion.
4. Understand how the windows work.
Should the contractor fail to complete this process access to other flats to start new installations will be denied until the process is complete and under such circumstances no delays or associated costs will be entertained by the Employer in this regard.
4.12.26 | External Architraves Allow to supply and fit ex 20 thick x 30mm wide 19 x 75mm moulded external architraves to all sash windows all elevations. See detail drawing. Fully decorated with microporous paint system to match windows. |  |  |  | inc
4.12.27 | Head Flashings - To all vertically sliding sash windows and casement windows located on elevations (excluding access balconies, supply and fit new 0.7mm welted zinc head drip flashings as detail. |  |  |  | inc
FENSA
4.12.28 | For window and door replacement works provide a FENSA certificate for every flat, with a copy for the Employer. |  |  |  | inc
4.13 | L20 DOORS
Doors – Flat Entrance and other Secondary residential doors to flats
Design
4.13.1 | Complete design new doors and provide drawings in accordance with L20.
4.13.2 | Allow to design, supply and install new complete pre-fabricated engineered timber door set systems complete with side and fan lights, Secured By Design and with glazing bars to suit Listed Building Consent. See L20:410A.
4.13.3 | NB it is a specific requirement of the Employer that the door manufacturer shall also supply and fit the doors/windows, not just supply for installation by others.
4.13.4 | Note doors to comply strictly with Listed Building consent. All doors to be fire rated, see scope of works below.
4.13.5 | Sample Flat Considerable effort has gone into achieving a design acceptable for listed building consent, door details and frame dimensions shall not be varied against the approved drawings. A sample door and side light have been fitted in flat 182 which can be inspected externally. This sample is not fully compliant and will need to be replaced in line with the tender drawings, but broadly demonstrates the style required noting incorrect details such as glazing bars, trickle vent etc are not acceptable.
Pilot Flat
4.13.6 | Entrance Door - Allow to complete the removal and replacement of 1No. Flat entrance door, including all making good, prior to progressing the fabrication and installation of further doors to the satisfaction of the Employer. Allow out of sequence working ahead of main programme. |  |  |  | 1866.8
Note the doors and adjacent windows are to be from one manufacturer/supplier/installer, to achieve the required certification. Bespoke solutions of windows and door systems being joined together will not be accepted unless PAS 24 certified as a complete unit.
Flat entrance Doors - 136 - 180
4.13.7 | Type I door and OPENABLE side window units 139, 140, 141, 142, 143, 144, 150, 151, 152, 153, 159, 160, 161, 162, 163, 169, 170, 171, 172, 175, 176, 177, 178, 179 and 180 | 25 | No |  | 59170
| Type R - door no window 136, 146, 149, 155, 156, 165, 166, and 174 | 8 | No |  | 14871.4
Fire Rated Flat Entrance doors and side windows
4.13.8 | Note - Doors and borrowed/side lights creating balcony 'dead-ends' in terms of means of escape in case of fire to be FD30 and all glazing to be non-wired with 30 min fire integrity, FIXED SHUT. Applies to;
| Type I - Flats 137, 145? 147?, 154, 157, 164, 168 and 173. | 7 | No |  | 16569
| Type R fire rated, no window - 138, 148?, 158, and 167 | 5 | No |  | 9183
Making Good
4.13.9 | The contractor shall be responsible for and allow for all making good work to door openings, both internally and externally, including masonry, plaster, all cills, reveals, jambs, heads, tiling, decorations etc. cladding and decorative finishes to reveals. Perimeter of doors and side window to be made good with mortar collar joint as described for tilt/hopper windows on access balconies. |  |  |  | inc
No additional allowance will be made for costs associated with making good unless identified as pre-existing damage in the schedule of condition and prior instructions obtained from the Employer.
Sealants
4.13.10 | Prime and Seal all external joints between framing and structure with low modulus neutral cure silicone sealant to BS5889 (1989). Sealant backing to be provided and detailed in drawings. |  |  |  | inc
Completion
4.13.11 | Upon completion of and on the same day of the installation of each replacement door, carry out all checks as item 4.12.24/25 for windows. |  |  |  | inc
Electrical, Access Control and Other Services
4.13.12 | Disconnect and refix access control cables and system as required. Allow for unclipping all existing telephone cables, aerial cables and the like from existing door frames, and re-clip to surround in a suitable location using new cable clips of appropriate size and colour. Any cables passing through a frame/structure joint shall be routed through a plastic sleeve, the inner end of which is to be higher than the outer to prevent water penetration along or through the sleeve. |  |  |  | inc
| Disconnect and reconnect to appliances as required and leave in full working order on completion to resident's satisfaction. |  |  |  | inc
Main Communal Entrance Doors
4.13.13 | Prior to commencement validate operation of access control system and report any defects. | 3 | No |  | inc
Overhaul Communal Doors – Elevations 13, 14 and 15
4.13.14 | Thoroughly overhaul 3 No. existing communal doors/gates; ease and adjust, lubricate all ironmongery, adjust and test self-closers to leave in sound working order. | 3 | No |  | 259
Store Doors, lift lobby cupboard doors, and Meter Cupboard Doors
4.13.15 | Thoroughly overhaul existing doors; ease and adjust, lubricate all ironmongery, adjust and leave in sound working order ready for decorations taken elsewhere. Allow 7 No Provisional Quantity. | 7 | No |  | 394
Lift Lobby Doors
4.13.16 | Survey all lift lobby doors at commencement to validate repairs required. | 8 | No |  | inc
4.13.17 | Thoroughly overhaul existing doors; ease and adjust, lubricate all ironmongery, adjust and leave in sound working order ready for decorations taken elsewhere. | 8 | No |  | 450
4.13.18 | Take off and discard door to lift lobby adjacent to flat 177 . Supply and fit replacement hardwood door with top and bottom glazing to match existing, GWPP, with pair and half fire rated butts, delayed action hydraulic overhead closer, push plate and pull handle, kick plates both sides. Leave ready for decorations taken later. | 1 | No |  | 372
Resident Security Gates/Doors
4.13.19 | Allow Provisionally to take off and return to occupant security door or gate fitted over flat entrance door. Make good all surfaces disturbed | 2 | No Prov Item |  | 180
FENSA
4.13.20 | Provide FENSA certificate for each door and window unit installed as described in windows section previously. |  |  |  | Noted
4.14 | BOILER FLUES AND GAS FIRES
4.14.1 | The contractor should note some flats have boiler flues that penetrate windows/doors. Allow to, as necessary, design, disconnect, adapt, provide bespoke door/window panel, and re-use boiler flues where they penetrate door or window openings. |  |  |  | 616
4.14.2 | Provide Gas Safe engineer's certificate for any work to boilers and provide a new CP12 landlord's certificate for the affected flats. |  |  |  | Noted
4.14.3 | Where boiler flues pose a risk to the contractors workforce, e.g. concrete and render repairs allow for close resident liaison to turn off boilers on a daily basis and restart on completion of works in the vicinity. |  |  |  | inc
Fireplaces and Flues
4.14.4 | Prior to commencement of any works to chimnies, (e.g. render renewal, brick repairs and the like) fully survey all flats internally and establish any open fireplaces, vents and gas appliances. All open fire places and vents to be fully sealed during the works. All gas appliances to be temporarily disconnected and reinstated on completion of chimney works and flue checks. Provisional sum taken later for gas appliances, all other works to be priced here. |  |  |  | inc
4.14.5 | Allow the provisional sum of £4,000 for works to gas fires as may be required over and above item 4.14.1 - 4 above. |  | Prov Sum |  | 4000
4.14.6 | Air Vents in Brickwork
| Carefully cut hole in external brick wall assuming 330mm thick and install 215 x 215mm Terra cotta square hole clay air brick BS 493: 1995 externally with insect mesh (gas compliant) , and white plastic louvre internally. Make good all surfaces disturbed. Allow Provisional Quantity. | 4 | No Prov Item |  | 528
4.15 | M20 - RENDERED/ROUGHCAST COATINGS - Refer to Section 2 Specification
Survey and test existing – All Elevations 1, 2, 17, 18, 12, 13, 14, 15 and 16, and part 6 applicable to 136 - 180 (Chalton Street end)
4.15.1 | See earlier item regarding gas fires. Allow for hammer testing of entire existing external render to all existing rendered surfaces including walls, chimneys and gables. Provide a detailed report and marked up drawings showing all defective and sound areas for agreement on extent of works to go forward. |  | Item |  | 237
Samples and Control Sample Area
4.15.2 | A - Mix samples. In agreement with Employer take a minimum of 10 No samples of original render (not modern patch repairs) from various levels and elevations. Clearly label and identify and submit to a specialist competent testing house to provide a detailed analytical report on the original design mix and constituents. Agree with Employer and conservation officer appropriate mix for repairs and renewals. | 10 | No |  | 788
| B - Control Sample Trial Area - re render to full specification min 2 sq. m in agreed location and fully paint as M60. Allow to dry for agreement before proceeding with remainder of works. | 2 | m² |  | 122
Chimnies - Nos 1, 2, 3, 4, 5, 6, 7, 8, 9, 10 and 11, (refer to roof plan for locations) various heights
4.15.3 | Allow to remove all render complete to all 11 chimnies to this block and prepare brickwork for re-rendering, including dubbing out and pointing up lose and defective brickwork. See also item 4.14 earlier in this section. |  |  |  | 9013
4.15.4 | Re render chimnies in roughcast style to match original design mix (established from items above) and texture and leave ready for painting. Include stop and drip beads to all flashings and weatherings. |  |  |  | inc
| NB new render to be applied to a consistent standard, spraying of top coat recommended. See example on block 1-21 courtyard elevation and chimnies. |  |  |  | Noted
Notes;
| Excludes side of chimney No 8 on elevations 1 and 3 to adjacent block 112-135 subject to inspection. |  |  |  | Noted
Flaunchings – 11 chimnies
4.15.5 | Remove and re-flaunch all flue terminals and pots in sand: cement mortar finished to a neat weathered profile. |  |  |  | 1463
Elevations
4.15.6 | Carefully hack off render as schedule below. Prepare surfaces and re-render in roughcast pattern to an agreed mix, assume 1:1:6. Note - rendering to be carried out by experienced and competent conservation/restoration specialists to meet requirements of Listed building consent and as M20. Form rebates/reveals/returns to all window and door openings to match original design intent. Note spraying recommendation as for chimnies and previous example in courtyard (north) elevation of block 1 - 21 Levita.
4.15.7 | Subject to testing in items above allow for provisional areas and/or quantities as follows and with reference to the drawings;
| 1. Elevation 12 - complete excluding access balcony column features. |  |  |  | 4557
| 2. Elevation 13 – complete excluding access balcony column features. |  |  |  | 9113
| 3. Elevation 14 – complete excluding access balcony column features. |  |  |  | 2228
| 4. Elevation 15 - complete excluding access balcony column features. |  |  |  | 9113
| 5. Elevation 16 - complete - balcony column features are not to be removed. |  |  |  | 13214
| 6. Elevation 6 - ….sqm. NB The decorative parapet features and balcony recess features are not to be removed. |  |  |  | 4388
| 7. Elevation 17 - ….sqm. NB The decorative parapet features are not to be removed. |  |  |  | 8100
| 8. Elevation 18 - ….sqm. NB The decorative parapet features are not to be removed. |  |  |  | 4725
| 9. Elevation 1 - ….sqm. NB The decorative parapet features are not to be removed. |  |  |  | 8100
| 10. Decorative features parapet level - Extra over above item for reforming decorative features to parapet level, allow 40 linear metres of parapet. Provisional Quantity | 40 | m |  | 3375
| 11. Extra over above item reform curved feature to access elevation balcony columns. Allow 10 No Provisional quantity. | 10 | Prov Quant |  | 844
4.16 | M60 - PAINTING/CLEAR FINISHING
Redecorations
4.16.1 | Note - Shop fronts and ground storey of retail units, and Somerstown Coffee House public House elevations are excluded from the works.
4.16.2 | Prepare and decorate all previously or usually decorated surfaces and elements. Thoroughly prepare and redecorate all previously or usually so treated surfaces including, but not limited to; |  |  |  | 43467.6
Joinery M60:130
4.16.3 | · Communal area store doors and frames, lift lobby unglazed doors, plant rooms and intakes, roof access hatches, etc. not stained or otherwise treated. NB all painted inside and out. |  | Item |  | inc
4.16.4 | · Lift lobby glazed doors and frames with panel over, two per level first floor upwards, both sides. | 8 | No |  | inc
4.16.5 | . Lift lobby windows, both sides. Include to replace all missing and defective putties approx. size 2030 x 1850mm. | 4 | No |  | inc
4.16.6 | · Any other previously or usually so treated joinery. |  | Item |  | inc
4.16.7 | · Dormer window fascia details. | 25 | No |  | inc
Joinery M60:171A - Stained
4.16.8 | · Hardwood handrails to entrance steps. |  | Item |  | inc
4.16.9 | · Sub frames to narrow slot style windows at entrances, 135 x 1090mm GWPP glazed. | 4 | No |  | inc
Metalwork M60:130
4.16.10 | · Communal access balcony railings, mesh and perforated panels, security gates and screens (including previously powder coated), and all other usually so treated features, fixtures and fittings. NB Allow for additional preparation to severely corroded areas, to be needle gunned, grit blasted or otherwise treated to remove heavy corrosion. Apply suitable metal fillers to all pitted areas. Advise Employer of any steel found to be unsound. |  | Item |  | inc
4.16.11 | · Communal access balcony conduit and trunking capping, overflows etc. NB allow for suitable primer to galvanised surfaces and note extensive existing flaking paintwork. |  | Item |  | inc
4.16.12 | · Communal stairs balustrades and handrails internally, and externally to entrances. |  | Item |  | inc
4.16.13 | · Doors to former bin chutes/lift motor room, inside and out and electrical risers (ground storey). |  | Item |  | inc
4.16.14 | · SVPs, wastes, RWPs and hoppers all levels, access balcony gully gratings. |  | Item |  | inc
4.16.15 | · Refuse hoppers (sealed shut), all levels. |  | Item |  | inc
4.16.16 | · Gas distribution pipes. On completion supply and fit 50mm wide pipe marking and identification tapes, manufactured to BS1710 and BS4800, at 10m centres and within 300mm of any penetrations through walls, floors and ceilings, or change of direction. |  | Item |  | inc
4.16.17 | · Dry riser doors and frames, including de-rusting. |  | Item |  | inc
4.16.18 | · Dry riser pipes where exposed. |  | Item |  | inc
4.16.19 | · Steel handrail to top of parapet gutter parapet walls. |  | Item |  | inc
Rendering and painted brickwork - M60:170 MAXIMUM EXPOSURE SMOOOTH MASONRY PAINT
4.16.20 | · All render to all elevations including chimnies and all columns. |  | Item |  | inc
4.16.21 | · All existing painted brickwork to inside face of parapet walls and access balcony walls only where painted at present. Note any brickwork unpainted is to remain unpainted, protect throughout the works. |  | Item |  | inc
4.16.22 | · Courtyard dwarf walls, walls to entrance steps, ramps etc. Allow to remove all vegetation growth in advance of preparation and decoration. |  | Item |  | inc
4.16.23 | · Copings to all access balcony parapet walls and to main roof parapet gutters. Allow to remove all vegetation growth in advance of preparation and decoration. |  | Item |  | inc
4.16.24 | Note - Masonry paint colours will be predominantly Classic Cream with white features to be picked out, e.g. access balcony copings and columns, to be confirmed by CA on site. Allow for masking and cutting in. |  |  |  | inc
Communal stair walls and stair soffits, communal access balconies - Specification M60:170A
4.16.25 | Textured soffits to stairs and communal walkways - carefully remove all existing textured coatings back to sound substrate and make good ready for new coatings. |  | Item |  | inc
4.16.26 | To all walls carefully remove localised areas of failed coatings back to sound render and brick substrate. Jet wash all surfaces ready for new coatings. |  | Item |  | inc
4.16.27 | Prepare for, supply and apply a water based class 0 coating system eggshell finish, including compatibility tested for adhesion and paint film thickness build up. Ceilings and Soffits as M60:170A Eggshell Finish, walls as M60:170A Antigraffiti system. Note remove all existing flaking and defective coatings and thoroughly prepare walls and soffits, test dry film thickness of remaining surfaces. Allow to decorate only one stair at a time, and top floor main stair flights to be left in use at end of each work period to maintain access for residents. |  | Item |  | inc
4.16.28 | To include painted door reveals to lift lobby doors. |  | Item |  | inc
4.16.29 | To include all services riser casings on stairs on completion of repairs and fire stopping taken elsewhere. |  | Item |  | inc
4.17 | R 11 ABOVE GROUND DRAINAGE
Test and Report
4.17.1 | Upon completion of scaffolding test and report on condition of entire surface water drainage system including gutters, hoppers and RWP and SVP downpipes. Agree with Employer extent of repairs and renewals. |  |  |  | 273
Rainwater pipes – general overhaul
4.17.2 | Thoroughly overhaul rainwater downpipes, refixing clips, remaking joints as required to leave in sound watertight condition ready for decorations. |  |  |  | 507
Repairs and Renewals
Allow to remove and replace the following provisional quantities of surface water drainage;
1. Gutters
4.17.3 | Item not used.
2. Downpipes SVP/RWP
4.17.4 | Cast Iron, 110mm nominal diameter SVP/RWP to match existing – 50 Linear metres. Provisional Quantity | 50 | m |  | 3094
3. Downpipes RWP
Item not used.
Hoppers - Elevations 1, 2, 17 and 18.
4.17.5 | Carefully dismantle existing hoppers, these are ornate and need to be retained. Engage specialist to shot blast without damaging the base design. Completely refurbish, repairing all holes and corrosion, prepare and decorate and refix, connecting to new or existing downpipes. Provide temporary plastic hoppers whilst permanent are being repaired. | 6 | No |  | 1013
Flat 176 (Vicinity)
4.17.6 | Carefully dismantle Timesaver type rainwater outlet and pipe to soffit from parapet gutter above. Renew complete to match existing and connect to downpipe. | 1 | Item |  | 1024
4.18 | MISCELLANEOUS REPAIRS
Reglazing
4.18.1 | Hack out and Reglaze Crittall window to main entrance, approx. 100mm x 1050mm and leave ready for decorations. | 1 | No |  | 45
Pidgeon deterrent spikes
4.18.2 | Supply and fit Pidgeon deterrent spikes to canopy projection noted in item 4.08.8. To be Stainless Steel Bird Spikes are made from 304 grade stainless steel wires protruding from a super tough Durolon UV stabilised polycarbonate base. Provide a 25-Year "No Rust" Warranty. |  | Item |  | 282
Entrance Handrails
4.18.3 | Left Entrance - Remove and replace hardwood handrail to match existing and leave ready for decorations. |  | Item |  | 197
4.18.4 | Main Entrance - Replace hardwood handrail, scrolls to match original and leave ready for decorations. | 2 | No |  | 422
4.18.5 | Right Entrance - Replace length of hardwood handrail complete near flat 144 and leave ready for decorations. |  | Item |  | 225
4.19 | P12 FIRE STOPPING
Both Stairwells
4.19.1 | Carefully dismantle ply pipe/cable service risers on every stair and set aside for reuse. Sizes vary 440 x 200 ground storey pair 350 x 170 x 2550 high pair 275 x 230 x 2550 high pair 350 x 170 x 3950 high top level pair | 8 | No |  | 7184
4.19.2 | Engage third party accredited passive fire protection specialists for all services. To be members of the BRE/LPCB passive fire protection installer Scheme LPS 1531. |  |  |  | inc
4.19.3 | Seal around all pipes, cables and other services where they penetrate stair landing slabs and soffits with proprietary rapid setting, Gypsum based mortar material, zero shrinkage, 1 hours minimum fire resistance to EN1366-3 up to EI120, including BS476 Pt 20 and BS6399-1 Loading for Buildings “Code of Practice for dead and applied loads”. Include for temporary formwork, ensure removed on completion. All fire stopping to be photographed and certified on completion and full records provided with As Built information. | 8 | No |  | inc
4.19.4 | Reinstate all ply casings removed with new brass cups and screws, leave ready for decorations. | 8 | No |  | inc
4.2 | U90 MECHANICAL VENTILATION
Survey
4.20.1 | The contractor shall survey every flat and identify existing extractor fan types and locations and test and report on same prior to window manufacture for the flat concerned. Agree with CA locations for replacement fans. |  |  |  | 155
4.20.2 | Survey leaseholders and identify if they wish to take up option of fan installation/replacement and report to Employer. Note Tenants will have fans installed under this contract if none provided already in satisfactory condition. |  |  |  | 155
Allow Provisional Quantities to design and install fans as above and following items;
4.20.3 | Kitchen Fans – 20 No | 20 | No |  | 2582
4.20.4 | Bathroom Fans – 20 No | 20 | No |  | 2365
4.20.5 | Separate WC – 5 No | 5 | No |  | 592
Design and Install Fans
4.20.6 | To kitchens, bathrooms and WCs to all flats, survey, design, provide and fix the following, allowing for triple pole isolators to each unit. Allow for all wiring necessary. |  |  |  | 824
| Kitchens - Though wall humidity controlled extract with a minimum intermittent extract rate of 60 l/s. |  |  |  | inc
| Bathrooms - Through wall ducts humidity controlled fans with a minimum intermittent extract rate of 15 l/s. |  |  |  | inc
| Separate WCs - Through wall ducts humidity controlled fans with a minimum intermittent extract rate of 6 l/s. |  |  |  | inc
4.20.7 | Allow for through wall ducting for fans to internal courtyard elevations. Fans not to be window mounted. Include proposals within design submission. |  |  |  | 5412
4.20.8 | Provide NICEIC test certificate on completion for each flat. |  |  |  | 405
Window Fans
4.20.9 | Indicate alternative all in cost per fan for installation through windows, including purpose made sealed unit. Do not carry cost to pricing column for this item. £……………. saving/addition (delete as appropriate).
4.21 | V90 - COMMUNAL ACCESS BALCONY AND STAIRCASE LIGHTING ENHANCEMENT
4.21.1 | Complete design, supply and installation of communal and emergency lighting and controls as set out in Section 2 V90 and Fitzgerald or equivalent Scope of Work document appended thereto and Relux light calculations/simulations. Fitzgerald contact James Baldwin 07815 851996. Ref 46577. All conduit to be galvanised steel reusing existing where possible, adapting to suit. |  |  |  | 37337
4.22 | BUILDER'S WORK IN CONNECTION WITH SERVICES
Generally
4.22.1 | The contractor shall include for all builders work including, but not limited to:
4.22.2 | Cutting holes and chases for Mechanical and Electrical services and making good ready for decorations. Including but not limited to electrical supply rerouting, communal area lighting, public health engineering/rainwater goods, mechanical fan and ductwork installations, etc. |  |  |  | inc
4.22.3 | Fire stopping where all services penetrate walls, ceilings and any other compartment fire stop around with suitable intumescent boarding, mortar, sealant etc. as appropriate to the service and structure being penetrated. |  |  |  | inc
| See also as specification items P12. |  |  |  | Noted
Elevations 12, 13, 14, 15 and 16 - Cables
4.22.4 | Tidy up and refix all cables loosely fixed to the elevation. Remove any redundant cables and make good. |  |  |  | 488
4.23 | PROVISIONAL SUMS
Provisional Sums
4.23.1 | Refer to preliminaries A54 for provisional sums, to be expended in part or whole only as directed by Employer. Ensure all carried forward to tender total. |  |  |  | Noted

## Section 4 Collection
Section 4 | £
Page 1
Page 2
Page 3
Page 4
Page 5
Page 6
Page 7
Page 8
Page 9
Page 10
Page 11
Page 12
Page 13
Page 14
Page 15
Page 16
Page 17
Page 18
Page 19
Page 20
Page 21
Page 22
Page 23
Page 24
Page 25
Page 26
Page 27
Page 28
Page 29
Page 30
Page 31
Page 32
Page 33
Page 34
Page 35
Page 36
Page 37
Page 38
Page 39
Page 40
Page 41
Page 42
Page 43
Page 44
Page 45
Page 46
Page 47
Total to main Summary | 1218121.0644
Total 35

## Section 5 Sch of Works
Ref | Item (Works) | Q | Unit | Rate | £ | p
BLOCK 181 - 203
5.01 | SURVEY C10/ SCHEDULING / EXEMPLARS / TRIALS – ALL SECTIONS OF WORK
Survey for new components
5.01.1 | The Contractor is to carry out a full survey of all the works to all elements of construction as required for the design and installation of the new works. Ensure that each area and building element is treated on a bespoke basis as one size fits all is not acceptable. |  |  |  | 338
Control Samples / Exemplars
5.01.2 | The Contractor is to carry out control samples of various items of works to agree standard with the CA prior to commencing the remainder of the project. These works are set out in the various sections that follow where applicable, e.g. pilot window installation, render etc. Allow for all necessary cost incurred in out of sequence procurement and working in this regard.
All trials to be undertaken at appropriate time ahead of the programme and may be part of the completed works provided standards are achieved.
Allow for all temporary access and protection in connection with the trials/samples.
Hoardings
5.01.3 | The contractor shall erect secure hoardings, Class O rated and dust proof, at the entrance to the designated site area. Maintain and adapt as required for the duration, remove on completion and make good all surfaces. |  |  |  | 1080
5.01.4 | Access is to be maintained at all times to adjoining estate external areas. Under no circumstances shall works interrupt the function of any mains supplies without written notification min 21 days in advance and agreement of methodology with the Council.
5.01.5 | Roofing - Carry out a full photographic internal schedule of condition of all internal areas under roofs and parapet gutters recording condition of finishes and decorations and agree with resident. Notify CA of any significant defects before proceeding. Provide full annotated USB copy to the CA for each flat. |  | Item |  | 234
Windows and Doors
5.01.6 | Before removal of any window or door prepare a schedule of condition of each and every window and door opening, recording condition of finishes and decorations and agree with resident. Include for a photograph of every window and door. Notify CA of any significant defects before proceeding. Provide full annotated USB copy to the CA. |  |  |  | 1137
5.02 | C20 Demolitions and Spot Items - Refer to Section 2
Asbestos Survey
5.02.1 | A number of pre refurbishment surveys have been carried out to date and are available with the Pre-Construction Information, Council and CA. Some areas were inaccessible (roof externally, and voids, windows and doors at upper levels not accessible from access balconies) and require scaffolding. On completion and handover of scaffolding engage an accredited asbestos survey company to complete a Pre Refurbishment survey of the external areas not previously accessible and provide a copy of the report to the CA and Employer in PDF format. For your information the company that carried out a number of the existing surveys to date is O C Consulting (UK) Ltd t/a Manestream INSPECTION BODY Tel: 01992 780300 enquiries@manestream.co.uk. |  |  |  | 2532
Asbestos Removal
5.02.2 | Refer to prelims A54 for Provisional Sum.
5.03 | C40 CLEANING MASONRY/CONCRETE
Brickwork Access Balcony Elevations 3
5.03.1 | Allow to clean all facing brickwork with DOFF, or equal approved system at all access balcony and ground storey levels, entire elevations and inside face of access balcony/communal walkway parapet walls. |  |  |  | 6034
54.03.2 | Allow pilot sample area of 2m2 each to yellow stock and red brickwork to be trialled and agreed with Council and conservation officer prior to full application described above. | 4 | m² |  | 394
5.03.3 | Remove and refix all signs in conjunction with these works to allow cleaning behind. |  |  |  | inc
5.03.4 | Provide all necessary attendances on specialist cleaner and safe temporary electrical supply system, NB may need 240 Volts. |  |  |  | inc
Ground Storey “Stonework” Courtyard Elevation 11, and street and garden elevations 2 and 3.
5.03.5 | Allow to steam clean external ground storey stone/exposed aggregate with DOFF, or equal approved system. Area to include courtyard facing ring beams etc. above ground storey access way up to and including first floor access balcony parapet wall. |  | Item |  | 3439
5.03.6 | Clean as above item inside face of parapet in "stonework" in section from flats 188 to 190. |  | Item |  | 261
5.03.7 | Remove all paintwork to painted brick elevation to flat 203 back to face stock brickwork. |  | Item |  | 614
5.03.8 | Allow pilot sample area of 2m2 to be trialled and agreed with Council representative and conservation officer prior to full application. See specification item C40:232. | 2 | m² |  | 394
Quarry Tiled floors and Grano Stairs
5.03.9 | Deep clean grano floors to ground storey access stair lobby. Deep clean all stair flights and landings. Deep clean separate ground storey lobby to flats 181 and 182. |  | Item |  | 560
5.03.10 | Stairs – Dado red face brickwork. |  | Item |  | 151
5.04 | C41 REPAIRING/RENOVATING/CONSERVING MASONRY - Refer to Section 2
Ground Storey “Stonework” – Courtyard Elevation 11, and street/rear garden elevations 2 and 3.
5.04.1 | Allow to take samples of original mortar to stonework/exposed aggregate bed joints in locations agreed with Council representative, min 2 No per elevation. Analyse samples through a competent testing house (e.g. Sandberg or equivalent) and establish original mix. Provide written report to Council representative. |  | Item |  | 507
5.04.2 | Allow to rake out min depth 19mm and repoint all lose and defective and non-matching joints to stonework in assumed lime mortar, mix to be designed by contractor and agreed with CA subject to test results from item above. Allow Provisional Quantity 15 lin metres. | 15 | m |  | 253.5
Repointing Brickwork
Rake out to 19mm depth and repoint brickwork in random locations as below, to match original style and colour;
5.04.3 | No 188 - 190 - Parapet wall to access balcony, inside face - 1 sqm. | 1 | m² |  | 62
5.04.4 | No 191/192 - Parapet wall to access balcony, inside face - 0.5 sqm. | 0.5 | m² |  | 62
5.04.5 | No 193/195 - Curved parapet wall to access balcony, inside face - 2 sqm. | 2 | m² |  | 123.8
5.04.6 | No 196/197 - Curved parapet wall to access balcony, inside face - 3 sqm. Remove all vegetation growth. Make good vertical crack at abutment with column. | 3 | m² |  | 186
5.04.7 | Flat 198 - curved parapet - rake out and repoint vertical crack, 800mm. | 0.8 | m |  | 21.25
5.04.8 | Main Entrance - rake out and repoint minor areas of mortar. | 2 | m |  | 42.5
Access Balcony Copings Generally
5.04.9 | Rake out to 19mm depth and repoint all copings to match original style ready for painting. |  | Item |  | 282
Brick Repairs –
5.04.10 | Survey all existing face brick work after cleaning and report all defects to Council representative. See F10 for repairs later. |  | Item |  | 282
5.05 | C42 REPAIRING/RENOVATING/CONSERVING CONCRETE - Refer to Section 2
Extent of Surfaces to be Repaired and Re-coated
5.05.1 | The contractor is to carry out repairs and recoating to all existing external exposed concrete at all levels to all elevations of the block, including but not limited to;
5.05.2 | · Ring beams, communal access balconies soffits and edges, and all other concrete features.
5.05.3 | · Private balcony top, soffits and edges, on rear elevation 11 above arch.
5.05.4 | · Communal area staircase - 1No.
5.05.5 | · Exposed aggregate face “stonework” to lower stories all elevations.
Survey
5.05.6 | Undertake a detailed survey of all the concrete surfaces as described in C42 and present findings to the Council's representative by way of a written report, photographs, annotated drawings and approximate quantities of repairs required. |  | Item |  | 550
Preparation
5.05.7 | Allow to thoroughly REMOVE ALL existing concrete coatings to;
5.05.8 | • Access balcony ceilings/soffits and downstand beams/edges/soffits. |  | Item
5.05.9 | • Private balcony and projecting beams and soffits. |  | Item
5.05.10 | • Stair soffits and landing ceilings including lift landings and lobbies. |  | Item
5.05.11 | Check condition of all other coatings and remove locally any lose material to a smooth edge. |  | Item
5.05.12 | Prepare all existing concrete surfaces ready to receive repairs and new coatings, as C42. In the event existing coatings are found to be sound and well adhered, proven by adhesion and pull off tests, existing coatings may remain subject to formal instruction from the Council's representative to this effect. Coating removals to be designed to extract dust and arisings at source, and to include for all temporary protection and sealing of windows, vents, doors and any other apertures that may permit dust penetration into the building. |  | Item
Concrete Repairs – PROVISIONAL QUANTITIES – TO BE REMEASURED
5.05.13 | Break out defective concrete, prepare and prime steel exposed, make good reinforcement bars and bases of staircase balustrades as described in C42, and carry out concrete repairs as C42 to all concrete surfaces allowing the following provisional quantities;
WALL OR COLUMN FACES
Repair as described in C42: items 105 – 165A
5.05.14 | Depth not exceeding 25mm
A | area not exceeding 0.01m² | 5 | No |  | 27.5
B | area exceeding 0.01m² but not 0.05m² | 5 | No |  | 44
C | area exceeding 0.05m² but not 0.10m² | 5 | No |  | 68.75
D | area exceeding 0.10m² but not 0.25m² | 5 | No |  | 129.25
E | area exceeding 0.25m² but not 0.50m² | 5 | No |  | 239.25
F | area exceeding 0.50m² but not 1.00m² | 5 | No |  | 341
G | area exceeding 1.00m² | 1 | m² |  | 85.8
5.05.14 | Depth exceeding 25mm but not exceeding 50mm
A | area not exceeding 0.01m² | 5 | No |  | 44
B | area exceeding 0.01m² but not 0.05m² | 5 | No |  | 88
C | area exceeding 0.05m² but not 0.10m² | 5 | No |  | 132
D | area exceeding 0.10m² but not 0.25m² | 5 | No |  | 280.5
E | area exceeding 0.25m² but not 0.50m² | 5 | No |  | 462
F | area exceeding 0.50m² but not 1.00m² | 5 | No |  | 605
G | area exceeding 1.00m² | 1 | m² |  | 166.1
5.05.15 | Depth exceeding 50mm but not exceeding 75mm
A | area not exceeding 0.01m² | 5 | No |  | 55
B | area exceeding 0.01m² but not 0.05m² | 5 | No |  | 156.75
C | area exceeding 0.05m² but not 0.10m² | 5 | No |  | 264
D | area exceeding 0.10m² but not 0.25m² | 5 | No |  | 462
E | area exceeding 0.25m² but not 0.50m² | 5 | No |  | 759
F | area exceeding 0.50m² but not 1.00m² | 5 | No |  | 837.1
G | area exceeding 1.00m² | 1 | m² |  | 213.4
SIDES & SOFFITS OF BEAMS & LINTELS
5.05.16 | Depth not exceeding 25mm - Side & soffit
A | area not exceeding 0.01m² | 5 | No |  | 27.5
B | area exceeding 0.01m² but not 0.05m² | 5 | No |  | 44
C | area exceeding 0.05m² but not 0.10m² | 5 | No |  | 68.75
D | area exceeding 0.10m² but not 0.25m² | 5 | No |  | 129.25
E | area exceeding 0.25m² but not 0.50m² | 5 | No |  | 239.25
F | area exceeding 0.50m² but not 1.00m² | 5 | No |  | 341
G | area exceeding 1.00m² | 1 | m² |  | 85.8
5.05.17 | Depth exceeding 25mm but not exceeding 50mm - Side & soffit
A | area not exceeding 0.01m² | 5 | No |  | 44
B | area exceeding 0.01m² but not 0.05m² | 5 | No |  | 88
C | area exceeding 0.05m² but not 0.10m² | 5 | No |  | 132
D | area exceeding 0.10m² but not 0.25m² | 5 | No |  | 280.5
E | area exceeding 0.25m² but not 0.50m² | 5 | No |  | 462
F | area exceeding 0.50m² but not 1.00m² | 5 | No |  | 605
G | area exceeding 1.00m² | 1 | m² |  | 166.1
5.05.18 | Depth exceeding 50mm but not exceeding 75mm - Side & soffit
A | area not exceeding 0.01m² | 5 | No |  | 55
B | area exceeding 0.01m² but not 0.05m² | 5 | No |  | 156.75
C | area exceeding 0.05m² but not 0.10m² | 5 | No |  | 264
D | area exceeding 0.10m² but not 0.25m² | 5 | No |  | 462
E | area exceeding 0.25m² but not 0.50m² | 5 | No |  | 759
F | area exceeding 0.50m² but not 1.00m² | 5 | No |  | 836
G | area exceeding 1.00m² | 1 | m² |  | 213.4
SINGLE ARRIS OF WALLS AND COLUMNS
5.05.19 | Depth not exceeding 25mm
Girth 0 -150mm
A | length not exceeding 300mm | 3 | No |  | 47.85
B | length exceeding 300mm but not exceeding 600mm | 3 | No |  | 85.8
C | length exceeding 600mm | 1 | m |  | 48.4
5.05.20 | Depth not exceeding 25mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 136.345
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 263.175
C | length exceeding 600mm | 2 | m |  | 164.384
Depth not exceeding 25mm
5.05.21 | Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 263.175
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 410.96
C | length exceeding 600mm | 1 | m |  | 112.519
5.05.22 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 176
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 280.5
C | length exceeding 600mm | 1 | m |  | 79.2
5.05.23 | Depth exceeding 25mm but not exceeding 50mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 317.46
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 515.35
C | length exceeding 600mm | 1 | m |  | 145.728
5.05.24 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 515.35
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 728.64
C | length exceeding 600mm | 1 | m |  | 192.049
5.05.25 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 317.515
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 452.76
C | length exceeding 600mm | 1 | m |  | 147.972
5.05.26 | Depth exceeding 50mm but not exceeding 75mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 452.76
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 739.86
C | length exceeding 600mm | 1 | m |  | 211.024
5.05.27 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 739.86
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1055.12
C | length exceeding 600mm | 1 | m |  | 246.092
SINGLE ARRIS OF BEAMS AND LINTELS
5.05.28 | Depth not exceeding 25mm
Girth 0 -150mm
A | length not exceeding 300mm | 10 | No |  | 187
B | length exceeding 300mm but not exceeding 600mm | 10 | No |  | 330
C | length exceeding 600mm | 1 | m |  | 53.35
5.05.29 | Depth not exceeding 25mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 159.17
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 295.845
C | length exceeding 600mm | 1 | m |  | 94.281
5.05.30 | Depth not exceeding 25mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 295.845
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 471.405
C | length exceeding 600mm | 1 | m |  | 127.446
5.05.31 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 214.5
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 341
C | length exceeding 600mm | 1 | m |  | 94.6
5.05.32 | Depth exceeding 25mm but not exceeding 50mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 372.02
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 602.69
C | length exceeding 600mm | 1 | m |  | 162.415
5.05.33 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 602.69
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 812.075
C | length exceeding 600mm | 1 | m |  | 219.692
5.05.34 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 372.02
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 525.47
C | length exceeding 600mm | 1 | m |  | 169.059
5.05.35 | Depth exceeding 50mm but not exceeding 75mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 525.47
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 845.295
C | length exceeding 600mm | 1 | m |  | 242.385
5.05.36 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 845.295
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1211.925
C | length exceeding 600mm | 1 | m |  | 279.609
TWO ARRIS REPAIR OF BEAMS AND LINTELS
5.05.37 | Depth not exceeding 25mm
Girth 0 -300mm
A | length not exceeding 300mm | 5 | No |  | 131.45
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 195.25
C | length exceeding 600mm | 1 | m |  | 73.073
5.05.38 | Depth not exceeding 25mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 195.25
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 365.365
C | length exceeding 600mm | 1 | m |  | 111.672
5.05.39 | Depth not exceeding 25mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 365.365
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 558.36
C | length exceeding 600mm | 1 | m |  | 150.601
5.05.40 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 - 300mm
A | length not exceeding 300mm | 5 | No |  | 224.675
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 449.35
C | length exceeding 600mm | 1 | m |  | 146.157
5.05.41 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 449.35
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 730.785
C | length exceeding 600mm | 1 | m |  | 197.285
5.05.42 | Depth exceeding 25mm but not exceeding 50mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 730.785
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 986.425
C | length exceeding 600mm | 1 | m |  | 262.713
5.05.43 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 - 300mm
A | length not exceeding 300mm | 5 | No |  | 454.96
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 636.625
C | length exceeding 600mm | 1 | m |  | 198.484
5.05.44 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 636.625
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 992.42
C | length exceeding 600mm | 1 | m |  | 277.574
5.05.45 | Depth exceeding 50mm but not exceeding 75mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 992.42
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1387.87
C | length exceeding 600mm | 1 | m |  | 325.6
CRACK REPAIRS IN SURFACES OF WALLS, COLUMNS, ETC.
Repair cracks C42:items 105 – 165A
5.05.46 | After preparation width not exceeding 5mm, depth not exceeding 10mm
A | crack length 0 to 150mm | 5 | No |  | 22
B | crack length 150mm to 300mm | 10 | No |  | 60.5
C | crack length 300mm to 450mm | 10 | No |  | 72.6
D | crack length 450mm to 600mm | 10 | No |  | 101.2
E | crack length 600 to 750mm | 10 | No |  | 126.5
F | crack length exceeding 0.75m | 2 | m |  | 33.22
5.05.47 | After preparation width 10mm, depth not exceeding 20mm
A | crack length 0 to 150mm | 5 | No |  | 37.4
B | crack length 150mm to 300mm | 10 | No |  | 101.2
C | crack length 300mm to 450mm | 10 | No |  | 123.2
D | crack length 450mm to 600mm | 10 | No |  | 165
E | crack length 600 to 750mm | 10 | No |  | 198
F | crack length exceeding 0.75m | 2 | m |  | 54.12
5.05.48 | After preparation width 15mm, depth not exceeding 30mm
A | crack length 0 to 150mm | 5 | No |  | 60.5
B | crack length 150mm to 300mm | 10 | No |  | 165
C | crack length 300mm to 450mm | 10 | No |  | 198
D | crack length 450mm to 600mm | 10 | No |  | 269.5
E | crack length 600 to 750mm | 10 | No |  | 365.2
F | crack length exceeding 0.75m | 2 | m |  | 94.6
Large Repairs - Balcony Beams – Straight Sections, render finish
5.05.49 | Cut away concrete to expose balcony edge steel beam as indicated on sketch drawing 5675-A(2)002. Install suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 5 No beams n/e 2.8m clear span between columns/walls | 5 | No |  | 4735.5
5.05.50 | Cut away concrete to expose balcony edge steel beam as indicated on sketch drawing 5675-A(2)002. Install suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 5 No beams approx. 3.3 m clear span between columns/walls. Elevation 3. | 5 | No |  | 7441.5
Large Repairs – Balcony Beams - Straight section, exposed aggregate finish.
5.05.51 | Carry out works as above item but to ground storey balcony beam with exposed aggregate finish.
| Allow Provisionally – 2 No beams n/e 3 metres long. | 2 | No |  | 3265.262
Large Repairs - Balcony Beams – Curved Sections to communal access balconies, render finish.
5.05.52 | Cut away concrete to expose balcony edge beam (assumed steel angle). Provide suitable reinforcement armature and fix to existing steels and concrete as described for above items. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 2 No radius beams @ approx. 3.3 linear metres each. | 2 | No |  | 3591.786
Large Repairs - Stairwell lintels – Straight Sections, render finish
5.05.53 | Cut away concrete to expose assumed steel beam as indicated on sketch drawing 5675-A(2)002. Provide suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 2 No lintels approx. 800mm clear span between columns/walls | 2 | No |  | 721.6
Miscellaneous Large Repairs - Requiring Further Investigation
5.05.54 | Third Floor Ceiling/Soffit near Flat 196 - Cut out crack to soffit to expose structure.
5.05.55 | Allow Provisional Sum of £250 for repair to structural soffit prior to application of fairing coat taken later. |  | Prov Sum |  | 250
LEVELLING MORTAR/FAIRING COAT
5.05.55 | Supply and apply a single component polymer modified cementitious fairing coat/overall levelling coat to ALL concrete surfaces, repaired and sound, on completion of repairs as C42:166A prior to application of anti-carbonation coatings. Include;
| - Communal access balcony beams and lintels, soffits and edges – do not extend over any movement joints |  | Item |  | 1775.4
| - Communal access balcony soffits/ceilings. |  | Item |  | 4438.5
| - Stairs and landings soffits. |  | Item |  | 3329.04
COATINGS
5.05.56 | Prepare, prime and apply anti-carbonation decorative coatings to all concrete surfaces as C42, repaired and existing, comprising silane-siloxane primer and acrylic co-polymer pigmented top coat as C42:167A onwards. Colours to be confirmed with Employer. |  | Item |  | 5728.8
| NB Stairs and communal balcony soffits to be Class O standard. |  | Item |  | Noted
EXPOSED AGGREGATE REPAIRS - GROUND STOREY
WALL OR COLUMN FACES
5.05.57 | Repair as described in C42:105 – 165A
Depth not exceeding 25mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 16.06
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 27.5
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 33.462
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 68.464
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 107.03
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 135.3
G | area exceeding 1.00m² | 1 | m² |  | 86.9
5.05.58 | Depth exceeding 25mm but not exceeding 50mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 18.59
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 43.12
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 66
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 94.6
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 139.48
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 174.9
G | area exceeding 1.00m² | 1 | m² |  | 109.78
5.05.59 | Depth exceeding 50mm but not exceeding 75mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 33.88
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 48.84
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 77.88
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 114.4
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 169.62
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 215.6
G | area exceeding 1.00m² | 1 | m² |  | 133.1
SIDES & SOFFITS OF EXPOSED AGGREGATE FINISH BEAMS & LINTELS
5.05.60 | Depth not exceeding 25mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 16.06
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 27.5
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 33.462
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 68.464
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 107.03
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 135.3
G | area exceeding 1.00m² | 1 | m² |  | 86.9
5.05.61 | Depth exceeding 25mm but not exceeding 50mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 18.59
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 43.12
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 66
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 94.6
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 139.48
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 174.9
G | area exceeding 1.00m² | 1 | m² |  | 109.78
5.05.62 | Depth exceeding 50mm but not exceeding 75mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 33.88
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 48.84
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 77.88
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 114.4
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 169.62
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 215.6
G | area exceeding 1.00m² | 1 | m² |  | 133.1
STAIR REPAIRS
Repair as described in C42:105 – 165A, but with granolithic finish to match existing
Main Stairs
5.05.63 | Ground Floor - bottom tread - repair approx. 100mm x 100mm x 50mm. Reform nosing. | 1 | No |  | 103.554
5.05.64 | First Floor - String repair, approx. 50mm x 50mm x 50mm. | 1 | No |  | 103.554
5.05.65 | First floor - minor nosing repairs up to half landing, allow 5 No n/e 30 x 30 x 30mm. | 5 | No |  | 517.77
5.05.66 | First Floor - first tread and riser repair as above items, approx. 75mm x 75mm x 50mm. | 1 | No |  | 103.554
5.05.67 | Second Floor - first tread and riser repair as above items, approx. 75mm x 75mm x 50mm. | 1 | No |  | 103.554
5.05.68 | Stairs and half landing - full width riser repair as previously described. | 1 | No |  | 103.554
5.05.69 | Upper flight - String repair, 100mm x 100mm x 50mm, repair as described previously. | 1 | No |  | 103.554
5.05.70 | Third Floor - Repair tread approx. 250 x 100 x 100mm including nosing around balustrade. | 1 | No |  | 103.554
5.06 | F10 AND F30/F31 BRICK WALLING AND COPINGS - Refer to Section 2 Specification
Brick Repairs following Render Removal – Walls and Chimnies
5.06.1 | On completion of render removal (taken later in M20) survey all walls and chimnies and provide a quantified report and marked up drawing to the Employer for instructions on repairs and renewals required. |  |  |  | 282
5.06.2 | Allow for brickwork patch repair, stitching, replacement and repointing to damaged masonry following removal of render.
| Allow Provisionally 15 sq. metres in small patches n/e 0.5 sq.m. | 15 | m² |  | 3554.25
Main Roof Parapet Copings
5.06.3 | Remove existing coping stones to entire length of all parapet walls, to entire main roof as indicated on roof plan and clear away from site.
5.06.4 | Supply and install new once weathered top, twice throated coping stones, with suitable expansion joints and neatly pointed and jointed in position. Note coping projections are to suit the new thicker parapet wall design, ply cladding and weatherproofing to achieve clear projection and clear drip throatings on both faces. Refer to drawing No 5675-A(2)001. |  |  |  | 15587.6091
5.06.5 | Expansion joints in copings - to be provided within 1.5 metres of all internal and external corners and generally at not exceeding 12 metres. Joints min 12mm wide, primed and sealed with silicone sealant on polyethylene backing rods. |  |  |  | 345
5.07 | H65 SINGLE LAP ROOF TILING - Refer to Section 2 Specification
Strip Existing roofs 181 - 203 Levita House
Elevations - 2, 3, part 4, 11, and part 12
5.07.1 | Carefully strip up entire tiled roof covering including flashings and accessories. Clear away all redundant tiling complete, along with all battens, accessories and any underlay. |  |  |  | 98072.521
5.07.2 | Allow review of existing "eaves"/parapet detail, ridge and hip details and suitability for new tiling before proceeding. |  |  |  | inc
Additional first fix carpentry - PROVISIONAL
5.07.3 | Tilting fillet - Remove rotten tilting fillet, supply and install new to match existing, assume 125mm wide x 25mm thick. Allow provisional quantity 110 linear metres. | 110 | m |  | 1086.25
5.07.4 | Close Boarding - Remove & renew rotten & damaged roof close boarding (100mm) in various locations - total 150 linear metres, Provisional Quantity | 150 | m |  | 1613.25
5.07.5 | Ridges and Hips - build up ridge board or hip rafter height, allow 50 x 125mm tanalised timber fixed to existing, Provisional quantity 90 linear metres. | 90 | m |  | 1310
Tiling
5.07.6 | Upon completion of insulation works (taken elsewhere) retile the slopes using vapour permeable breathable sarking underlay laid horizontally over boarding as H65. Re-tile using new 38 x 12mm counter battens and 50 x 25mm tile battens and with, ensuring underside of tiles are ventilated as per manufacturer’s written recommendations. |  |  |  | inc
| Tiles to be Sandtoft BRIDGEWATER fixed entirely in accordance with manufacturer’s written recommendations and H65. |  |  |  | Noted
| Colour - SOMERSET |  |  |  | Noted
Detailing
5.07.7 | Ridge, hips, verges to Sandtoft/Wienerberger specification – Note allow for new matching half round mechanically fixed ridges and hips. Complete the design of and supply and fit all flashings and other weathering details. All flashings and weatherings to be in lead as Specification section H71 to meet listed building requirements to minimum Code and details as Lead Sheet Association. |  |  |  | inc
To include but not limited to;
· abutments;
· flashings;
· Valleys;
· secret gutters to dormers and gables;
· Chimney aprons, side flashings and back gutters;
· Dormer flat roof abutments
· pipe, fan and flue penetrations;
· Verges;
· Junctions and saddles;
and all other details as required to complete the installation.
Velux Roof Windows
5.07.8 | Existing Velux type roof windows (approx. 600 x 1200mm) to be retained. Carefully remove flashing kits and clear away. Supply and fix replacement Velux EDZ/EDW flashing kits entirely in accordance with manufacturer's written recommendations. | 1 | No |  | inc
Soil Vent Pipes
5.07.9 | Support all soil vent pipes and other pipe penetrations, removing and refixing as necessary. Provide Code 4 lead slates and weatherings, dressed under tiling on upper side min 100mm and dressed over and to tiles mon 150mm apron, and 150mm each side of pipe/penetration. |  |  |  | inc
Fan Terminals
5.07.10 | Replace all extract fan terminals currently discharging through the roof with new colour matched to tiles, to achieve minimum free air flow as existing. |  |  |  | 612
Fire Breaks
5.07.11 | Supply and install fire breaks over all party walls and communal areas. Fill the space over the wall with layers of mineral fibre quilt so that when the underlay and battens are laid it is lightly compressed. Tuck the edges of quilt between edges of wall and adjoining rafters. Lay 300 mm wide pads of mineral fibre quilt thick enough to seal all gaps and cut to fit snugly between the tile battens. At boxed eaves, completely seal all air paths with compressed mineral fibre quilt to completely fill void on line of party walls. |  |  |  | 912
Roof Insulation - Sloping ceilings/flats with dormers
5.07.12 | Refer to drawing 5675 – A(2)003 and 005. Carefully remove section of sarking boarding without disturbing internal finishes. Supply and install insulation system between rafters, in each rafter void, to "lap" parapet gutter insulation as detail drawings. Insulation to be as specified in Section 2 - P10 and as indicated on drawings. |  |  |  | 14620
5.07.13 | Reinstate sarking boarding with existing and make up quantity with matching new as required, to be screw fixed, not nailed, twice on each rafter |  |  |  | 8372
Remove existing insulation - sloping areas PROVISIONAL
5.07.14 | Allow Provisionally to remove assumed existing inadequate mineral wool and chicken wire insulation and clear from site. |  | Prov Item |  | 2059
Roof Insulation - Horizontal areas
5.07.15 | Allow Provisionally to remove assumed existing inadequate mineral wool and chicken wire insulation and clear from site. |  | Prov Item |  | 1789
5.07.16 | Supply and lay two layers 150mm mineral wool insulation as specification P10, 150mm laid between ceiling joist, 150mm laid over first layer at 90 degrees. Ensuring “eaves” ventilation to sloping parts is maintained. Sarking board removal taken with sloping insulation item |  | Item |  | 11183
5.07.17 | Roof Access Hatches - Allow provisionally to carefully cut out ceiling, trim joists and install proprietary loft access hatch, fully insulated and draft proofed, U Value 0.35, 30 mins fire resistance, Class O spared of flame Push-Up Loft Access Door Matt White 630 x 630mm approx. Make good ceiling and adjacent decorations disturbed, assuming two coats white emulsion to entire room or landing affected. | 5 | No |  | 1216
5.08 | H71 LEAD SHEET COVERINGS/FLASHINGS - Refer to Section 2 Specification
Dormers
5.08.1 | Carefully remove and cart away for recycling all dormer window cladding and roof coverings. |  |  |  | 912
Dormer Cheeks - insulation
5.08.2 | Carefully remove timber boarding to cheeks and supply and install insulation system between studs to be non combustible mineral wool and vapour permeable breather membrane on outer side. Leave 25mm air gap with insect screen, and reinstate new 12mm WBP ply boarding ready for cladding, making up quantity as necessary. Provide full details of selected materials for comment prior to proceeding. Refer to drawings 5675 – A (2) 003 and 004. 21 No dormers this block. | 20 | No |  | 40775
Dormer Roofs - insulation
5.08.3 | Supply and install insulation system to all dormer roofs carefully removing and replacing timber decking as required, assumed 100mm rigid mineral wool vapour permeable system. Provide 50mm ventilation gap as detailed and 18mm WBP ply deck to falls and cross falls. Provide full details for comment prior to proceeding. Leave ready for cladding. Refer to drawings 5675 – A (2) 003 and 004. | 20 | No |  | inc
Dormer Cladding and Roofing
5.08.4 | Supply and install Code 5 lead cladding and roofing to dormers ensuring all lead work to Lead Sheet Association recommendations, thickness Codes etc. Form all detailing, drips rolls, splash laps, clips, and joints similar to existing (note Listed Building) taking care to ensure falls are correct. Dormer roofs to fall to each side and not discharge over the windows to avoid dripping on widow cills. Include insect mesh as detailed. Form min 150mm effective vertical height sloping upstand and fillet to underside of tiled roof abutments at top of dormer including welted edge. See drawing No 5675-A(2)004. | 20 | No |  | inc
5.08.5 | Supply and fit new s.w. PAR fascias to dormers and leave ready for decorations. Ensure all surfaces including back of fascia primed and undercoated before installation. Assume 25mm x 150mm. | 20 | No |  | inc
Chimney “dormers” infill – 1No. Chimney 12
5.08.6 | Carefully strip, re-roof and re-clad in lead 2No lead “dormer” infill structures located behind the main block chimnies, all as item 5.08.4 above. Refer also to roof plan L (0)011 for locations. | 1 | No |  | 949.5
5.09 | J21 COMMUNAL ACCESS BALCONIES - ASPHALT REPAIRS
Carry out asphalt repairs to communal access balconies using hot poultice method as J21 as follows;
5.09.1 | Ground Storey Walkway near flat 183 - cut out and renew asphalt fillet around gas pipes. 1 No n/e 0.5 sqm | 1 | No |  | 32.07
5.09.2 | Area outside flats 184 and 185 - take up asphalt complete and relay to correct falls, reforming drainage channel and dressing into outlet. Reform fillet/upstand to parapet. Allow approx. 5 sq.m | 5 | m² |  | 478.13
5.09.3 | Parapet - 185 - Cut out and reform fillet/upstand. Allow 15 linear metres. | 15 | m |  | 379.69
5.09.4 | Works in conjunction with flat entrance door replacement - PROVISIONAL - Cut out asphalt and reform upstands and fillets to flat entrance doors after replacement. Allow 13 No. | 13 | No |  | 416.82
5.09.5 | Third Floor Access Balcony - Renew fillet to top of asphalt upstand flats 196 - 197. Allow 20 linear metre total. | 20 | m |  | 303.75
5.09.6 | Curved balcony projection - take up asphalt complete and relay with new lead welted drip trim, and weather to all metal railing details. | Item |  |  | 928.13
5.09.7 | Private balcony - Take up and renew asphalt complete to private balcony, elevation 11 above entrance arch, in two coat asphalt. |  | Item |  | 590.63
5.09.8 | Private balcony - Take up and renew asphalt complete to private balcony, elevation 3, in two coat asphalt. |  | Item
590.63
5.1 | J31 PARAPET GUTTER AND ASSOCIATED FLAT ROOFS - LIQUID APPLIED WATERPROOFING - Refer Section 2 Specification
Introduction
5.10.1 | The refurbishment of the internal parapet gutters is to be carried out in conjunction with the replacement of the main pitched tiled roofs. Works will need to be designed and programmed to ensure that the installation works co-ordinate satisfactorily and any finished areas of gutters are protected from other trades. |  |  |  | Noted
| NB in addition to the gutters the wider gutter extensions/roofs areas are to be treated similarly , on this block (1 No location 11 near chimney 19/20) and 2 No bay roofs to elevation 3 at ground storey entrance level. See roof plan. |  |  |  | Noted
5.10.2 | The gutter lining system shall not be a hot works solution, no hot works are permitted at roof level. Please refer to drawing 5675 – A (2) 001 for existing detail. For the contractor's information Block 1-21 incorporated the use of Moy Materials Ltd ENKOPUR system, Tel 07917 896307 or 012435 707449. |  |  |  | Noted
5.10.3 | Cores - In conjunction with the selected Liquid system supplier who will be guaranteeing the installation take cores samples through parapet gutter and roofs over sufficient areas to establish the existing roof/covering build up. |  | Item |  | 330
5.10.4 | Adhesion tests - carry out adhesion test of waterproofing to parapet gutters base and sides, and allow to cure for 1 week before proceeding. |  | Item |  | inc
Waterproofing and Insulation
5.10.5 | Supply and install complete cold poured polyester resin fleece reinforced waterproofing and thermal insulation lining system to the parapet gutters. Ensure insulation proposals link with pitched roof insulation. Selected solution is to be provided and installed to achieve a minimum 15 year BBA certified single point guarantee for labour, materials and workmanship and as such will need to be a proprietary system installed by a system approved specialist. |  |  |  | 33523.86
5.10.6 | Preparation - Power wash all surfaces. Remove existing localised repairs. Remove all moss, dirt and debris. Inspect and repair the existing surface. Blisters in the asphalt should be carefully warmed, pierced and smoothed down to a level surface to receive the overlay system. |  |  |  | inc
5.10.7 | Copings – see F10/31, and schedule of works section 5.06. |  |  |  | inc
5.10.8 | Parapet Walls - Make good any localised damage to existing parapet walls, as required, and board out the internal face of parapet with 12mm plywood (mechanically fixed), to allow the new waterproofing to be dressed up and over. Refer to drawing detail 5675-A(2)005 for change in wall thickness on inside face of parapet. |  |  |  | 16197
5.10.9 | Cut new chases in rendered abutments at increased height (staircase walls and chimney stacks), to receive new lead flashing (upstand 150mm min). |  |  |  | inc
5.10.10 | Supply and fit a lay-board to allow dressing of the new waterproofing below the pitched tiled roof as drawing No 5675-A(2)005. |  |  |  | inc
5.10.11 | Coordinate gutter lining with replacement lead cladding to dormers. Remove lead flashings and lead cheeks from dormer windows to allow access for waterproofing. Surfaces to receive waterproofing must be clean, smooth and dry. |  |  |  | inc
Priming
5.10.12 | Supply and apply suitable substrate Primer to existing asphalt. Carry out adhesion test and record results. Allow to dry. |  |  |  | 16506
Vapour Control Layer
5.10.13 | Supply and install suitable vapour control layer under insulation, self-adhesive. |  |  |  | inc
Insulation
5.10.14 | Supply and lay suitable insulation e.g. 140mm rigid Insulation (bonded in suitable Insulation Bonding Adhesive). U Value 0.18W/m²K (compliant with Building Regulations Part L 2010) as indicated on the drawing 5675-A(2)005. |  |  |  | inc
Insulation Priming and Preparation
5.10.15 | Prime upper face of insulation with Bonding Agent and allow to dry. Apply preparation Layer self-adhesive. |  |  |  | inc
Waterproofing - gutters, roofs and details
5.10.16 | Supply and lay cold pour resin waterproofing including primer to detailing, finish colour Dark Grey, all to coverage rates specified by manufacturer to achieve guarantee. Ensure bridging tape used at junction of dissimilar materials. Use MC Primer at all metal outlets, lead chute and pipes. Ensure all upstands are min 150mm. |  |  |  | inc
Cover Flashings - chimnies 12, 14, and 18 and walls (excluding parapets as these are coated full height and under copings)
5.10.17 | Except where waterproofing is dressed over parapet under coping and up adjacent roof slopes all abutments to be provided with Code 4 lead cover flashings as recommended by the Lead Sheet Association. |  |  |  | inc
Rainwater Outlets
5.10.18 | Locate and renew all rainwater outlets. Form sumps to all outlets and leave clear and free flowing on completion. |  |  |  | 2577
Cables
5.10.19 | Throughout the works carefully support all data and communications cabling, noting there are large bundles of cables running along the parapet and copings, as well as some in the parapet gutter itself. All lose cables in parapet gutter to be re-supported on suitable galvanised tray support on re-fixed copings to Employers approval. |  |  |  | inc
Railings
5.10.20 | Carefully unbolt, label, set aside and ultimately refix railings fixed to parapet walls and copings, all elevations. |  |  |  | inc
5.11 | J31 FLAT ROOFS – NON RESIDENTIAL
Flat Roofs
5.11.1 | Flat roofs are provided to this block the ground storey bin stores on courtyard elevation 11 and ground storey bay roofs to elevation 3. Refer to roof plan L (0)011. All are to be overlaid. |  |  |  | inc
Waterproofing
5.11.2 | Supply and install complete waterproofing system to the flat roofs. No insulation required. Design solution is to be provided and installed to achieve a minimum 15 year guarantee for labour, materials and workmanship and as such will need to be a proprietary system installed by an approved specialist. |  |  |  | inc
Preparation
5.11.3 | Remove existing localised repairs. Remove all moss, dirt and debris. Inspect and repair the existing surface. Blisters in the asphalt should be carefully warmed, pierced and smoothed down to a level surface to receive the overlay system. |  |  |  | inc
5.11.4 | Bay Roofs (street elevation) – Carefully remove all buddleia growth, rubbish and debris collected on these two bay roofs and clean ready for re covering works. Example below. |  |  |  | inc
5.11.5 | Copings - Remove existing coping stones to 2 No small high level parapet walls on elevation 11, replace with wider copings as described elsewhere. Example below. |  |  |  | 1860
5.11.6 | Parapet Walls - Make good any localised damage to existing parapet walls, as required, and board out the internal face of parapet with 12mm plywood (mechanically fixed), to allow the new waterproofing to be dressed up and over. |  |  |  | inc
Waterproofing - all flat roofs noted above.
5.11.7 | Supply and lay cold pour resin waterproofing including primer to detailing, finish colour Dark Grey, all to coverage rates specified by manufacturer to achieve guarantee. Ensure bridging tape used at junction of dissimilar materials. Use MC Primer at all metal outlets, lead chute and pipes. Ensure all upstands are min 150mm. |  |  |  | inc
Cover Flashings
5.11.8 | All abutments to be provided with non lead flashings. Cut new chases in rendered abutments at increased height (staircase walls), to receive new Ubiflex B3 or equivalent Lead Alternative Grey 3.5mm thick flashing (upstand 150mm min). Lead alternative. Seal with suitable Gap Seal and Fixing wedges.
Perimeter Trims and detailing
5.11.9 | Supply and install all necessary GRP trims and other detailing to roof edges, forming upstands, water checks and kerbs as required. |  |  |  | inc
Rainwater Outlets
5.11.10 | Locate, design and renew all rainwater outlets, design and form sumps to all outlets and leave clear and free flowing on completion. |  |  |  | inc
5.12 | L10 WINDOWS
New Windows
Design and Listed Building Consent
5.12.1 | Complete the detailed design of the new replacement windows and provide drawings as specification item L10:210A. |  |  |  | Noted
5.12.2 | Considerable effort has gone into achieving a design acceptable for listed building consent, window details and frame dimensions shall not be varied against the approved drawings. An approved sample sash window Type K and a tilt window Type J have been fitted in flat 182 which can be inspected externally. The type K window is to be the minimum standard acceptable on this project for a sash window but will need to be replaced to allow for installation of external architrave and head flashing details. The type J tilt/hopper window needs to be replaced, it is broadly acceptable but improved detailing is shown on the tender drawings. |  |  |  | Noted
Supply and Installation
5.12.3 | NB it is a specific requirement of the Employer that the window manufacturer shall supply and fit the windows, not just supply for installation by others. |  |  |  | Noted
Pilot Flat
5.12.4 | Windows - Allow to complete the removal and replacement of windows in 1No. Flat including all window types in full, including all making good, prior to progressing the fabrication and installation of further windows, all to the satisfaction of the Employer. Allow out of sequence working ahead of main programme. |  |  |  | 1250
Surveys
5.12.5 | Every window shall be surveyed and manufactured to suit the specific opening. The contractor should allow to remove and dispose of the external architraves fitted to vertically sliding sash windows to enable the actual structural opening size to be established. Allow for any temporary seals to windows once architraves are removed. Similarly turn back lead head flashings as required to allow accurate survey. |  |  |  | inc
Remove Existing Windows – all flats
5.12.6 | Carefully remove existing timber windows, fanlight and side lights and ensure units are only removed if they are to be replaced the same working day. See clause 5.12.12 below which will be strictly enforced. |  |  |  | 8044
5.12.7 | Notes from pilot window installation;
| - Vertically sliding sash windows are not original, they are fixed with lugs/straps back into the plaster reveals. |  |  |  | Noted
| - The new sash window frames are deeper than existing, the contractor must allow to carefully cut away internal plaster to allow the windows to be set into the reveals to achieve an external reveal suitable for sealant. |  |  |  | Noted
| - Tilt windows do appear to be original and are built in, bedded on mortar with frame ties. The mortar bedding will need removing from brickwork, the ties need cutting. |  |  |  | Noted
5.12.8 | Remove windows as below: (Approx. Quantities - contractor to verify and confirm with tender. All windows to be replaced and to the entire block unless indicated otherwise on drawings). |  |  |  | Noted
| Bring forward total cost of windows to this block from window schedule here. |  |  |  | 274175.297
Generally
5.12.9 | Allow for ensuring all timber framing materials and glass is recycled once removed from site. Allow for removal of any debris from existing units and thoroughly clean the working area. |  |  |  | inc
5.12.10 | Allow for all reveal surfaces of the openings to be cleaned to remove all existing frame sealant, mastic, bedding mortar etc. ready for the installation of the new units. |  |  |  | inc
5.12.11 | Security fittings - many windows have security bars and fittings attached on a "DIY" basis. Allow to remove and discard but option to return fittings to residents. |  |  |  | inc
5.12.12 | Under no circumstances shall a window be removed unless the replacement window is ready, checked and suitable for installation, with sufficient time that day to complete the installation. Appointments with residents should not be made until the replacement window or door is manufactured and quality checked in the factory, delivered to site and re-checked, ensuring it is clearly labelled for the given flat and all components are available and undamaged. Allow for all necessary on site storage. |  |  |  | Noted
Replacement Windows – all flats
5.12.13 | Complete the design, manufacture, supply and installation of engineered timber windows systems together with glazing as required in Section L10 of Section 2 – Materials and Workmanship and as detailed on drawings to meet Secured by Design PAS 24 standards. Windows to comprises high performance double glazed; |  |  |  | inc
· Vertical sliding sash with semi concealed balances, NO tilt facility, and
· Casements, outward opening,
· Inward opening hopper/tilt inwards windows (Accepted not Secured by Design)
· Fixed lights
and combinations thereof as indicated on the approved listed building consent and planning drawings.
5.12.14 | Contractor to allow for and design all associated ironmongery and necessary fixings to create a fully operational, safe and user friendly window system. Refer to L10 specification. |  |  |  | inc
5.12.15 | Tilt/hopper and casement window frames on access balconies are to be positioned level with the existing external window line wherever possible. Sliding sash windows to be set back into the reveals as described earlier. Ensure all frames are plumb, and level and without bow. Window positioning in the reveals is key to the listed Building Consents as well as retention of sight lines and glazing bar profiles. |  |  |  | inc
5.12.16 | Provide fully detailed drawings and ironmongery specifications period to manufacture for comment by Employer. |  |  |  | inc
5.12.17 | Windows to include trickle vents. External vent canopies are not permitted by the listed building consent, all vents to be concealed externally. Design to minimum Exposure Category B and Window Energy Rating A/whole window U value n/e 0.6, Secured by Design (except tilt windows where Employer accepts not achievable). |  |  |  | inc
1. Air permeability 600 PA
2. Water tightness 300 PA
3. Wind resistance 2000 PA
Sealants
5.12.18 | Prime and Seal all external joints between framing and structure with low modulus neutral cure silicone sealant to BS5889 (1989). Sealant backing to be provided and detailed in drawings. |  |  |  | 5907
Making Good
5.12.19 | The contractor shall be responsible for and allow for all making good work to window openings, both internally and externally, including external rough cast render margin around all sash windows, masonry, plaster, all cills, reveals, jambs, heads, tiling, decorations etc. cladding and decorative finishes to reveals. |  |  |  | 31551
| Note - External reveals to sliding sash windows in rendered elevations to include making good perimeter with roughcast render finish to M20 specification to allow for setting windows back into the reveals. Tilt windows to be made good with mortar collar joint externally, raked out to min depth 15mm before pointing. Collar joint works to be by experienced bricklayers. |  |  |  | 31551
Internal trims to be min 30 x 10mm painted timber (PVC not permitted).
5.12.20 | No additional allowance will be made for costs associated with making good unless identified as pre-existing damage in the schedule of condition (item 4.0 J earlier) and prior instructions obtained from the CA. |  |  |  | Noted
Electrical and Other Services
5.12.21 | Allow for unclipping all existing telephone cables, aerial cables and the like from existing windows frames, and re-clip to surround in a suitable location using new cable clips of appropriate size and colour. Any cables passing through a frame/structure joint shall be routed through a plastic sleeve, the inner end of which is to be higher than the outer to prevent water penetration along or through the sleeve. |  |  |  | 4481
5.12.22 | Disconnect and reconnect to appliances as required and leave in full working order on completion to resident's satisfaction. |  |  |  | inc
Curtain Tracks, Net Curtain Hooks and Furnishings
5.12.23 | Remove and re-fit existing curtain tracks and other soft furnishings as applicable. Curtain rods to be plugged and screw fixed with new hooks to window reveal soffit, not frame head where it would obstruct trickle vents and ironmongery. Inform Employer of any tracks and soft furnishings not suitable for re-instatement. |  |  |  | inc
Completion
5.12.24 | Upon completion of and on the same day of the installation of each replacement window/door, all glazing, window frames, handles and all other surfaces are to be cleaned with a mild detergent. All components are to be checked for security of fixings, adequacy of clearances, adjustment of hinges, locks etc. as may be necessary to leave the window/door units in good working order. |  |  |  | Noted
5.12.25 | On completion of window installation on the same day the contractor shall: |  |  |  | Noted
- Snag his own work and make good.
- Remove all debris, dirt etc.
- Clean the window inside and out.
- Demonstrate the operation of the window to the resident and ensure the resident confirms that they understand the methods of window operation, notably any ironmongery operation, cleaning facilities, restrictors and locks.
- Obtain a signed sheet from the resident confirming:
1. They are satisfied with installation.
2. Making good is complete.
3. Cleaning completion.
4. Understand how the windows work.
Should the contractor fail to complete this process access to other flats to start new installations will be denied until the process is complete and under such circumstances no delays or associated costs will be entertained by the Employer in this regard.
5.12.26 | External Architraves Allow to supply and fit ex 20 thick x 30mm wide 19 x 75mm moulded external architraves to all sash windows all elevations. See detail drawing. Fully decorated with microporous paint system to match windows. |  |  |  | inc
5.12.27 | Head Flashings - To all vertically sliding sash windows and casement windows located on elevations (excluding access balconies, supply and fit new 0.7mm welted zinc head drip flashings as detail. |  |  |  | inc
FENSA
5.12.28 | For window and door replacement works provide a FENSA certificate for every flat, with a copy for the Employer. |  |  |  | inc
5.13 | L20 DOORS
Doors – Flat Entrance and other Secondary residential doors to flats
Design
5.13.1 | Complete design new doors and provide drawings in accordance with L20.
5.13.2 | Allow to design, supply and install new complete pre-fabricated engineered timber door set systems complete with side and fan lights, Secured By Design and with glazing bars to suit Listed Building Consent. See L20:410A.
5.13.3 | NB it is a specific requirement of the Employer that the door manufacturer shall also supply and fit the doors/windows, not just supply for installation by others.
5.13.4 | Note doors to comply strictly with Listed Building consent. All doors to be fire rated, see scope of works below.
5.13.5 | Sample Flat Considerable effort has gone into achieving a design acceptable for listed building consent, door details and frame dimensions shall not be varied against the approved drawings. A sample door and side light have been fitted in flat 182 which can be inspected externally. This sample is not fully compliant and will need to be replaced in line with the tender drawings, but broadly demonstrates the style required noting incorrect details such as glazing bars, trickle vent etc are not acceptable.
Secondary Door
One flat appears to have a secondary door, located 198/199. This door is to be provided to meet listed building consent but will require internal thumb turn/emergency means of escape purpose ironmongery, not operable from outside i.e. effectively “dummy” door. Allow to survey flat to confirm requirements before ordering.
Pilot Flat
5.13.6 | Entrance Door - Allow to complete the removal and replacement of 1No. Flat entrance door, including all making good, prior to progressing the fabrication and installation of further doors to the satisfaction of the Employer. Allow out of sequence working ahead of main programme.
Note the doors and adjacent windows are to be from one manufacturer/supplier/installer, to achieve the required certification. Bespoke solutions of windows and door systems being joined together will not be accepted unless PAS 24 certified as a complete unit.
Flat entrance Doors - 181 - 203
5.13.7 | Type I door and OPENABLE side window units - 182, 183, 187, 191, 196 and 202 | 6 | No |  | 14200.8
| Type R - door no side window - flats 186, 190, 195 and 201 | 4 | No |  | 7435.7
Fire Rated Flat Entrance doors and side windows
5.13.8 | Note - Doors and borrowed/side lights creating balcony 'dead-ends' in terms of means of escape in case of fire to be FD30 and all glazing to be non-wired with 30 min fire integrity, FIXED SHUT. Applies to;
| Type I - Flats 184, 185, 188, 189, 192, 193, 194, 197, 198, 199 and 203. | 11 | No |  | 26037
| Type R - fire rated door without side window - "dummy door" between 198/199, and flat 181. | 2 | No |  | 3673.2
Making Good
5.13.9 | The contractor shall be responsible for and allow for all making good work to door openings, both internally and externally, including masonry, plaster, all cills, reveals, jambs, heads, tiling, decorations etc. cladding and decorative finishes to reveals. Perimeter of doors and side window to be made good with mortar collar joint as described for tilt/hopper windows on access balconies. |  |  |  | inc
| No additional allowance will be made for costs associated with making good unless identified as pre-existing damage in the schedule of condition and prior instructions obtained from the Employer. |  |  |  | Noted
Sealants
5.13.10 | Prime and Seal all external joints between framing and structure with low modulus neutral cure silicone sealant to BS5889 (1989). Sealant backing to be provided and detailed in drawings. |  |  |  | inc
Completion
5.13.11 | Upon completion of and on the same day of the installation of each replacement door, carry out all checks as item 4.12.24/25 for windows. |  |  |  | inc
Electrical, Access Control and Other Services
5.13.12 | Disconnect and refix access control cables and system as required. Allow for unclipping all existing telephone cables, aerial cables and the like from existing door frames, and re-clip to surround in a suitable location using new cable clips of appropriate size and colour. Any cables passing through a frame/structure joint shall be routed through a plastic sleeve, the inner end of which is to be higher than the outer to prevent water penetration along or through the sleeve. |  |  |  | inc
| Disconnect and reconnect to appliances as required and leave in full working order on completion to resident's satisfaction. |  |  |  | inc
Main Communal Entrance Doors
5.13.13 | Prior to commencement validate operation of access control system and report any defects. | 3 | No |  | inc
Overhaul Communal Doors – Elevation 3
5.13.14 | Thoroughly overhaul 2 No. existing communal doors/gates; ease and adjust, lubricate all ironmongery, adjust and test self-closers to leave in sound working order. | 2 | No |  | 172.67
Store Doors, lift lobby cupboard doors, and Meter Cupboard Doors
5.13.15 | Thoroughly overhaul existing doors; ease and adjust, lubricate all ironmongery, adjust and leave in sound working order ready for decorations taken elsewhere. Allow 8 No Provisional Quantity. | 8 | No |  | 450.29
Resident Security Gates/Doors
5.13.16 | Allow Provisionally to take off and return to occupant security door or gate fitted over flat entrance door. Make good all surfaces disturbed | 2 | No Prov Item |  | 180
FENSA
5.13.17 | Provide FENSA certificate for each door and window unit installed as described in windows section previously. |  |  |  | inc
5.14 | BOILER FLUES AND GAS FIRES
5.14.1 | The contractor should note some flats have boiler flues that penetrate windows/doors. Allow to, as necessary, design, disconnect, adapt, provide bespoke door/window panel, and re-use boiler flues where they penetrate door or window openings. |  | Item |  | 616
5.14.2 | Provide Gas Safe engineer's certificate for any work to boilers and provide a new CP12 landlord's certificate for the affected flats. |  | Item |  | inc
5.14.3 | Where boiler flues pose a risk to the contractors workforce, e.g. concrete and render repairs allow for close resident liaison to turn off boilers on a daily basis and restart on completion of works in the vicinity. |  | Item |  | inc
Fireplaces and Flues
5.14.4 | Prior to commencement of any works to chimnies, (e.g. render renewal, brick repairs and the like) fully survey all flats internally and establish any open fireplaces, vents and gas appliances. All open fire places and vents to be fully sealed during the works. All gas appliances to be temporarily disconnected and reinstated on completion of chimney works and flue checks. Provisional sum taken later for gas appliances, all other works to be priced here. |  | Item |  | inc
5.14.5 | Allow the provisional sum of £2,000 for works to gas fires as may be required over and above item 5.14.1 - 4 above. |  | Prov Sum |  | 2500
Air Vents in Brickwork
5.14.6 | Carefully cut hole in external brick wall assuming 330mm thick and install 215 x 215mm Terra cotta square hole clay air brick BS 493: 1995 externally with insect mesh (gas compliant) , and white plastic louvre internally. Make good all surfaces disturbed. Allow Provisional Quantity. | 4 | No Prov Item |  | 528
5.15 | M20 - RENDERED/ROUGHCAST COATINGS - Refer to Section 2 Specification
Survey and test existing – All Elevations 3 and 11
5.15.1 | See earlier item regarding gas fires. Allow for hammer testing of entire existing external render to all existing rendered surfaces including walls, chimneys and gables. Provide a detailed report and marked up drawings showing all defective and sound areas for agreement on extent of works to go forward. |  | Item |  | 237
Samples and Control Sample Area
5.15.2 | A - Mix samples. In agreement with Employer take a minimum of 10 No samples of original render (not modern patch repairs) from various levels and elevations. Clearly label and identify and submit to a specialist competent testing house to provide a detailed analytical report on the original design mix and constituents. Agree with Employer and conservation officer appropriate mix for repairs and renewals. | 10 | No |  | 788
| B - Control Sample Trial Area - re render to full specification min 2 sq. m in agreed location and fully paint as M60. Allow to dry for agreement before proceeding with remainder of works. | 2 | m² |  | 122
Chimnies - Nos 12, 13, 14, 15, 16, 17, 18, and 19 (refer to roof plan for locations) various heights
5.15.3 | Allow to remove all render complete to all 11 chimnies to this block and prepare brickwork for re-rendering, including dubbing out and pointing up lose and defective brickwork. See also item 4.14 earlier in this section.
5.15.4 | Re render chimnies in roughcast style to match original design mix (established from items above) and texture and leave ready for painting. Include stop and drip beads to all flashings and weatherings.
NB new render to be applied to a consistent standard, spraying of top coat recommended. See example on block 1-21 courtyard elevation and chimnies.
Flaunchings – 11 chimnies
5.15.5 | Remove and re-flaunch all flue terminals and pots in sand: cement mortar finished to a neat weathered profile. |  |  |  | 1200
Elevations
5.15.6 | Carefully hack off render as schedule below. Prepare surfaces and re-render in roughcast pattern to an agreed mix, assume 1:1:6. Note - rendering to be carried out by experienced and competent conservation/restoration specialists to meet requirements of Listed building consent and as M20. Form rebates/reveals/returns to all window and door openings to match original design intent. Note spraying recommendation as for chimnies and previous example in courtyard (north) elevation of block 1 - 21 Levita.
5.15.7 | Subject to testing in items above allow for provisional areas and/or quantities as follows and with reference to the drawings;
| 1. Elevation 3 - complete first storey upwards to all access balcony areas and returns, i.e. from above archway to end of flat 190 up to parapet 198 - 201, and upper level 202 to 203. NB Excluding access balcony column features. NB The decorative parapet features are not to be removed. |  | Item |  | 1688
| 2. Elevation 3 remainder - other rendered areas, patch repairs. Provisional allowance 10 sqm. | 10 | m² |  | 675
| 3. Elevation 11 - rendered areas, patch repairs. NB The decorative parapet features and balcony recess features are not to be removed. Provisional allowance 15 sqm. | 15 | m² |  | 1013
| 4. Elevation 2 - rendered areas, patch repairs. NB The decorative parapet features are not to be removed. Provisional allowance 5 sqm. | 5 | m² |  | 338
| 5. Decorative features parapet level - Extra over above item for reforming decorative features to parapet level, allow 40 linear metres of parapet. Provisional Quantity | 40 | m |  | 3375
| 6. Extra over above item reform curved feature to access elevation balcony columns. Allow 10 No Provisional quantity. | 10 | Prov Quant |  | 844
5.16 | M60 - PAINTING/CLEAR FINISHING
Redecorations
5.16.1 | Prepare and decorate all previously or usually decorated surfaces and elements. Thoroughly prepare and redecorate all previously or usually so treated surfaces including, but not limited to; |  |  |  | 46365.44
Joinery M60:130
5.16.2 | · Communal area store doors and frames, plant rooms and intakes, roof access hatches, etc. not stained or otherwise treated. NB all painted inside and out. |  | Item |  | inc
5.16.3 | · Elevation 11 painted pipe casings near bin store. |  | Item |  | inc
5.16.4 | · Communal access balcony top floor boxed in rainwater outlets serving parapet gutter. |  | Item |  | inc
5.16.5 | · Any other previously or usually so treated joinery. |  | Item |  | inc
5.16.6 | · Stairs dado rail |  | Item |  | inc
5.16.7 | · Dormer window fascia details. | 21 | No |  | inc
Joinery M60:171A - Stained
5.16.8 | · Hardwood louvres to return of elevation 11 above bin stores. |  | Item |  | inc
Metalwork M60:130
5.16.9 | · Communal access balcony railings, mesh and perforated panels, security gates and screens (including previously powder coated), and all other usually so treated features, fixtures and fittings. NB Allow for additional preparation to severely corroded areas, to be needle gunned, grit blasted or otherwise treated to remove heavy corrosion. Apply suitable metal fillers to all pitted areas. Advise Employer of any steel found to be unsound. |  | Item |  | inc
5.16.10 | · Communal access balcony conduit and trunking capping, overflows etc. NB allow for suitable primer to galvanised surfaces and note extensive existing flaking paintwork. |  | Item |  | inc
5.16.11 | · Communal stairs balustrades and handrails internally, and externally to entrances. |  | Item |  | inc
5.16.12 | · Communal area railings and gates at top floor providing access to tank room and roof void. Stairs balustrades and handrails internally, and externally to entrances. |  | Item |  | inc
5.16.13 | · Doors to former bin chutes/lift motor room, inside and out and electrical risers (ground storey). |  | Item |  | inc
5.16.14 | · SVPs, wastes, RWPs and hoppers all levels. |  | Item |  | inc
5.16.15 | · Refuse hoppers (sealed shut), all levels. |  | Item |  | inc
5.16.16 | · Gas distribution pipes. On completion supply and fit 50mm wide pipe marking and identification tapes, manufactured to BS1710 and BS4800, at 10m centres and within 300mm of any penetrations through walls, floors and ceilings, or change of direction. |  | Item |  | inc
5.16.17 | · Dry riser doors and frames, including de-rusting. |  | Item |  | inc
5.16.18 | · Dry riser pipes where exposed. |  | Item |  | inc
5.16.19 | · All gutters and downpipes, to include INSIDE of all conventional eaves gutters to elevation 11 bin store. |  | Item |  | inc
5.16.20 | · Steel handrail to top of parapet gutter parapet walls. |  | Item |  | inc
5.16.21 | · Garden and Footpath/garden wall railings to street elevation 3. |  | Item |  | inc
Rendering and painted brickwork - M60:170 MAXIMUM EXPOSURE SMOOOTH MASONRY PAINT
5.16.22 | · All render to all elevations including chimnies and all columns. |  | Item |  | inc
5.16.23 | · All existing painted brickwork to inside face of parapet walls and access balcony walls only where painted at present. Note any brickwork unpainted is to remain unpainted, protect throughout the works. |  | Item |  | inc
5.16.24 | · Street facing dwarf walls, walls to entrance steps, ramps etc. Allow to remove all vegetation growth in advance of preparation and decoration. |  | Item |  | inc
5.16.25 | · Copings to all access balcony parapet walls and to main roof parapet gutters. Allow to remove all vegetation growth in advance of preparation and decoration. |  | Item |  | inc
5.16.26 | Note - Masonry paint colours will be predominantly Classic Cream with white features to be picked out, e.g. access balcony copings and columns, to be confirmed by CA on site. Allow for masking and cutting in.
Communal stair walls and stair soffits, communal access balconies - Specification M60:170A
5.16.27 | Textured soffits to stairs and communal walkways - carefully remove all existing textured coatings back to sound substrate and make good ready for new coatings. |  | Item |  | inc
5.16.28 | To all walls carefully remove localised areas of failed coatings back to sound render and brick substrate. Jet wash all surfaces ready for new coatings. |  | Item |  | inc
5.16.29 | Prepare for, supply and apply a water based class 0 coating system eggshell finish, including compatibility tested for adhesion and paint film thickness build up. Ceilings and Soffits as M60:170A Eggshell Finish, walls as M60:170A Antigraffiti system. Note remove all existing flaking and defective coatings and thoroughly prepare walls and soffits, test dry film thickness of remaining surfaces. Allow to decorate only one stair at a time, and top floor main stair flights to be left in use at end of each work period to maintain access for residents. |  | Item |  | inc
5.16.30 | To include all services riser casings on stairs on completion of repairs and fire stopping taken elsewhere. |  | Item |  | inc
5.17 | R 11 ABOVE GROUND DRAINAGE
Test and Report
5.17.1 | Upon completion of scaffolding test and report on condition of entire surface water drainage system including gutters, hoppers and RWP and SVP downpipes. Agree with Employer extent of repairs and renewals. |  |  |  | 273
General Overhaul – Bin Store gutters
5.17.2 | Thoroughly clean out and overhaul all gutters to bin store, remake joints and adjust falls. Test on completion and leave ready for decoration. |  |  |  | 190
Rainwater pipes – general overhaul
5.17.3 | Thoroughly overhaul rainwater downpipes, refixing clips, remaking joints as required to leave in sound watertight condition ready for decorations. |  |  |  | 507
Repairs and Renewals
Allow to remove and replace the following provisional quantities of surface water drainage;
1. Gutters
5.17.4 | 110mm nominal cast iron half round, allow 5 linear metres complete with brackets, stop ends, outlets and al other accessories. | 5 | m |  | 281.25
2. Downpipes SVP/RWP
5.17.5 | Cast Iron, 110mm nominal diameter SVP/RWP to match existing – 5 Linear metres. Provisional Quantity | 5 | m |  | 309.375
Hoppers - Elevations 3 and 11.
5.17.6 | Carefully dismantle existing hoppers, these are ornate and need to be retained. Engage specialist to shot blast without damaging the base design. Completely refurbish, repairing all holes and corrosion, prepare and decorate and refix, connecting to new or existing downpipes. Provide temporary plastic hoppers whilst permanent are being repaired. | 4 | No |  | 590
Flat 202 (Vicinity)
5.17.7 | Carefully dismantle timber pipe casing to assumed rainwater outlet. Allow provisionally to dismantle assumed Timesaver type rainwater outlet and pipe to soffit from parapet gutter above. Renew complete to match existing and connect to downpipe. Reinstate pipe casing and leave ready for decorations. | 1 | Item |  | 750
Flat 203 (Vicinity)
5.17.8 | Carefully dismantle timber pipe casing to assumed rainwater outlet and replace as above item. | 1 | Item |  | 275
5.18 | MISCELLANEOUS REPAIRS
Tarmac Areas - street elevation 3
5.18.1 | Carefully take up entire area of tarmac to street elevation to three areas, outside entrance to 18/182, area outside 183, and larger area outside 184 - 186. Excavate and reduce levels, back fill all sunken areas with MOT material well compacted. Supply and lay 150mm MOT type material, and 50mm tarmac base course, and 20mm tarmac wearing course, laid to falls and cross falls to exiting gullies. All tarmac work to be to BS EN 13108 and BS 594987. Take up and re-set all inspection chamber covers. Approx. areas; 181 - 182 - 18 sqm. approx. 183 - 15.5 sqm approx. 184 - 186 - 96 sqm approx. | 129.5 | m² |  | 4917
5.19 | P12 FIRE STOPPING
Stairwell
5.19.1 | Carefully dismantle ply pipe/cable service risers on every stair and set aside for reuse. Sizes vary 100 x 615 splayed ground storey 180 x 530 first to second 180 x 430 second to third 170 x 320 third to fourth | 4 | No |  | 7184
5.19.2 | Engage third party accredited passive fire protection specialists for all services. To be members of the BRE/LPCB passive fire protection installer Scheme LPS 1531. |  |  |  | inc
5.19.3 | Seal around all pipes, cables and other services where they penetrate stair landing slabs and soffits with proprietary rapid setting, Gypsum based mortar material, zero shrinkage, 1 hours minimum fire resistance to EN1366-3 up to EI120, including BS476 Pt 20 and BS6399-1 Loading for Buildings “Code of Practice for dead and applied loads”. Include for temporary formwork, ensure removed on completion. All fire stopping to be photographed and certified on completion and full records provided with As Built information. | 4 | No |  | inc
5.19.4 | Reinstate all ply casings removed with new brass cups and screws, leave ready for decorations. | 4 | No |  | inc
5.2 | U90 MECHANICAL VENTILATION
Survey
5.20.1 | The contractor shall survey every flat and identify existing extractor fan types and locations and test and report on same prior to window manufacture for the flat concerned. Agree with CA locations for replacement fans. |  |  |  | 78
5.20.2 | Survey leaseholders and identify if they wish to take up option of fan installation/replacement and report to Employer. Note Tenants will have fans installed under this contract if none provided already in satisfactory condition. |  |  |  | 78
Allow Provisional Quantities to design and install fans as above and following items;
5.20.3 | Kitchen Fans – 10 No | 10 | No |  | 1341
5.20.4 | Bathroom Fans – 10 No | 10 | No |  | 1183
5.20.5 | Separate WC – 5 No | 5 | No |  | 592
Design and Install Fans
5.20.6 | To kitchens, bathrooms and WCs to all flats, survey, design, provide and fix the following, allowing for triple pole isolators to each unit. Allow for all wiring necessary. |  |  |  | 456
| Kitchens - Though wall humidity controlled extract with a minimum intermittent extract rate of 60 l/s. |  |  |  | inc
| Bathrooms - Through wall ducts humidity controlled fans with a minimum intermittent extract rate of 15 l/s. |  |  |  | inc
| Separate WCs - Through wall ducts humidity controlled fans with a minimum intermittent extract rate of 6 l/s. |  |  |  | inc
5.20.7 | Allow for through wall ducting for fans to internal courtyard elevations. Fans not to be window mounted. Include proposals within design submission. |  |  |  | 3162
5.20.8 | Provide NICEIC test certificate on completion for each flat. |  |  |  | 405
Window Fans
5.20.9 | Indicate alternative all in cost per fan for installation through windows, including purpose made sealed unit. Do not carry cost to pricing column for this item. £……………. saving/addition (delete as appropriate).
5.21 | V90 - COMMUNAL ACCESS BALCONY AND STAIRCASE LIGHTING ENHANCEMENT
| Complete design, supply and installation of communal and emergency lighting and controls as set out in Section 2 V90 and Fitzgerald or equivalent Scope of Work document appended thereto and Relux light calculations/simulations. Fitzgerald contact James Baldwin 07815 851996. Ref 46577. All conduit to be galvanised steel reusing existing where possible, adapting to suit. |  |  |  | 37337
5.22 | BUILDER'S WORK IN CONNECTION WITH SERVICES
Generally
5.22.1 | The contractor shall include for all builders work including, but not limited to: |  |  |  | inc
5.22.2 | Cutting holes and chases for Mechanical and Electrical services and making good ready for decorations. Including but not limited to electrical supply rerouting, communal area lighting, public health engineering/rainwater goods, mechanical fan and ductwork installations, etc. |  |  |  | inc
5.22.3 | Fire stopping where all services penetrate walls, ceilings and any other compartment fire stop around with suitable intumescent boarding, mortar, sealant etc. as appropriate to the service and structure being penetrated. |  |  |  | inc
See also as specification items P12.
Elevations 3 and 11 - Cables
5.22.4 | Tidy up and refix all cables loosely fixed to the elevations. Remove any redundant cables and make good. |  |  |  | 427
5.23 | PROVISIONAL SUMS
Provisional Sums
5.23.1 | Refer to preliminaries A54 for provisional sums, to be expended in part or whole only as directed by Employer. Ensure all carried forward to tender total.

## Section 5 Collection
Section 5 | £
Page 1
Page 2
Page 3
Page 4
Page 5
Page 6
Page 7
Page 8
Page 9
Page 10
Page 11
Page 12
Page 13
Page 14
Page 15
Page 16
Page 17
Page 18
Page 19
Page 20
Page 21
Page 22
Page 23
Page 24
Page 25
Page 26
Page 27
Page 28
Page 29
Page 30
Page 31
Page 32
Page 33
Page 34
Page 35
Page 36
Page 37
Page 38
Page 39
Page 40
Page 41
Page 42
Page 43
Page 44
Page 45
Page 46
Total to main Summary | 914279.5391
Total 35

## Section 6 Sch of Works
Ref | Item (Works) | Q | Unit | Rate | £ | p
BLOCK 204 - 238
6.01 | SURVEY C10/ SCHEDULING / EXEMPLARS / TRIALS – ALL SECTIONS OF WORK
Survey for new components
6.01.1 | The Contractor is to carry out a full survey of all the works to all elements of construction as required for the design and installation of the new works. Ensure that each area and building element is treated on a bespoke basis as one size fits all is not acceptable. |  |  |  | 338
Control Samples / Exemplars
6.01.2 | The Contractor is to carry out control samples of various items of works to agree standard with the CA prior to commencing the remainder of the project. These works are set out in the various sections that follow where applicable, e.g. pilot window installation, render etc. Allow for all necessary cost incurred in out of sequence procurement and working in this regard.
All trials to be undertaken at appropriate time ahead of the programme and may be part of the completed works provided standards are achieved.
Allow for all temporary access and protection in connection with the trials/samples.
Hoardings
6.01.3 | The contractor shall erect secure hoardings, Class O rated and dust proof, at the entrance to the designated site area. Maintain and adapt as required for the duration, remove on completion and make good all surfaces. |  |  |  | 1080
6.01.4 | Access is to be maintained at all times to adjoining Somers Town Coffee House public house, shops, and estate external areas. Under no circumstances shall works interrupt the function of any mains supplies without written notification min 21 days in advance and agreement of methodology with the Council.
6.01.5 | Roofing - Carry out a full photographic internal schedule of condition of all internal areas under roofs and parapet gutters recording condition of finishes and decorations and agree with resident. Notify CA of any significant defects before proceeding. Provide full annotated USB copy to the CA for each flat. |  | Item |  | 234
Windows and Doors
6.01.6 | Before removal of any window or door prepare a schedule of condition of each and every window and door opening, recording condition of finishes and decorations and agree with resident. Include for a photograph of every window and door. Notify CA of any significant defects before proceeding. Provide full annotated USB copy to the CA. |  |  |  | 1137
6.02 | C20 Demolitions and Spot Items - Refer to Section 2
Asbestos Survey
6.02.1 | A number of pre refurbishment surveys have been carried out to date and are available with the Pre-Construction Information, Council and CA. Some areas were inaccessible (roof externally, and voids, windows and doors at upper levels not accessible from access balconies) and require scaffolding. On completion and handover of scaffolding engage an accredited asbestos survey company to complete a Pre Refurbishment survey of the external areas not previously accessible and provide a copy of the report to the CA and Employer in PDF format. For your information the company that carried out a number of the existing surveys to date is O C Consulting (UK) Ltd t/a Manestream INSPECTION BODY Tel: 01992 780300 enquiries@manestream.co.uk.
Asbestos Removal
6.02.2 | Refer to prelims A54 for Provisional Sum. |  |  |  | 2532
6.03 | C40 CLEANING MASONRY/CONCRETE
Brickwork Access Balcony Elevations 4, 5 including concealed internal Court flat elevations (see drawing L-(0)002.
6.03.1 | Allow to clean all facing brickwork with DOFF, or equal approved system at all access balcony and ground storey levels, entire elevations and inside face of access balcony/communal walkway parapet walls. |  |  |  | 7443
6.03.2 | Allow pilot sample area of 2m2 each to yellow stock and red brickwork to be trialled and agreed with Council and conservation officer prior to full application described above. | 4 | m² |  | 394
6.03.3 | Remove and refix all signs in conjunction with these works to allow cleaning behind. |  |  |  | inc
6.03.4 | Provide all necessary attendances on specialist cleaner and safe temporary electrical supply system, NB may need 240 Volts. |  |  |  | inc
Ground Storey “Stonework” Courtyard Elevations 4, 5, part 8, and 10.
6.03.5 | Allow to steam clean external ground storey stone/exposed aggregate with DOFF, or equal approved system. Area to include courtyard facing ring beams etc. above ground storey access way up to and including first floor access balcony parapet wall. |  |  |  | 3046
6.03.6 | Allow pilot sample area of 2m2 to be trialled and agreed with Council representative and conservation officer prior to full application. See specification item C40:232. | 2 | m² |  | 394
6.03.7 | First Floor Flat 210 - Remove all paintwork to access balcony elevation brickwork from flat entrance door to lift lobby, back to face brick. | 9 | m² |  | 355
Quarry Tiled floors and Grano Stairs
6.03.8 | Deep clean quarry tiles floors to ground storey access stair lobbies (2No). Deep clean all stair flights and landings. Deep clean asphalt lift lobby at each level. |  |  |  | 560
6.04 | C41 REPAIRING/RENOVATING/CONSERVING MASONRY - Refer to Section 2
Ground Storey “Stonework” – Courtyard Elevations 4, part 8, and 10.
6.04.1 | Allow to take samples of original mortar to stonework/exposed aggregate bed joints in locations agreed with Council representative, min 2 No per elevation. Analyse samples through a competent testing house (e.g. Sandberg) and establish original mix. Provide written report to Council representative. |  | Item |  | 507
6.04.2 | Allow to rake out min depth 19mm and repoint all lose and defective and non-matching joints to stonework in assumed lime mortar, mix to be designed by contractor and agreed with CA subject to test results from item above. Allow Provisional Quantity 20 lin metres. | 20 | m |  | 338
Repointing Brickwork
Rake out to 19mm depth and repoint brickwork in random locations as below, to match original style and colour;
6.04.3 | No 210 First Floor - Cut out and make good hole in brickwork to match existing, located adjacent to boiler flue. |  | Item |  | 130
6.04.4 | First Floor balcony parapet - Make good redundant power or light point recess and conduit chase in wall to match existing adjacent surfaces. Approx. 100mm x 200mm. |  | Item |  | 74
6.04.5 | First Floor balcony parapet - - Rake out and repoint joints to blockwork on inside face of parapet wall prior to decorations. | 24 | m |  | 405.6
| Repoint panel prior to decorations, inside face. | 3.5 | m |  | 59.15
6.04.6 | Second Floor Flat 218 - Curved parapet wall to access balcony, - reset displaced coping stone and repoint brickwork locally. |  | Item |  | 107
6.04.7 | 3rd Floor near flat 227 at top of stairs - Rake out and repoint crack extending 7 courses below lintel bearing. |  | Item |  | 50.7
6.04.8 | 3rd Floor level - rake out and repoint top two courses of 2 No curved parapet walls near flat 227. | 7.5 | m |  | 126.75
6.04.9 | 3rd floor level parapet wall - remove fillet joint along top of asphalt upstand, rake out min 19mm and repoint. | 3.7 | m |  | 111
Brick Repairs –
6.04.12 | Survey all existing face brick work after cleaning and report all defects to Council representative. See F10 for repairs later. |  | Item |  | 282
6.05 | C42 REPAIRING/RENOVATING/CONSERVING CONCRETE - Refer to Section 2
Extent of Surfaces to be Repaired and re- coated
6.05.1 | The contractor is to carry out repairs and recoating to all existing external exposed concrete at all levels to all elevations of the block, including but not limited to;
6.05.2 | · Ring beams, communal access balconies soffits and edges, and all other concrete features.
6.05.3 | · Lower ground floor level exposed concrete including soffits to ground storey units.
6.05.4 | · Communal area staircases - 2No.
6.05.5 | · Exposed aggregate face “stonework” to lower stories.
Survey
6.05.6 | Undertake a detailed survey of all the concrete surfaces as described in C42 and present findings to the Council's representative by way of a written report, photographs, annotated drawings and approximate quantities of repairs required. |  | Item |  | 275
Preparation
6.05.7 | Allow to thoroughly REMOVE ALL existing concrete coatings to;
6.05.8 | • Access balcony ceilings/soffits and downstand beams/edges/soffits. |  | Item
6.05.9 | • Stairs soffits and landing ceilings including lift landings and lobbies. |  | Item
6.05.10 | Check condition of all other coatings and remove locally any lose material to a smooth edge. |  | Item
6.05.11 | Prepare all existing concrete surfaces ready to receive repairs and new coatings, as C42. In the event existing coatings are found to be sound and well adhered, proven by adhesion and pull off tests, existing coatings may remain subject to formal instruction from the Council's representative to this effect. Coating removals to be designed to extract dust and arisings at source, and to include for all temporary protection and sealing of windows, vents, doors and any other apertures that may permit dust penetration into the building. |  | Item
Concrete Repairs – PROVISIONAL QUANTITIES – TO BE REMEASURED
6.05.12 | Break out defective concrete, prepare and prime steel exposed, make good reinforcement bars and bases of staircase balustrades as described in C42, and carry out concrete repairs as C42 to all concrete surfaces allowing the following provisional quantities;
WALL OR COLUMN FACES
Repair as described in C42: items 105 – 165A
6.05.13 | Depth not exceeding 25mm
A | area not exceeding 0.01m² | 10 | No |  | 55
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 88
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 137.5
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 258.5
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 478.5
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 682
G | area exceeding 1.00m² | 2 | m² |  | 171.6
6.05.14 | Depth exceeding 25mm but not exceeding 50mm |  |  |  | 0
A | area not exceeding 0.01m² | 10 | No |  | 88
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 176
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 264
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 561
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 924
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1210
G | area exceeding 1.00m² | 2 | m² |  | 332.2
6.05.15 | Depth exceeding 50mm but not exceeding 75mm |  |  |  | 0
A | area not exceeding 0.01m² | 10 | No |  | 110
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 313.5
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 528
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 924
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 1518
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1674.2
G | area exceeding 1.00m² | 1 | m² |  | 213.4
SIDES & SOFFITS OF BEAMS & LINTELS
6.05.16 | Depth not exceeding 25mm - Side & soffit
A | area not exceeding 0.01m² | 10 | No |  | 55
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 88
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 137.5
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 258.5
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 478.5
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 682
G | area exceeding 1.00m² | 2 | m² |  | 171.6
6.05.17 | Depth exceeding 25mm but not exceeding 50mm - Side & soffit
A | area not exceeding 0.01m² | 10 | No |  | 88
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 176
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 264
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 561
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 924
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1210
G | area exceeding 1.00m² | 2 | m² |  | 332.2
6.05.18 | Depth exceeding 50mm but not exceeding 75mm - Side & soffit
A | area not exceeding 0.01m² | 10 | No |  | 110
B | area exceeding 0.01m² but not 0.05m² | 10 | No |  | 313.5
C | area exceeding 0.05m² but not 0.10m² | 10 | No |  | 528
D | area exceeding 0.10m² but not 0.25m² | 10 | No |  | 924
E | area exceeding 0.25m² but not 0.50m² | 10 | No |  | 1518
F | area exceeding 0.50m² but not 1.00m² | 10 | No |  | 1674.2
G | area exceeding 1.00m² | 1 | m² |  | 213.4
SINGLE ARRIS OF WALLS AND COLUMNS
6.05.19 | Depth not exceeding 25mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 79.75
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 143
C | length exceeding 600mm | 2 | m |  | 96.8
6.05.20 | Depth not exceeding 25mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 136.345
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 263.175
C | length exceeding 600mm | 2 | m |  | 164.384
Depth not exceeding 25mm
6.05.21 | Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 263.175
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 410.96
C | length exceeding 600mm | 1 | m |  | 112.519
6.05.22 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 176
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 280.5
C | length exceeding 600mm | 1 | m |  | 79.2
6.05.23 | Depth exceeding 25mm but not exceeding 50mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 317.46
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 515.35
C | length exceeding 600mm | 1 | m |  | 145.728
6.05.24 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 515.35
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 728.64
C | length exceeding 600mm | 1 | m |  | 192.049
6.05.25 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 317.515
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 452.76
C | length exceeding 600mm | 1 | m |  | 147.972
6.05.26 | Depth exceeding 50mm but not exceeding 75mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 452.76
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 739.86
C | length exceeding 600mm | 1 | m |  | 211.024
6.05.27 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 739.86
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1055.12
C | length exceeding 600mm | 1 | m |  | 246.092
SINGLE ARRIS OF BEAMS AND LINTELS
6.05.28 | Depth not exceeding 25mm
Girth 0 -150mm
A | length not exceeding 300mm | 10 | No |  | 187
B | length exceeding 300mm but not exceeding 600mm | 10 | No |  | 330
C | length exceeding 600mm | 1 | m |  | 53.35
6.05.29 | Depth not exceeding 25mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 159.17
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 295.845
C | length exceeding 600mm | 1 | m |  | 94.281
6.05.30 | Depth not exceeding 25mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 295.845
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 471.405
C | length exceeding 600mm | 1 | m |  | 127.446
6.05.31 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 214.5
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 341
C | length exceeding 600mm | 1 | m |  | 94.6
6.05.32 | Depth exceeding 25mm but not exceeding 50mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 372.02
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 602.69
C | length exceeding 600mm | 1 | m |  | 162.415
6.05.33 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 602.69
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 812.075
C | length exceeding 600mm | 1 | m |  | 219.692
6.05.34 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 -150mm
A | length not exceeding 300mm | 5 | No |  | 372.02
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 525.47
C | length exceeding 600mm | 1 | m |  | 169.059
6.05.35 | Depth exceeding 50mm but not exceeding 75mm
Girth 150mm - 300mm
A | length not exceeding 300mm | 5 | No |  | 525.47
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 845.295
C | length exceeding 600mm | 1 | m |  | 242.385
6.05.36 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 845.295
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1211.925
C | length exceeding 600mm | 1 | m |  | 279.609
TWO ARRIS REPAIR OF BEAMS AND LINTELS
6.05.37 | Depth not exceeding 25mm
Girth 0 -300mm
A | length not exceeding 300mm | 5 | No |  | 131.45
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 195.25
C | length exceeding 600mm | 1 | m |  | 73.073
6.05.38 | Depth not exceeding 25mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 195.25
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 365.365
C | length exceeding 600mm | 1 | m |  | 150.601
6.05.39 | Depth not exceeding 25mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 365.365
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 558.36
C | length exceeding 600mm | 1 | m |  | 150.601
6.05.40 | Depth exceeding 25mm but not exceeding 50mm
Girth 0 - 300mm
A | length not exceeding 300mm | 5 | No |  | 224.675
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 449.35
C | length exceeding 600mm | 1 | m |  | 146.157
6.05.41 | Depth exceeding 25mm but not exceeding 50mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 449.35
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 730.785
C | length exceeding 600mm | 1 | m |  | 197.285
6.05.42 | Depth exceeding 25mm but not exceeding 50mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 730.785
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 986.425
C | length exceeding 600mm | 1 | m |  | 262.713
6.05.43 | Depth exceeding 50mm but not exceeding 75mm
Girth 0 - 300mm
A | length not exceeding 300mm | 5 | No |  | 454.96
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 636.625
C | length exceeding 600mm | 1 | m |  | 198.484
6.05.44 | Depth exceeding 50mm but not exceeding 75mm
Girth 300mm - 600mm
A | length not exceeding 300mm | 5 | No |  | 636.625
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 992.42
C | length exceeding 600mm | 1 | m |  | 277.574
6.05.45 | Depth exceeding 50mm but not exceeding 75mm
Girth 600mm - 900mm
A | length not exceeding 300mm | 5 | No |  | 992.42
B | length exceeding 300mm but not exceeding 600mm | 5 | No |  | 1387.87
C | length exceeding 600mm | 1 | m |  | 325.6
CRACK REPAIRS IN SURFACES OF WALLS, COLUMNS, ETC.
Repair cracks C42:items 105 – 165A
6.05.46 | After preparation width not exceeding 5mm, depth not exceeding 10mm
A | crack length 0 to 150mm | 10 | No |  | 44
B | crack length 150mm to 300mm | 20 | No |  | 121
C | crack length 300mm to 450mm | 20 | No |  | 145.2
D | crack length 450mm to 600mm | 10 | No |  | 101.2
E | crack length 600 to 750mm | 10 | No |  | 126.5
F | crack length exceeding 0.75m | 2 | m |  | 33.22
6.05.47 | After preparation width 10mm, depth not exceeding 20mm
A | crack length 0 to 150mm | 10 | No |  | 74.8
B | crack length 150mm to 300mm | 20 | No |  | 202.4
C | crack length 300mm to 450mm | 20 | No |  | 246.4
D | crack length 450mm to 600mm | 10 | No |  | 165
E | crack length 600 to 750mm | 10 | No |  | 198
F | crack length exceeding 0.75m | 2 | m |  | 54.12
6.05.48 | After preparation width 15mm, depth not exceeding 30mm
A | crack length 0 to 150mm | 10 | No |  | 121
B | crack length 150mm to 300mm | 20 | No |  | 330
C | crack length 300mm to 450mm | 20 | No |  | 396
D | crack length 450mm to 600mm | 10 | No |  | 269.5
E | crack length 600 to 750mm | 10 | No |  | 365.2
F | crack length exceeding 0.75m | 2 | m |  | 94.6
Large Repairs - Balcony Beams – Straight Sections, render finish
6.05.49 | Cut away concrete to expose balcony edge steel beam as indicated on sketch drawing 5675-A(2)002. Install suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 20 No beams approx. 3.35m clear span between columns/walls | 20 | No |  | 31570
6.05.50 | Cut away concrete to expose balcony edge steel beam as indicated on sketch drawing 5675-A(2)002. Install suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 2 No beams approx. 3.5m clear span between columns/walls. Elevation 4. | 2 | No |  | 3157
Large Repairs – Balcony Beams - Straight section, exposed aggregate finish.
6.05.51 | Carry out works as above item but to ground storey balcony beam with exposed aggregate finish.
| Allow Provisionally – 3 No beams n/e 3.35 metres long. | 3 | No |  | 5469.321
Large Repairs - Balcony Beams – Curved Sections to communal access balconies, render finish.
6.05.52 | Cut away concrete to expose curved balcony edge beam (assumed steel angle). Provide suitable reinforcement armature and fix to existing steels and concrete as described for above items. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 4 No radius beams @ approx. 3.7 linear metres each. | 4 | No |  | 8054.332
6.05.53 | Curved radius beam as above item, Youth Centre end, 2.1 linear metres. Allow 1 No. | 1 | No |  | 1137.235
Large Repairs - Stairwell lintels – Straight Sections, render finish
6.05.54 | Cut away concrete to expose assumed steel beam as indicated on sketch drawing 5675-A(2)002. Provide suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 2 No lintels approx. 1650mm clear span between columns/walls | 2 | No |  | 1795.904
6.05.55 | Cut away concrete to expose assumed steel beam as indicated on sketch drawing 5675-A(2)002. Provide suitable reinforcement armature and fix to existing steels and concrete. Carry out concrete repairs to reinstate to original profile.
| Allow Provisionally 7 No beams approx. 1.7 m clear span between columns/walls | 7 | No |  | 6476.085
6.05.56 | Not used
LEVELLING MORTAR/FAIRING COAT
6.05.57 | Supply and apply a single component polymer modified cementitious fairing coat/overall levelling coat to ALL concrete surfaces, repaired and sound, on completion of repairs as C42:166A prior to application of anti-carbonation coatings. Include;
| - Communal access balcony beams and lintels, soffits and edges – do not extend over any movement joints |  | Item |  | 1775.4
| - Communal access balcony soffits/ceilings. |  | Item |  | 4438.5
| - Stairs and landings soffits. |  | Item |  | 3329.04
COATINGS
6.05.58 | Prepare, prime and apply anti-carbonation decorative coatings to all concrete surfaces as C42, repaired and existing, comprising silane-siloxane primer and acrylic co-polymer pigmented top coat as C42:167A onwards. Colours to be confirmed with Employer. |  | Item |  | 5728.8
| NB Stairs and communal balcony soffits to be Class O standard. |  | Item |  | Noted
EXPOSED AGGREGATE REPAIRS - GROUND STOREY
WALL OR COLUMN FACES
6.05.59 | Repair as described in C42:105 – 165A
Depth not exceeding 25mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 16.06
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 27.5
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 33.462
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 68.464
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 107.03
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 135.3
G | area exceeding 1.00m² | 1 | m² |  | 86.9
6.05.60 | Depth exceeding 25mm but not exceeding 50mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 18.59
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 43.12
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 66
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 94.6
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 139.48
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 174.9
G | area exceeding 1.00m² | 1 | m² |  | 109.78
6.05.61 | Depth exceeding 50mm but not exceeding 75mm EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 33.88
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 48.84
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 77.88
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 114.4
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 169.62
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 215.6
G | area exceeding 1.00m² | 1 | m² |  | 133.1
SIDES & SOFFITS OF EXPOSED AGGREGATE FINISH BEAMS & LINTELS
6.05.62 | Depth not exceeding 25mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 16.06
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 27.5
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 33.462
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 68.464
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 107.03
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 135.3
G | area exceeding 1.00m² | 1 | m² |  | 86.9
6.05.63 | Depth exceeding 25mm but not exceeding 50mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 18.59
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 43.12
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 66
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 94.6
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 139.48
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 174.9
G | area exceeding 1.00m² | 1 | m² |  | 109.78
6.05.64 | Depth exceeding 50mm but not exceeding 75mm - Side & soffit EXPOSED AGGREGATE
A | area not exceeding 0.01m² | 2 | No |  | 33.88
B | area exceeding 0.01m² but not 0.05m² | 2 | No |  | 48.84
C | area exceeding 0.05m² but not 0.10m² | 2 | No |  | 77.88
D | area exceeding 0.10m² but not 0.25m² | 2 | No |  | 114.4
E | area exceeding 0.25m² but not 0.50m² | 2 | No |  | 169.62
F | area exceeding 0.50m² but not 1.00m² | 2 | No |  | 215.6
G | area exceeding 1.00m² | 1 | m² |  | 133.1
STAIR REPAIRS
Repair as described in C42:105 – 165A, but with granolithic finish to match existing
Main Stairs
6.05.65 | Ground Storey - second tread - repair corner, approx. 100mm x 120mm x 100mm. Reform nosing. | 1 | No |  | 103.554
6.05.66 | Ground Storey - first tread down from half landing - repair corner, approx. 100mm x 120mm x 100mm. Reform nosing. | 1 | No |  | 103.554
6.05.67 | Ground Storey - first tread up from half landing - repair corner, approx. 100mm x 120mm x 100mm. Reform nosing. | 1 | No |  | 103.554
6.05.68 | First Floor level - Tread and nosing repairs as above item on flight up from half landing. 3No. | 3 | No |  | 310.662
6.05.69 | First floor half landing - cut out and make good crack at abutment of half landing with riser. | 1 | No |  | 103.554
6.05.70 | Half Landing level second floor - full width riser repair as above items. | 1 | No |  | 103.554
6.05.71 | First Floor level - Tread and nosing repairs as above item on flight up from half landing. | 1 | No |  | 103.554
6.05.72 | Half Landing level second floor to third floor - full width riser repair as above items. | 1 | No |  | 103.554
6.05.73 | Second floor to third floor - Tread and nosing repairs as above items on flight up from half landing. | 1 | No |  | 103.554
6.05.74 | Third floor - full width riser repair as above items, riser to half landing. 2No. | 2 | No |  | 207.108
6.05.75 | Third floor - half landing up to third floor - full width riser repair as above items, riser to half landing. | 1 | No |  | 103.554
6.05.76 | Flight to third floor - Repair tread approx. 250 x 100 x 100mm including nosing. 2 No first and fourth treads. | 2 | No |  | 207.108
6.05.77 | Top landing level - cut out 2 No cracks and repair to top riser. | 2 | No |  | 207.108
6.05.78 | Third floor level - cut out crack to first tread corner by brickwork and repair as described. | 1 | No |  | 103.554
6.05.79 | Third floor to fourth floor - Tread and nosing repair as above items on flight up from half landing. | 1 | No |  | 103.554
6.05.80 | Top tread - cut out and repair horizontal crack. | 1 | No |  | 103.554
6.05.81 | Fourth Floor - Repair tread approx. 250 x 100 x 100mm including nosing, first tread.
6.05.82 | Fourth Floor - cut out and repair crack full width to half landing nosing. | 1 | No |  | 103.554
6.06 | F10 AND F30/F31 BRICK WALLING AND COPINGS - Refer to Section 2 Specification
Brick Repairs following Render Removal – Walls and Chimnies
6.06.1 | On completion of render removal (taken later in M20) survey all walls and chimnies and provide a quantified report and marked up drawing to the Employer for instructions on repairs and renewals required. |  |  |  | 282
6.06.2 | Allow for brickwork patch repair, stitching, replacement and repointing to damaged masonry following removal of render.
| Allow Provisionally 20 sq. metres in small patches n/e 0.5 sq.m. | 20 | m² |  | 4739
Main Roof Parapet Copings
6.06.3 | Remove existing coping stones to entire length of all parapet walls, to entire main roof as indicated on roof plan and clear away from site. |  |  |  | 21660.4025
6.06.4 | Supply and install new once weathered top, twice throated coping stones, with suitable expansion joints and neatly pointed and jointed in position. Note coping projections are to suit the new thicker parapet wall design, ply cladding and weatherproofing to achieve clear projection and clear drip throatings on both faces. Refer to drawing No 5675-A(2)001. |  |  |  | 447.7812
6.06.5 | Expansion joints in copings - to be provided within 1.5 metres of all internal and external corners and generally at not exceeding 12 metres. Joints min 12mm wide, primed and sealed with silicone sealant on polyethylene backing rods. |  |  |  | 312.5
Miscellaneous Brickwork alterations and spot items
6.06.6 | Provisional Quantity - Allow to cut out and stitch in replacement yellow stock bricks to access balcony elevation or parapet, to match existing, fully bedded and pointed in mortar to match original. Allow 25 No individual bricks provisional quantity. | 25 | No |  | 312.5
6.07 | H65 SINGLE LAP ROOF TILING - Refer to Section 2 Specification
Strip Existing roofs 204 - 238 Levita House EXCLUDING New Horizon Centre low rise blocks.
Elevations - 4, part 5, part 6, part 7, part 8, and 10
6.07.1 | Carefully strip up entire tiled roof covering including flashings and accessories. Clear away all redundant tiling complete, along with all battens, accessories and any underlay. |  |  |  | 98823.161
6.07.2 | Allow review of existing "eaves"/parapet detail, ridge and hip details and suitability for new tiling before proceeding.
Additional first fix carpentry - PROVISIONAL
6.07.3 | Tilting fillet - Remove rotten tilting fillet, supply and install new to match existing, assume 125mm wide x 25mm thick. Allow Provisional quantity 128 linear metres. | 155 | m |  | 1264
6.07.4 | Close Boarding - Remove & renew rotten & damaged roof close boarding (100mm) in various locations - total 200 linear metres, Provisional Quantity | 200 | m |  | 2151
6.07.5 | Ridges and Hips - build up ridge board or hip rafter height, allow 50 x 125mm tanalised timber fixed to existing, Provisional quantity 90 linear metres. | 142 | m |  | 1310
Tiling
6.07.6 | Upon completion of insulation works (taken elsewhere) retile the slopes using vapour permeable breathable sarking underlay laid horizontally over boarding as H65. Re-tile using new 38 x 12mm counter battens and 50 x 25mm tile battens and with, ensuring underside of tiles are ventilated as per manufacturer’s written recommendations. |  |  |  | inc
| Tiles to be Sandtoft BRIDGEWATER fixed entirely in accordance with manufacturer’s written recommendations and H65. |  |  |  | Noted
| Colour - SOMERSET |  |  |  | Noted
Detailing
6.07.7 | Ridge, hips, verges to Sandtoft/Wienerberger specification – Note allow for new matching half round mechanically fixed ridges and hips. Complete the design of and supply and fit all flashings and other weathering details. All flashings and weatherings to be in lead as Specification section H71 to meet listed building requirements to minimum Code and details as Lead Sheet Association. |  |  |  | inc
To include but not limited to;
· abutments;
· flashings;
· Valleys;
· secret gutters to dormers and gables;
· Chimney aprons, side flashings and back gutters;
· Dormer flat roof abutments
· pipe, fan and flue penetrations;
· Verges;
· Junctions and saddles;
and all other details as required to complete the installation.
Soil Vent Pipes
6.07.8 | Support all soil vent pipes and other pipe penetrations, removing and refixing as necessary. Provide Code 4 lead slates and weatherings, dressed under tiling on upper side min 100mm and dressed over and to tiles mon 150mm apron, and 150mm each side of pipe/penetration. |  |  |  | inc
Fan Terminals
6.07.9 | Replace all extract fan terminals currently discharging through the roof with new colour matched to tiles, to achieve minimum free air flow as existing. |  |  |  | 816
Fire Breaks
6.07.10 | Supply and install fire breaks over all party walls and communal areas. Fill the space over the wall with layers of mineral fibre quilt so that when the underlay and battens are laid it is lightly compressed. Tuck the edges of quilt between edges of wall and adjoining rafters. Lay 300 mm wide pads of mineral fibre quilt thick enough to seal all gaps and cut to fit snugly between the tile battens. At boxed eaves, completely seal all air paths with compressed mineral fibre quilt to completely fill void on line of party walls. |  |  |  | 912
Roof Insulation - Sloping ceilings/flats with dormers
6.07.11 | Refer to drawing 5675 – A(2)003 and 005. Carefully remove section of sarking boarding without disturbing internal finishes. Supply and install insulation system between rafters, in each rafter void, to "lap" parapet gutter insulation as detail drawings. Insulation to be as specified in Section 2 - P10 and as indicated on drawings. |  |  |  | 13844
6.07.12 | Reinstate sarking boarding with existing and make up quantity with matching new as required, to be screw fixed, not nailed, twice on each rafter |  |  |  | 7946
Remove existing insulation - sloping areas PROVISIONAL
6.07.13 | Allow Provisionally to remove assumed existing inadequate mineral wool and chicken wire insulation and clear from site. |  | Prov Item |  | 1958
Roof Insulation - Horizontal areas
6.07.14 | Allow Provisionally to remove assumed existing inadequate mineral wool and chicken wire insulation and clear from site. |  | Prov Item |  | 1654
6.07.15 | Supply and lay two layers 150mm mineral wool insulation as specification P10, 150mm laid between ceiling joist, 150mm laid over first layer at 90 degrees. Ensuring “eaves” ventilation to sloping parts is maintained. Sarking board removal taken with sloping insulation item |  | Item |  | 10148
6.07.16 | Roof Access Hatches - Allow provisionally to carefully cut out ceiling, trim joists and install proprietary loft access hatch, fully insulated and draft proofed, U Value 0.35, 30 mins fire resistance, Class O spread of flame Push-Up Loft Access Door Matt White 630 x 630mm approx. Make good ceiling and adjacent decorations disturbed, assuming two coats white emulsion to entire room or landing affected. | 7 | No |  | 1216
Strip Existing roofs New Horizon Centre low rise blocks - PROVISIONAL.
6.07.17 | Strip and retile both low rise hipped tiled roofs to New Horizon Youth Centre, Chalton Street, entirely as items 6.07.1 and 6.07. 6 to 6.07.12 inclusive. See roof plan drawing L(0)011 and elevations. |  | Prov Item |  | 23234.188
6.07.18 | Allow for replacement tilt fillet to New Horizon as 6.07.3, allow Provisional Quantity 32 lin metres. | 32 | m |  | 316
6.07.19 | Allow for ridge board build up to New Horizon as 6.07.5, allow Provisional Quantity 32 lin metres. | 32 | m |  | 465.78
Roof Insulation - New Horizon Centre low rise blocks - PROVISIONAL.
6.07.20 | Insulation - Insulate both roofs to New Horizon ow rise blocks as described for main block items 6.07.11 - 15 inclusive. |  | Prov Item |  | 8243
6.08 | H71 LEAD SHEET COVERINGS/FLASHINGS - Refer to Section 2 Specification (Insulation as specification section P10)
Dormers
6.08.1 | Carefully remove and cart away for recycling all dormer window cladding and roof coverings. | 28 | No |  | 912
Dormer Cheeks - insulation
6.08.2 | Carefully remove timber boarding to cheeks and supply and install insulation system between studs to be non combustible mineral wool and vapour permeable breather membrane on outer side. Leave 25mm air gap with insect screen, and reinstate new 12mm WBP ply boarding ready for cladding, making up quantity as necessary. Provide full details of selected materials for comment prior to proceeding. Refer to drawings 5675 – A (2) 003 and 004. 28 No dormers this block. | 28 | No |  | 45668
Dormer Roofs - insulation
6.08.3 | Supply and install insulation system to all dormer roofs carefully removing and replacing timber decking as required, assumed 100mm rigid mineral wool vapour permeable system. Provide 50mm ventilation gap as detailed and 18mm WBP ply deck to falls and cross falls. Provide full details for comment prior to proceeding. Leave ready for cladding. Refer to drawings 5675 – A (2) 003 and 004. | 28 | No |  | inc
Dormer Cladding and Roofing
6.08.4 | Supply and install Code 5 lead cladding and roofing to dormers ensuring all lead work to Lead Sheet Association recommendations, thickness Codes etc. Form all detailing, drips rolls, splash laps, clips, and joints similar to existing (note Listed Building) taking care to ensure falls are correct. Dormer roofs to fall to each side and not discharge over the windows to avoid dripping on widow cills. Include insect mesh as detailed. Form min 150mm effective vertical height sloping upstand and fillet to underside of tiled roof abutments at top of dormer including welted edge. See drawing No 5675-A(2)004. | 28 | No |  | inc
6.08.5 | Supply and fit new s.w. PAR fascias to dormers and leave ready for decorations. Ensure all surfaces including back of fascia primed and undercoated before installation. Assume 25mm x 150mm. | 28 | No |  | inc
New Horizon Youth Centre Dormers Provisional Items
6.08.6 | Insulate dormer cheeks to New Horizon dormers as item 6.08.1 & 2 above. Allow 5 No | 5 | No |  | 8155
6.08.7 | Insulate dormer roofs to New Horizon Youth Centre as item 6.08.3 above. Allow 5 No. | 5 | No |  | inc
6.08.8 | Clad New Horizon Youth Centre dormers as 6.08.4 above. 5 No. | 5 | No |  | inc
6.08.9 | Provide fascia to New Horizon dormers as 6.08.5 above. | 5 | No |  | inc
Main Roof - Chimney “dormers” infill – 2No. Chimnies, 21 and 26 as roof plan
6.08.10 | Carefully strip, re-roof and re-clad in lead 2No lead “dormer” infill structures located behind the main block chimnies, all as item 6.08.4 above. Refer also to roof plan L (0)011 for locations. | 2 | No |  | 1500
6.09 | J21 COMMUNAL ACCESS BALCONIES AND ROOFS - ASPHALT REPAIRS
Carry out asphalt repairs to communal access balconies using hot poultice method as J21 as follows;
6.09.1 | Rainwater pipe between flats 219 and 220 - Cut out asphalt by hot poultice method and expose gully and RWP. Reform two coat asphalt work, dress into gully, re seat grating. Make good asphalt fillet/upstand including internal and external angles. | 1 | m² |  | 43.32
6.09.2 | Second Floor top of stairs - cut out and renew n/e 2 sqm damaged asphalt at top of stairs. | 2 | m² |  | 86.63
Dry Riser Roof - Ground Storey Elevation 4
6.09.3 | Remove remaining lead covering to dry riser small flat roof elevation 4 and clear away. Supply and lay two coat asphalt roof covering compete with GRP drip trim and 150mm upstand at abutment with main building. Apply two coats solar reflective paint on completion. |  | Item |  | 928.13
6.09.4 | Gully grating - replace missing gully grating adjacent to flat 205. | 1 | Item |  | 22.5
6.09.5 | Gully grating - replace damaged gully grating adjacent to flat 206/7. | 1 | Item |  | 22.5
6.1 | J31 PARAPET GUTTER AND ASSOCIATED FLAT ROOFS - LIQUID APPLIED WATERPROOFING - Refer Section 2 Specification
Introduction
6.10.1 | The refurbishment of the internal parapet gutters is to be carried out in conjunction with the replacement of the main pitched tiled roofs. Works will need to be designed and programmed to ensure that the installation works co-ordinate satisfactorily and any finished areas of gutters are protected from other trades. |  |  |  | Noted
| NB in addition to the gutters the wider gutter extensions/roofs areas are to be treated similarly , on this block (2 No locations near chimnies 20 and 27. See roof plan. |  |  |  | Noted
6.10.2 | The gutter lining system shall not be a hot works solution, no hot works are permitted at roof level. Please refer to drawing 5675 – A (2) 001 for existing detail. For the contractor's information Block 1-21 incorporated the use of Moy Materials Ltd ENKOPUR system, Tel 07917 896307 or 012435 707449. |  |  |  | Noted
6.10.3 | Cores - In conjunction with the selected Liquid system supplier who will be guaranteeing the installation take cores samples through parapet gutter and roofs over sufficient areas to establish the existing roof/covering build up. |  | Item |  | 330
6.10.4 | Adhesion tests - carry out adhesion test of waterproofing to parapet gutters base and sides, and allow to cure for 1 week before proceeding. |  | Item |  | inc
Waterproofing and Insulation
6.10.5 | Supply and install complete cold poured polyester resin fleece reinforced waterproofing and thermal insulation lining system to the parapet gutters. Ensure insulation proposals link with pitched roof insulation. Selected solution is to be provided and installed to achieve a minimum 15 year BBA certified single point guarantee for labour, materials and workmanship and as such will need to be a proprietary system installed by a system approved specialist. |  |  |  | 39670.748
6.10.6 | Preparation - Power wash all surfaces. Remove existing localised repairs. Remove all moss, dirt and debris. Inspect and repair the existing surface. Blisters in the asphalt should be carefully warmed, pierced and smoothed down to a level surface to receive the overlay system. |  |  |  | inc
6.10.7 | Copings – see F10/31, and schedule of works section 6.06. |  |  |  | inc
6.10.8 | Parapet Walls - Make good any localised damage to existing parapet walls, as required, and board out the internal face of parapet with 12mm plywood (mechanically fixed), to allow the new waterproofing to be dressed up and over. Refer to drawing detail 5675-A(2)005 for change in wall thickness on inside face of parapet. |  |  |  | 22467
6.10.9 | Cut new chases in rendered abutments at increased height (staircase walls and chimney stacks), to receive new lead flashing (upstand 150mm min). |  |  |  | inc
6.10.10 | Supply and fit a lay-board to allow dressing of the new waterproofing below the pitched tiled roof as drawing No 5675-A(2)005. |  |  |  | inc
6.10.11 | Coordinate gutter lining with replacement lead cladding to dormers. Remove lead flashings and lead cheeks from dormer windows to allow access for waterproofing. Surfaces to receive waterproofing must be clean, smooth and dry. |  |  |  | inc
Priming
6.10.12 | Supply and apply suitable substrate Primer to existing asphalt. Carry out adhesion test and record results. Allow to dry. |  |  |  | 18193
Vapour Control Layer
6.10.13 | Supply and install suitable vapour control layer under insulation, self-adhesive. |  |  |  | inc
Insulation
6.10.14 | Supply and lay suitable insulation e.g. 140mm rigid Insulation (bonded in suitable Insulation Bonding Adhesive). U Value 0.18W/m²K (compliant with Building Regulations Part L 2010) as indicated on the drawing 5675-A(2)005. |  |  |  | inc
Insulation Priming and Preparation
6.10.15 | Prime upper face of insulation with Bonding Agent and allow to dry. Apply preparation Layer self-adhesive. |  |  |  | inc
Waterproofing - gutters, roofs and details
6.10.16 | Supply and lay cold pour resin waterproofing including primer to detailing, finish colour Dark Grey, all to coverage rates specified by manufacturer to achieve guarantee. Ensure bridging tape used at junction of dissimilar materials. Use MC Primer at all metal outlets, lead chute and pipes. Ensure all upstands are min 150mm. |  |  |  | inc
Cover Flashings - chimnies 29 and 31, and walls (excluding parapets as these are coated full height and under copings)
6.10.17 | Except where waterproofing is dressed over parapet under coping and up adjacent roof slopes all abutments to be provided with Code 4 lead cover flashings as recommended by the Lead Sheet Association. |  |  |  | inc
Rainwater Outlets
6.10.18 | Locate and renew all rainwater outlets. Form sumps to all outlets and leave clear and free flowing on completion. |  |  |  | 3499
Cables
6.10.19 | Throughout the works carefully support all data and communications cabling, noting there are large bundles of cables running along the parapet and copings, as well as some in the parapet gutter itself. All lose cables in parapet gutter to be re-supported on suitable galvanised tray support on re-fixed copings to Employers approval. |  |  |  | inc
Railings
6.10.20 | Carefully unbolt, label, set aside and ultimately refix railings fixed to parapet walls and copings, all elevations. |  |  |  | inc
NEW HORIZON CENTRE - Ground Storey Parapet Roofs - PROVISIONAL
6.10.21 | Clean off roofs to elevation 6 to New Horizon Youth Centre and recover with insulation entirely as above items 6.10 - 19 above. See roof plan. Dress coverings into exiting outlets. Note internal investigations of downpipes taken elsewhere. |  | Prov Item |  | 3740
6.11 | J31 FLAT ROOFS – NON RESIDENTIAL AND PRIVATE BALCONIES
Flat Roofs
6.11.1 | Flat roofs are provided to this top storey elevation 4. Refer to roof plan L (0)011. All are to be overlaid. |  |  |  | inc
Private balconies are located on elevation 10 (2No)
Waterproofing
6.11.2 | Supply and install complete waterproofing system to the flat roofs and balconies. No insulation required. Design solution is to be provided and installed to achieve a minimum 15 year guarantee for labour, materials and workmanship and as such will need to be a proprietary system installed by an approved specialist. |  |  |  | inc
Preparation
6.11.3 | Remove existing localised repairs. Remove all moss, dirt and debris. Inspect and repair the existing surface. Blisters in the asphalt should be carefully warmed, pierced and smoothed down to a level surface to receive the overlay system. |  |  |  | inc
Waterproofing
6.11.4 | Supply and lay cold pour resin waterproofing including primer to detailing, finish colour Dark Grey, all to coverage rates specified by manufacturer to achieve guarantee. Ensure bridging tape used at junction of dissimilar materials. Use MC Primer at all metal outlets, lead chute and pipes. Ensure all upstands are min 150mm. |  |  |  | inc
Cover Flashings
6.11.5 | All abutments to be provided with non lead flashings. Cut new chases in rendered abutments at increased height (staircase walls), to receive new Ubiflex B3 or equivalent Lead Alternative Grey 3.5mm thick flashing (upstand 150mm min). Lead alternative. Seal with suitable Gap Seal and Fixing wedges. |  |  |  | 2653
Perimeter Trims and detailing
6.11.6 | Supply and install all necessary GRP trims and other detailing to roof edges, forming upstands, water checks and kerbs as required. |  |  |  | inc
Rainwater Outlets
6.11.7 | Locate, design and renew all rainwater outlets, design and form sumps to all outlets and leave clear and free flowing on completion. |  |  |  | inc
6.12 | L10 WINDOWS
New Windows
Design and Listed Building Consent
6.12.1 | Complete the detailed design of the new replacement windows and provide drawings as specification item L10:210A, drawings and Window Schedule |  |  |  | Noted
6.12.2 | Considerable effort has gone into achieving a design acceptable for listed building consent, window details and frame dimensions shall not be varied against the approved drawings. An approved sample sash window Type K and a tilt window Type J have been fitted in flat 182 which can be inspected externally. The type K window is to be the minimum standard acceptable on this project for a sash window but will need to be replaced to allow for installation of external architrave and head flashing details. The type J tilt/hopper window needs to be replaced, it is broadly acceptable but improved detailing is shown on the tender drawings. |  |  |  | Noted
Supply and Installation
6.12.3 | NB it is a specific requirement of the Employer that the window manufacturer shall supply and fit the windows, not just supply for installation by others. |  |  |  | Noted
Pilot Flat
6.12.4 | Refer to block 136 - 180. |  |  |  | 1250
Surveys
6.12.5 | Every window shall be surveyed and manufactured to suit the specific opening. The contractor should allow to remove and dispose of the external architraves fitted to vertically sliding sash windows to enable the actual structural opening size to be established. Allow for any temporary seals to windows once architraves are removed. Similarly turn back lead head flashings as required to allow accurate survey. |  |  |  | inc
Remove Existing Windows – all flats NB New Horizon Centre is excluded from this - refer to section M60 later for decorations.
6.12.6 | Carefully remove existing timber windows, fanlight and side lights and ensure units are only removed if they are to be replaced the same working day. See clause 6.12.12 below which will be strictly enforced. |  |  |  | 10800
6.12.7 | Notes from pilot window installation;
| - Vertically sliding sash windows are not original, they are fixed with lugs/straps back into the plaster reveals. |  |  |  | Noted
| - The new sash window frames are deeper than existing, the contractor must allow to carefully cut away internal plaster to allow the windows to be set into the reveals to achieve an external reveal suitable for sealant. |  |  |  | Noted
| - Tilt windows do appear to be original and are built in, bedded on mortar with frame ties. The mortar bedding will need removing from brickwork, the ties need cutting. |  |  |  | Noted
6.12.8 | Remove windows as below: (Approx. Quantities - contractor to verify and confirm with tender. All windows to be replaced and to the entire block unless indicated otherwise on drawings).
| Bring forward total cost of windows to this block from window schedule here. |  |  |  | 333905.891
Generally
6.12.9 | Allow for ensuring all timber framing materials and glass is recycled once removed from site. Allow for removal of any debris from existing units and thoroughly clean the working area. |  |  |  | inc
6.12.10 | Allow for all reveal surfaces of the openings to be cleaned to remove all existing frame sealant, mastic, bedding mortar etc. ready for the installation of the new units. |  |  |  | inc
6.12.11 | Security fittings - many windows have security bars and fittings attached on a "DIY" basis. Allow to remove and discard but option to return fittings to residents. |  |  |  | inc
6.12.12 | Under no circumstances shall a window be removed unless the replacement window is ready, checked and suitable for installation, with sufficient time that day to complete the installation. Appointments with residents should not be made until the replacement window or door is manufactured and quality checked in the factory, delivered to site and re-checked, ensuring it is clearly labelled for the given flat and all components are available and undamaged. Allow for all necessary on site storage. |  |  |  | Noted
Replacement Windows – all flats
6.12.13 | Complete the design, manufacture, supply and installation of engineered timber windows systems together with glazing as required in Section L10 of Section 2 – Materials and Workmanship and as detailed on drawings to meet Secured by Design PAS 24 standards. Windows to comprises high performance double glazed; |  |  |  | inc
· Vertical sliding sash with semi concealed balances, NO tilt facility, and
· Casements, outward opening,
· Inward opening hopper/tilt inwards windows (Accepted not Secured by Design)
· Fixed lights
and combinations thereof as indicated on the approved listed building consent and planning drawings.
6.12.14 | Contractor to allow for and design all associated ironmongery and necessary fixings to create a fully operational, safe and user friendly window system. Refer to L10 specification. |  |  |  | inc
6.12.15 | Tilt/hopper and casement window frames on access balconies are to be positioned level with the existing external window line wherever possible. Sliding sash windows to be set back into the reveals as described earlier. Ensure all frames are plumb, and level and without bow. Window positioning in the reveals is key to the listed Building Consents as well as retention of sight lines and glazing bar profiles. |  |  |  | inc
6.12.16 | Provide fully detailed drawings and ironmongery specifications period to manufacture for comment by Employer. |  |  |  | inc
6.12.17 | Windows to include trickle vents. External vent canopies are not permitted by the listed building consent, all vents to be concealed externally. Design to minimum Exposure Category B and Window Energy Rating A/whole window U value n/e 0.6, Secured by Design (except tilt windows where Employer accepts not achievable). |  |  |  | inc
1. Air permeability 600 PA
2. Water tightness 300 PA
3. Wind resistance 2000 PA
Sealants
6.12.18 | Prime and Seal all external joints between framing and structure with low modulus neutral cure silicone sealant to BS5889 (1989). Sealant backing to be provided and detailed in drawings. |  |  |  | 8100
Making Good
6.12.19 | The contractor shall be responsible for and allow for all making good work to window openings, both internally and externally, including external rough cast render margin around all sash windows, masonry, plaster, all cills, reveals, jambs, heads, tiling, decorations etc. cladding and decorative finishes to reveals. |  |  |  | 43251
Note - External reveals to sliding sash windows in rendered elevations to include making good perimeter with roughcast render finish to M20 specification to allow for setting windows back into the reveals. Tilt windows to be made good with mortar collar joint externally, raked out to min depth 15mm before pointing. Collar joint works to be by experienced bricklayers.
Internal trims to be min 30 x 10mm painted timber (PVC not permitted).
6.12.20 | No additional allowance will be made for costs associated with making good unless identified as pre-existing damage in the schedule of condition (item 4.0 J earlier) and prior instructions obtained from the CA. |  |  |  | Noted
Electrical and Other Services
6.12.21 | Allow for unclipping all existing telephone cables, aerial cables and the like from existing windows frames, and re-clip to surround in a suitable location using new cable clips of appropriate size and colour. Any cables passing through a frame/structure joint shall be routed through a plastic sleeve, the inner end of which is to be higher than the outer to prevent water penetration along or through the sleeve. |  |  |  | inc
6.12.22 | Disconnect and reconnect to appliances as required and leave in full working order on completion to resident's satisfaction. |  |  |  | inc
Curtain Tracks, Net Curtain Hooks and Furnishings
6.12.23 | Remove and re-fit existing curtain tracks and other soft furnishings as applicable. Curtain rods to be plugged and screw fixed with new hooks to window reveal soffit, not frame head where it would obstruct trickle vents and ironmongery. Inform Employer of any tracks and soft furnishings not suitable for re-instatement. |  |  |  | inc
Completion
6.12.24 | Upon completion of and on the same day of the installation of each replacement window/door, all glazing, window frames, handles and all other surfaces are to be cleaned with a mild detergent. All components are to be checked for security of fixings, adequacy of clearances, adjustment of hinges, locks etc. as may be necessary to leave the window/door units in good working order. |  |  |  | inc
6.12.25 | On completion of window installation on the same day the contractor shall: |  |  |  | inc
- Snag his own work and make good.
- Remove all debris, dirt etc.
- Clean the window inside and out.
- Demonstrate the operation of the window to the resident and ensure the resident confirms that they understand the methods of window operation, notably any ironmongery operation, cleaning facilities, restrictors and locks.
- Obtain a signed sheet from the resident confirming:
1. They are satisfied with installation.
2. Making good is complete.
3. Cleaning completion.
4. Understand how the windows work.
Should the contractor fail to complete this process access to other flats to start new installations will be denied until the process is complete and under such circumstances no delays or associated costs will be entertained by the Employer in this regard.
6.12.26 | External Architraves Allow to supply and fit ex 20 thick x 30mm wide 19 x 75mm moulded external architraves to all sash windows all elevations. See detail drawing. Fully decorated with microporous paint system to match windows. |  |  |  | inc
6.12.27 | Head Flashings - To all vertically sliding sash windows and casement windows located on elevations (excluding access balconies, supply and fit new 0.7mm welted zinc head drip flashings as detail. |  |  |  | inc
FENSA
6.12.28 | For window and door replacement works provide a FENSA certificate for every flat, with a copy for the Employer. |  |  |  | inc
6.13 | L20 DOORS
Doors – Flat Entrance and other Secondary residential doors to flats
Design
6.13.1 | Complete design new doors and provide drawings in accordance with L20.
6.13.2 | Allow to design, supply and install new complete pre-fabricated engineered timber door set systems complete with side and fan lights, Secured By Design and with glazing bars to suit Listed Building Consent. See L20:410A.
6.13.3 | NB it is a specific requirement of the Employer that the door manufacturer shall also supply and fit the doors/windows, not just supply for installation by others.
6.13.4 | Note doors to comply strictly with Listed Building consent. All doors to be fire rated, see scope of works below.
6.13.5 | Sample Flat Considerable effort has gone into achieving a design acceptable for listed building consent, door details and frame dimensions shall not be varied against the approved drawings. A sample door and side light have been fitted in flat 182 which can be inspected externally. This sample is not fully compliant and will need to be replaced in line with the tender drawings, but broadly demonstrates the style required noting incorrect details such as glazing bars, trickle vent etc are not acceptable.
Pilot Flat
6.13.6 | Refer to block 136-180.
| Note the doors and adjacent windows are to be from one manufacturer/supplier/installer, to achieve the required certification. Bespoke solutions of windows and door systems being joined together will not be accepted unless PAS 24 certified as a complete unit. |  |  |  | 1866.8
Flat entrance Doors - 204 - 238
6.13.7 | Type I door and OPENABLE side window units - 204, 207, 208, 209, 211, 212, 213, 217, 219, 220, 221, 225, 227, 228 and 229. | 15 | No |  | 35502
| Type R - door no window - 214, 222, 231, 234 and 238216, 224, 233 | 5 | No |  | 9294.63
Fire Rated Flat Entrance doors and side windows
6.13.8 | Note - Doors and borrowed/side lights creating balcony 'dead-ends' in terms of means of escape in case of fire to be FD30 and all glazing to be non-wired with 30 min fire integrity, FIXED SHUT. Applies to;
| Type I - Flats 205, 206, 210, 215, 218, and 226. | 5 | No |  | 11835
| Type R fire rated, no window - 215, 216, 223, 224, 230, 232, 233, 235, 236 and 237 | 10 | No |  | 18366
Making Good
6.13.9 | The contractor shall be responsible for and allow for all making good work to door openings, both internally and externally, including masonry, plaster, all cills, reveals, jambs, heads, tiling, decorations etc. cladding and decorative finishes to reveals. Perimeter of doors and side window to be made good with mortar collar joint as described for tilt/hopper windows on access balconies. |  |  |  | inc
No additional allowance will be made for costs associated with making good unless identified as pre-existing damage in the schedule of condition and prior instructions obtained from the Employer.
Sealants
6.13.10 | Prime and Seal all external joints between framing and structure with low modulus neutral cure silicone sealant to BS5889 (1989). Sealant backing to be provided and detailed in drawings. |  |  |  | inc
Completion
6.13.11 | Upon completion of and on the same day of the installation of each replacement door, carry out all checks as item 4.12.24/25 for windows. |  |  |  | inc
Electrical, Access Control and Other Services
4.13.12 | Disconnect and refix access control cables and system as required. Allow for unclipping all existing telephone cables, aerial cables and the like from existing door frames, and re-clip to surround in a suitable location using new cable clips of appropriate size and colour. Any cables passing through a frame/structure joint shall be routed through a plastic sleeve, the inner end of which is to be higher than the outer to prevent water penetration along or through the sleeve. |  |  |  | inc
Disconnect and reconnect to appliances as required and leave in full working order on completion to resident's satisfaction.
Main Communal Entrance Doors
6.13.13 | Prior to commencement validate operation of access control system and report any defects. | 3 | No |  | inc
Overhaul Communal Doors – Elevations 4, 10/8 (corner door).
6.13.14 | Thoroughly overhaul 3 No. existing communal doors/gates; ease and adjust, lubricate all ironmongery, adjust and test self-closers to leave in sound working order. | 3 | No |  | 259
Store Doors, lift lobby cupboard doors, and Meter Cupboard Doors
6.13.15 | Thoroughly overhaul existing doors; ease and adjust, lubricate all ironmongery, adjust and leave in sound working order ready for decorations taken elsewhere. Allow 5 No Provisional Quantity. | 5 | No |  | 281.43
Resident Security Gates/Doors
6.13.19 | Allow Provisionally to take off and return to occupant security door or gate fitted over flat entrance door. Make good all surfaces disturbed | 2 | No Prov Item |  | 180
FENSA
6.13.20 | Provide FENSA certificate for each door and window unit installed as described in windows section previously. |  |  |  | inc
DRY RISER DOORS
6.13.21 | Allow to supply and fit padlocks, FB type, where missing. Allow 2 No. | 2 | No |  | 33.75
6.14 | BOILER FLUES AND GAS FIRES
6.14.1 | The contractor should note some flats have boiler flues that penetrate windows/doors. Allow to, as necessary, design, disconnect, adapt, provide bespoke door/window panel, and re-use boiler flues where they penetrate door or window openings. |  | Item |  | 616
6.14.2 | Provide Gas Safe engineer's certificate for any work to boilers and provide a new CP12 landlord's certificate for the affected flats. |  | Item |  | inc
6.14.3 | Where boiler flues pose a risk to the contractors workforce, e.g. concrete and render repairs allow for close resident liaison to turn off boilers on a daily basis and restart on completion of works in the vicinity. |  | Item |  | inc
Fireplaces and Flues
6.14.4 | Prior to commencement of any works to chimnies, (e.g. render renewal, brick repairs and the like) fully survey all flats internally and establish any open fireplaces, vents and gas appliances. All open fire places and vents to be fully sealed during the works. All gas appliances to be temporarily disconnected and reinstated on completion of chimney works and flue checks. Provisional sum taken later for gas appliances, all other works to be priced here. |  | Item |  | inc
6.14.5 | Allow the provisional sum of £3,000 for works to gas fires as may be required over and above item 6.14.1 - 4 above. |  | Prov Sum |  | 3000
Air Vents in Brickwork
6.14.6 | Carefully cut hole in external brick wall assuming 330mm thick and install 215 x 215mm Terra cotta square hole clay air brick BS 493: 1995 externally with insect mesh (gas compliant) , and white plastic louvre internally. Make good all surfaces disturbed. Allow Provisional Quantity. | 4 | No Prov Item |  | 528
6.15 | M20 - RENDERED/ROUGHCAST COATINGS - Refer to Section 2 Specification
Survey and test existing – All Elevations 4, 5, part 6, 7, part 8 and 10.
6.15.1 | See earlier item regarding gas fires. Allow for hammer testing of entire existing external render to all existing rendered surfaces including walls, chimneys and gables. Provide a detailed report and marked up drawings showing all defective and sound areas for agreement on extent of works to go forward. |  | Item |  | 237
Samples and Control Sample Area
6.15.2 | A - Mix samples. In agreement with Employer take a minimum of 10 No samples of original render (not modern patch repairs) from various levels and elevations. Clearly label and identify and submit to a specialist competent testing house to provide a detailed analytical report on the original design mix and constituents. Agree with Employer and conservation officer appropriate mix for repairs and renewals. | 10 | No |  | 788
| B - Control Sample Trial Area - re render to full specification min 2 sq. m in agreed location and fully paint as M60. Allow to dry for agreement before proceeding with remainder of works. | 2 | m² |  | 122
Chimnies - Nos 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30 and 31 (refer to roof plan for locations) various heights
6.15.3 | Allow to remove all render complete to all 11 chimnies to this block and prepare brickwork for re-rendering, including dubbing out and pointing up lose and defective brickwork. See also item 4.14 earlier in this section. |  |  |  | 8645
6.15.4 | Re render chimnies in roughcast style to match original design mix (established from items above) and texture and leave ready for painting. Include stop and drip beads to all flashings and weatherings. |  |  |  | inc
NB new render to be applied to a consistent standard, spraying of top coat recommended. See example on block 1-21 courtyard elevation and chimnies.
Notes;
Flaunchings – 12 chimnies
6.15.5 | Remove and re-flaunch all flue terminals and pots in sand: cement mortar finished to a neat weathered profile. |  |  |  | 1100
Elevations
6.15.6 | Carefully hack off render as schedule below. Prepare surfaces and re-render in roughcast pattern to an agreed mix, assume 1:1:6. Note - rendering to be carried out by experienced and competent conservation/restoration specialists to meet requirements of Listed building consent and as M20. Form rebates/reveals/returns to all window and door openings to match original design intent. Note spraying recommendation as for chimnies and previous example in courtyard (north) elevation of block 1 - 21 Levita.
6.15.7 | Subject to testing in items above allow for provisional areas and/or quantities as follows and with reference to the drawings;
| 1. Elevation 4 - 6 storey central section (flats 209 - 21 up to 234 - 238 inclusive), complete from first floor above "stonework" to parapet level, excluding access balcony column features. |  | Item |  | 10125
| 2. Elevation 4 – 4 storey section complete first floor above "stonework" to parapet ( flats 213 up to 229 - 230) complete excluding access balcony column features. |  | Item |  | 2430
| 3. Elevations 4 and 5 – other rendered areas, patch repairs Provisional allowance 30 sqm. | 40 | m² |  | 2700
| 4. Elevation 6 -15 sqm. NB The decorative parapet features and balcony recess features are not to be removed. Provisional area in patches. | 15 | m² |  | 1013
| 5. Elevation 7 (high level above New Horizon Youth Centre flat roof) - 4 sqm. NB The decorative parapet features and balcony recess features are not to be removed. Provisional allowance. | 4 | m² |  | 675
| 6. Elevation 8 - 5sqm. NB The decorative parapet features are not to be removed. Provisional allowance. | 5 | m² |  | 338
| 7. Elevation 10 - 25 sqm. NB The decorative parapet features are not to be removed. Provisional allowance. | 25 | m² |  | 1688
| 8. Decorative features parapet level - Extra over above item for reforming decorative features to parapet level, allow 40 linear metres of parapet. Provisional Quantity | 40 | m |  | 3375
| 9. Extra over above item reform curved feature to access elevation balcony columns. Allow 10 No Provisional quantity. | 10 | No |  | 844
6.16 | M60 - PAINTING/CLEAR FINISHING
Redecorations
6.16.1 | Note - Shop fronts and ground storey of retail units, and Somerstown Coffee House public House elevations are excluded from the works. |  |  |  | Noted
6.16.2 | Prepare and decorate all previously or usually decorated surfaces and elements. Thoroughly prepare and redecorate all previously or usually so treated surfaces including, but not limited to; |  |  |  | 57956.8
Joinery M60:130
6.16.3 | · Communal area store doors and frames, lift lobby unglazed doors, plant rooms and intakes, roof access hatches, etc. not stained or otherwise treated. NB all painted inside and out. |  | Item |  | inc
6.16.4 | · Lift lobby glazed doors and frames with panel over, two per level first floor upwards, both sides. | 8 | No |  | inc
6.16.5 | . Lift lobby windows, both sides. Include to replace all missing and defective putties approx. size 2030 x 1850mm. | 4 | No |  | inc
6.16.6 | · Any other previously or usually so treated joinery. |  | Item |  | inc
6.16.7 | · Dormer window fascia details. | 25 | No
New Horizon Youth Centre Windows and Doors
6.16.8 | Prepare and decorate all New Horizon Youth Centre ground, first floor and dormer windows as M60:130. Refer to window schedule and carry forward price to pricing column here. Total 44 No windows varying styles, and 3No painted doors. Refer to drawings. |  | Item |  | 1170
6.16.9 | Ensure all windows are eased and adjusted, and left in full working order on completion. Report any rot and other defects to CA. |  | Item
6.16.10 | Allow Provisional Sum of £250 for minor timber repairs and propriety resin window pre decoration repairs to New Horizon windows. |  | Prov Sum |  | 250
Metalwork M60:130
6.16.11 | · Communal access balcony railings, mesh and perforated panels, security gates and screens (including previously powder coated), and all other usually so treated features, fixtures and fittings. NB Allow for additional preparation to severely corroded areas, to be needle gunned, grit blasted or otherwise treated to remove heavy corrosion. Apply suitable metal fillers to all pitted areas. Advise Employer of any steel found to be unsound. |  | Item |  | inc
6.16.12 | · Communal access balcony conduit and trunking capping, overflows etc. NB allow for suitable primer to galvanised surfaces and note extensive existing flaking paintwork. |  | Item |  | inc
6.16.13 | · Communal stairs balustrades and handrails internally, and externally to entrances. |  | Item |  | inc
6.16.14 | · Doors to former bin chutes/lift motor room, inside and out and electrical risers (ground storey). |  | Item |  | inc
6.16.15 | · SVPs, wastes, RWPs and hoppers and gully gratings all levels. |  | Item |  | inc
6.16.16 | · Refuse hoppers (sealed shut), all levels. |  | Item |  | inc
6.16.17 | · Gas distribution pipes. On completion supply and fit 50mm wide pipe marking and identification tapes, manufactured to BS1710 and BS4800, at 10m centres and within 300mm of any penetrations through walls, floors and ceilings, or change of direction. |  | Item |  | inc
6.16.18 | · Dry riser doors and frames, including de-rusting. |  | Item |  | inc
6.16.19 | · Dry riser pipes where exposed. |  | Item |  | inc
6.16.20 | · Steel handrail to top of parapet gutter parapet walls. |  | Item |  | inc
6.16.21 | New Horizon Centre - Chalton Street boundary wall railings |  | Item |  | inc
Rendering and painted brickwork - M60:170 MAXIMUM EXPOSURE SMOOOTH MASONRY PAINT
6.16.21 | · All render to all elevations including chimnies and all columns. |  | Item |  | inc
6.16.22 | · All existing painted brickwork and blockwork/stonework to inside face of parapet walls and access balcony walls only where painted at present. Note any brickwork unpainted is to remain unpainted, protect throughout the works. |  | Item |  | inc
| (Indicate cost of above item attributable to New Horizon ground storey elevation 6, and low rise sections under pitched roofs 9 elevations 4, 5, 6, 7 and 8 £……………….) |  |  |  | inc
6.16.23 | · Courtyard dwarf walls, walls to entrance steps, ramps etc. Allow to remove all vegetation growth in advance of preparation and decoration. |  | Item |  | inc
6.16.24 | · Copings to all access balcony parapet walls and to main roof parapet gutters. Allow to remove all vegetation growth in advance of preparation and decoration. |  | Item |  | inc
6.16.25 | Note - Masonry paint colours will be predominantly Classic Cream with white features to be picked out EG access balcony copings and columns, to be confirmed by CA on site. Allow for masking and cutting in. |  |  |  | Noted
6.16.26 | New Horizon - Chalton Street boundary wall all sides. |  | Item
Communal stair walls and stair soffits, communal access balconies, stairs and corridor at top roof plant room level - Specification M60:170A
6.16.27 | Textured soffits to stairs and communal walkways - carefully remove all existing textured coatings back to sound substrate and make good ready for new coatings. |  | Item |  | inc
6.16.28 | To all walls carefully remove localised areas of failed coatings back to sound render and brick substrate. Jet wash all surfaces ready for new coatings. |  | Item |  | inc
6.16.29 | Prepare for, supply and apply a water based class 0 coating system eggshell finish, including compatibility tested for adhesion and paint film thickness build up. Ceilings and Soffits as M60:170A Eggshell Finish, walls as M60:170A Antigraffiti system. Note remove all existing flaking and defective coatings and thoroughly prepare walls and soffits, test dry film thickness of remaining surfaces. Allow to decorate only one stair at a time, and top floor main stair flights to be left in use at end of each work period to maintain access for residents. |  | Item |  | inc
6.16.30 | To include painted door reveals to lift lobby doors. |  | Item |  | inc
6.16.31 | To include all services riser casings on stairs on completion of repairs and fire stopping taken elsewhere. |  | Item |  | inc
6.16.32 | Prepare and paint top course of brickwork to access balcony elevations, currently painted black. |  | Item |  | inc
6.17 | R 11 ABOVE GROUND DRAINAGE
Test and Report
6.17.1 | Upon completion of scaffolding test and report on condition of entire surface water drainage system including gutters, hoppers and RWP and SVP downpipes. Agree with Employer extent of repairs and renewals. |  |  |  | 273
Rainwater pipes – general overhaul
6.17.2 | Thoroughly overhaul rainwater downpipes, refixing clips, remaking joints as required to leave in sound watertight condition ready for decorations. |  |  |  | 507
Repairs and Renewals
Allow to remove and replace the following provisional quantities of surface water drainage;
1. Gutters - New Horizon Youth Centre
6.17.3 | Take down and replace 110mm nominal cast iron half round gutter complete with all accessories including rafter brackets, bends, outlets, stop ends and the like. Allow provisional quantity of 34 m. | 34 | PROV QUAN metres |  | 1912.5
2. Downpipes SVP/RWP
6.17.4 | Cast Iron, 110mm nominal diameter SVP/RWP to match existing – 20 Linear metres. Provisional Quantity | 20 | m |  | 1237.5
3. Downpipes RWP - New Horizon Youth Centre
6.17.5 | Cast Iron, 110mm nominal diameter SVP/RWP to match existing – 10 Linear metres. Provisional Quantity | 10 | m |  | 618.75
Hoppers - Elevations 3 and 10.
6.17.6 | Carefully dismantle existing hoppers, these are ornate and need to be retained. Engage specialist to shot blast without damaging the base design. Completely refurbish, repairing all holes and corrosion, prepare and decorate and refix, connecting to new or existing downpipes. Provide temporary plastic hoppers whilst permanent are being repaired. | 3 | No |  | 337.5
Flats 235 and 238 (4th floor level) and 230 (3rd floor) vicinity.
6.17.7 | Carefully dismantle timber pipe casing approx. 300 x 375mm dp x width of balcony, to assumed rainwater outlet. Allow provisionally to dismantle assumed Timesaver type rainwater outlet and pipe to soffit from parapet gutter above. Renew complete to match existing and connect to downpipe. Reinstate pipe casing and leave ready for decorations. | 3 | No |  | 810
6.17.8 | Carefully dismantle Timesaver type rainwater outlet and pipe to soffit from parapet gutter above. Renew complete to match existing and connect to downpipe. | 3 | No |  | 641.25
6.18 | MISCELLANEOUS REPAIRS
Entrance Handrails
6.18.1 | Main Entrance - Remove and replace PVCu capping to handrails complete to match existing, colour to be agreed. |  | Item |  | 225
New Horizon Internal Downpipe Investigations and Repairs
6.18.2 | Internally within New Horizon Youth Centre carefully dismantle internal pipe casings in two locations serving rainwater pipes and outlets from narrow roof above. See photo below. Allow for weekend working. Provide all necessary protection and temporary barriers to protect from staff and students. | 2 | No |  | 1012.5
6.18.3 | Inspect roof outlets, water test and report damage and leaks to CA. | 2 | No |  | inc
6.18.4 | Allow Provisional Sum of £1,250 for repairs to outlet and pipes to be agreed with CA. |  | Prov Sum |  | 1250
6.18.5 | On completion reinstate all pipe casing and panelling with cups and screws to allow future removal. Redecorate locally to nearest internal and external angles with stain blocker and min two cost emulsion paint. | 2 | No |  | 337.5
Pipe Insulation - Block 204 - 238
6.18.5 | Main entrance/dry riser location - elevation 4. Remove all pipe insulation to ground storey area near dry riser and clear away. Supply and fit replacement flexible, UV-resistant closed cell, elastomeric, nitrile rubber insulation system engineered to prevent condensation and energy loss. System to include built-in anti-microbial protection to reduce mould and bacteria growth and with built in vapour barrier to prevent condensation. Approx. 5 linear metres including bends. | 5 | m |  | 309.375
6.19 | P12 FIRE STOPPING
Main Stairwell
6.19.1 | Carefully dismantle ply pipe/cable service risers on every stair and set aside for reuse. Sizes vary 100 x 460 plus splay 440mm ground to first, full height 100 x 460 plus splay 440mm first to second, full height 100 x 460 plus splay 440mm second to third, full height 100 x 460 plus splay 440mm third to fourth, full height high level 250 x 350 x 1500mm fourth floor level. | 5 | No |  | 2514.4
End Stair
| Carefully dismantle ply pipe/cable service risers on every stair and set aside for reuse. Sizes vary 110 x 320 plus splay 330mm ground to first, full height 400mm splay section, full height. 110 x 320 plus splay 330mm first to second, full height 400mm splay section, half height (first to second floor). 110 x 320 plus splay 330mm second to third, full height | 5 | No |  | 2267
6.19.2 | Engage third party accredited passive fire protection specialists for all services. To be members of the BRE/LPCB passive fire protection installer Scheme LPS 1531. |  |  |  | inc
6.19.3 | Seal around all pipes, cables and other services where they penetrate stair landing slabs and soffits with proprietary rapid setting, Gypsum based mortar material, zero shrinkage, 1 hours minimum fire resistance to EN1366-3 up to EI120, including BS476 Pt 20 and BS6399-1 Loading for Buildings “Code of Practice for dead and applied loads”. Include for temporary formwork, ensure removed on completion. All fire stopping to be photographed and certified on completion and full records provided with As Built information. | 10 | No |  | inc
6.19.4 | Reinstate all ply casings removed with new brass cups and screws, leave ready for decorations. | 10 | No |  | inc
6.2 | U90 MECHANICAL VENTILATION
Survey
6.20.1 | The contractor shall survey every flat and identify existing extractor fan types and locations and test and report on same prior to window manufacture for the flat concerned. Agree with CA locations for replacement fans. |  |  |  | 116
6.20.2 | Survey leaseholders and identify if they wish to take up option of fan installation/replacement and report to Employer. Note Tenants will have fans installed under this contract if none provided already in satisfactory condition. |  |  |  | 116
Allow Provisional Quantities to design and install fans as above and following items;
6.20.3 | Kitchen Fans – 15 No | 15 | No |  | 2011
6.20.4 | Bathroom Fans – 15 No | 15 | No |  | 1774
6.20.5 | Separate WC – 5 No | 5 | No |  | 592
Design and Install Fans
6.20.6 | To kitchens, bathrooms and WCs to all flats, survey, design, provide and fix the following, allowing for triple pole isolators to each unit. Allow for all wiring necessary. |  |  |  | 648
| Kitchens - Though wall humidity controlled extract with a minimum intermittent extract rate of 60 l/s. |  |  |  | inc
| Bathrooms - Through wall ducts humidity controlled fans with a minimum intermittent extract rate of 15 l/s. |  |  |  | inc
| Separate WCs - Through wall ducts humidity controlled fans with a minimum intermittent extract rate of 6 l/s. |  |  |  | inc
6.20.7 | Allow for through wall ducting for fans to internal courtyard elevations. Fans not to be window mounted. Include proposals within design submission. |  |  |  | 4287
6.20.8 | Provide NICEIC test certificate on completion for each flat. |  |  |  | 405
Window Fans
6.20.9 | Indicate alternative all in cost per fan for installation through windows, including purpose made sealed unit. Do not carry cost to pricing column for this item. £……………. saving/addition (delete as appropriate).
6.21 | V90 - COMMUNAL ACCESS BALCONY AND STAIRCASE LIGHTING ENHANCEMENT
6.21.1 | Complete design, supply and installation of communal and emergency lighting and controls as set out in Section 2 V90 and Fitzgerald or equivalent Scope of Work document appended thereto and Relux light calculations/simulations. Fitzgerald contact James Baldwin 07815 851996. Ref 46577. All conduit to be galvanised steel reusing existing where possible, adapting to suit. |  | Item |  | 25832
6.22 | BUILDER'S WORK IN CONNECTION WITH SERVICES
Generally
6.22.1 | The contractor shall include for all builders work including, but not limited to: |  |  |  | inc
6.22.2 | Cutting holes and chases for Mechanical and Electrical services and making good ready for decorations. Including but not limited to electrical supply rerouting, communal area lighting, public health engineering/rainwater goods, mechanical fan and ductwork installations, etc. |  |  |  | inc
6.22.3 | Fire stopping where all services penetrate walls, ceilings and any other compartment fire stop around with suitable intumescent boarding, mortar, sealant etc. as appropriate to the service and structure being penetrated. |  |  |  | inc
See also as specification items P12.
Elevations 4, 5, 6 7, part 8 and 10 - Cables
6.22.4 | Tidy up and refix all cables loosely fixed to the elevation. Remove any redundant cables and make good. |  |  |  | 427
6.23 | PROVISIONAL SUMS
Provisional Sums
6.23.1 | Refer to preliminaries A54 for provisional sums, to be expended in part or whole only as directed by Employer. Ensure all carried forward to tender total. |  |  |  | Noted

## Section 6 Collection
Section 6 | £
Page 1
Page 2
Page 3
Page 4
Page 5
Page 6
Page 7
Page 8
Page 9
Page 10
Page 11
Page 12
Page 13
Page 14
Page 15
Page 16
Page 17
Page 18
Page 19
Page 20
Page 21
Page 22
Page 23
Page 24
Page 25
Page 26
Page 27
Page 28
Page 29
Page 30
Page 31
Page 32
Page 33
Page 34
Page 35
Page 36
Page 37
Page 38
Page 39
Page 40
Page 41
Page 42
Page 43
Page 44
Total to main Summary | 1128155.9917
Total 35