	location 
	Type of work
	area/length 
	Duration weeks 

	Mercer st 
	ysp f/w &c/w setts 
	485 m2  
	6 wks 

	Wren st 
	new asp 
	386m2 
	5 wks 

	Cranleigh st 
	setts cw 
	658m2 
	14 wks 

	Charlton st  
	new asp & ysp + relay some 
	144m2 
	5 wks 

	St Pancras way 
	new asphalt 
	111m2 
	3 wks 

	Agar grove - sec 1 
	new asp 
	68m2 
	2 wks 

	Agar grove - sec2 
	new asp 
	459m2 
	10 wks 

	Pakenham st  
	new asp 
	383m2 
	9 wks 

	England’s lane 
	new asp 
	788m2 
	7 wks 

	Mortimer market 
	new asp 
	253m2 
	1 wk 

	Rousden st 
	new asp 
	304m2 
	7 wks 

	Belsize lane 
	new asp 
	649m2 
	9 wks 

	Mortimer market 
	new asp 
	253m2 
	1 wk 

	Ornan rd 
	new asp 
	285m2 
	3 wks 

	Shelton st  
	new ysp 
	363m2 
	4 wks 

	Cubitt st 
	new asp & r/l setts 
	300m2 
	6 wks 

	Ryland rd & Perrens st 
	new asp 
	320m2 
	6 wks 

	Daleham grds 
	new asp 
	102.9m2 
	2 wks 

	Pond st 
	relay & new ysp 
	100m2 
	3 wks 

	Southampton rd  
	new asp 
	572m2 
	12 wks 



