## Sheet1
Action No. | Matter & Issue | Policy/ Criteria/ Site | Action / Proposed Modification | Timeframe
1 | Matter 1 | n/a | Add the Council's opening statement to the Examination library | Action complete
2 | Matter 2 | n/a | Check whether LB Islington set a boundary for the Knowledge Quarter in their Local Plan | Action complete
3 | Matter 2 | n/a | Amend NMM38 to make clear what status Camden Planning Guidance will have post June 2026 and the weight it will be given in decision making | 2026-07-10
4 | Matter 2 | n/a | Provide the timetable for the review of the London Plan | Action complete
5 | Matter 11 | n/a | Provide a note on the status of the Mayor's London Plan Guidance on Support for Housebuilding | Action complete
6 | Matter 11 | Policy H4 Maximising the supply of affordable housing | Review the supporting text of Policy H4 at paragraphs 7.105 and 7.106 and consider whether a modification is required to better explain the role of the strategic target (50%) from the London Plan and its relationship to the Council's target to deliver 3,000 additional affordable homes over the plan period. | 2026-07-10
7 | Matter 3 Issue 1 | Policy H1 Maximising housing supply | Provide a note to explain the approach to the housing backlog | Action complete
8 | Matter 3 Issue 1 | n/a | Provide a list of the sites that comprise the 18% of housing delivery anticipated to come forward on sites of 1ha or less | Action complete
9 | Matter 3 Issue 2 | Policy H4 Maximising the supply of affordable housing | Provide further evidence to support the Council's approach to seeking affordable housing contributions from small sites | Action complete
10 | Matter 3 Issue 2 | Policy H4 Maximising the supply of affordable housing | Consider amendments to Policy H4 Part A to clarify the approach regarding the London Plan strategic target of 50% and London Plan viability thresholds | 2026-07-10
11 | Matter 3 Issue 2 | Policy H1 Maximising housing supply | Review Policy H1 Part B (2) and consider if it should include a reference to purpose built shared living | 2026-07-10
12 | Matter 3 Issue 2 | Site allocation policy S8 St Pancras Hospital | LBC to consider whether a modification should be made to Site Allocation S8 to clarify that Policy H2 (Maximising the supply of self-contained housing from mixed use schemes) will not be applied to any scheme coming forward on the site. Council can confirm they will propose a modification. | 2026-07-10
13 | Matter 3 | n/a | Move main modifications MM53, 75, 76, 77 and 110 to the schedule of non-main (additional) modifications | 2026-07-10
14 | Matter 3 Issue 2 | Policy H9 Purpose built student accommodation | Review Policy H9 Part B (1) and propose an alterative criterion based on the wording in the current Local Plan 2017. Consider whether paragraphs 7.283 and 7.284 would need to be updated in light of this and provide replacement wording if necessary. | 2026-07-10
15 | Matter 3 Issue 3 | Policy H11 Accommodation for Travellers | Review Policy H11 Part D (7) to remove reference to the need to "be attractive" | 2026-07-10
16 | Matter 5 | Policy IE2 Offices | Consider whether a modification should be made to paragraph 9.39 to clarify that, in the Bloomsbury Campus Area, higher education could be an acceptable alternative use when offices use is no longer feasible. | 2026-07-10
17 | Matter 5 | Policy IE2 Offices | Consider amending NMM21 to refer to affordable or low cost workspace | 2026-07-10
18 | Matter 5 | Policy IE2 Offices | Move NMM22 to the schedule of main modifications | 2026-07-10
19 | Matter 5 | Policy IE2 Offices | Propose a modification to paragraphs 9.36 and 9.37 to provide further guidance on how Part C of Policy IE2 will be applied in practice | 2026-07-10
20 | Matter 5 | Policy IE3 Industry | Consider whether a modification is required to Part B of Policy IE3 or the supporting text to clarify how the Council will apply the approach flexibly where there is a proposal for a B2, B8 or sui generis use | 2026-07-10
21 | Matter 5 | Policy IE5 Hotels and visitor accommodation | Move main modification MM81 to the schedule of non-main (additional) modifications | 2026-07-10
22 | Matter 5 | Policy IE6 Supporting designated centres and essential services | Move NMM56 to the schedule of main modifications | 2026-07-10
23 | Matter 5 | Policy IE9 Delivery led food businesses | Review the supporting text to Policy IE9 and consider whether the definition of a delivery-led food business needs further clarification | 2026-07-10
24 | Matter 6 | Policy SC1 Improving health and well-being | Propose a modification to paragraph 10.13 to clarify how Part C of Policy SC1 will be applied for non-major applications | 2026-07-10
25 | Matter 6 | Policy SC3 Social and community infrastructure | Move main modification MM82 to the schedule of non-main (additional) modifications | 2026-07-10
26 | Matter 6 | Policy SC5 Food growing | Propose a modification to Part A (2) of Policy SC5 to make it clear that food growing space will be sought as part of the overall open space contribution | 2026-07-10
27 | Matter 7 | Policy D2 Tall buildings | Council to propose a modification to paragraph 12.31 of the supporting text to Policy D2 to confirm that applications for tall buildings at locations not identified on Figure 22 or listed in Table 12 will also be considered against Policy D2 and other relevant policies. | 2026-07-10
28 | Matter 7 | Policy D6 Basements | Council to provide the Inspector with a timeframe for agreeing the schedule of proposed modifications to Policy D6 Basements with Basement Force and ASUC | Action complete
29 | Matter 7 | Policy D6 Basements | Council to provide Basement Force and ASUC with a schedule of proposed modifications to Policy D6 Basements for comment / agreement. | Action complete
30 | Matter 7 | Policy D6 Basements | Council to provide the Inspector with a note in respect of Policy D6 Basements setting out – proposed changes to the policy, reasons for the proposed changes and the weight to now be given to Topic Paper 9 Basements. | 2026-07-10
31 | Matter 7 | Policy A3 Air quality | Move main modification MM73 to the schedule of non-main (additional) modifications | 2026-07-10
32 | Matter 9 Issue 1 | Policy CC2 Prioritising the retention of existing buildings | Council to propose modifications to site allocation policies S5, S6, S7, S13, S20, C10, C12, C17, W6, and N4 to reflect the fact that the allocation assumes full demolition will occur on these sites to optimise capacity and that Parts A to D of Policy CC2 will therefore not apply to applications being brought forward on these sites. | 2026-07-10
33 | Matter 9 Issue 1 | Policy CC2 Prioritising the retention of existing buildings | Council to propose a modification to paragraph 1.39 of the supporting text in the Introduction (under the heading Site allocations) to reflect the modifications to site allocations policies set out in Action 34 | 2026-07-10
34 | Matter 9 Issue 1 | Policy CC2 Prioritising the retention of existing buildings | Move NMM09 to the schedule of main modifications | 2026-07-10
35 | Matter 9 Issue 1 | Policy CC3 Circular economy and the reduction of waste | Move main modification MM58 to the schedule of non-main (additional) modifications | 2026-07-10
36 | Matter 9 Issue 1 | Policy CC4 Minimising Carbon Emissions | Main modification MM59 - move the following part of the modification to the schedule of non-main (additional) modifications - "The Council will require applicants proposing developers for all new build major development | 2026-07-10
37 | Matter 9 Issue 1 | Policy CC8 Overheating and cooling | Move NMM16 and NMM17 to the schedule of main modifications | 2026-07-10
38 | Matter 9 Issue 1 | Policy CC11 Sustainable drainage | Move NMM19 to the schedule of main modifications to sit with MM64 | 2026-07-10
39 | Matter 9 Issue 1 | Policy CC7 Heat Networks | Council to review the wording of NMM14 to ensure it is future proof | 2026-07-10
40 | Matter 9 Issue 2 | Policy NE2 Biodiversity | Council to review the wording of NMM29 | 2026-07-10
41 | Matter 10 Central Issue 2 | Policy C1 Central Camden | Council to provide the Inspector with a list of policies that refer directly to the Highline. | 2026-06-19
42 | Matter 10 Central Issue 2 | Site Allocation Policy C2 Regis Road and Holmes Road Depot | Council to review the wording of MM22 | 2026-07-10
43 | Matter 10 Central Issue 2 | Site Allocation Policy C2 Regis Road and Holmes Road Depot | Move main modification MM96 and MM97 to the schedule of non-main (additional) modifications | 2026-07-10
44 | Matter 10 Central Issue 2 | Site Allocation Policy C4 Kentish Town Police Station | Move main modification MM25 to the schedule of non-main (additional) modifications | 2026-07-10
45 | Matter 10 Central Issue 2 | Site Allocation Policy C5 369 – 377 Kentish Town Road | Move main modification MM27 to the schedule of non-main (additional) modifications | 2026-07-10
46 | Matter 10 Central Issue 2 | Site Allocation Policy C3 Murphy Site | Council to review the wording of MM98 | 2026-07-10
47 | Matter 10 Central Issue 2 | Site Allocation Policy C2 Regis Road and Holmes Road Depot | Council to update the Inspector on the decision made at planning committee in respect of the planning application for the redevelopment of part of this site. | 2026-06-19
48 | Matter 10 Central Issue 2 | Site Allocation Policy C2 Regis Road and Holmes Road Depot | Council to also consider whether there are any implications for the context section of the site allocation if planning permission is granted (subject to the agreement of a section 106) and propose a modification if required. | 2026-07-10
49 | Matter 10 Central Issue 2 | Site Allocation Policy C7 Morrisons Supermarket | Delete MM28 from the schedule of proposed main modifications | 2026-07-10
50 | Matter 10 Central Issue 2 | Site Allocation Policy C8 Former Morrisons Petrol Filling Station | Delete MM29 from the schedule of proposed main modifications | 2026-07-10
51 | Matter 10 Central Issue 2 | Site Allocation Policy C9 100 Chalk Farm Road | Delete MM30 from the schedule of proposed main modifications | 2026-07-10
52 | Matter 10 Central Issue 2 | Site Allocation Policy C10 Juniper Crescent | Council to consider whether the indicative capacity for the site and the context section should be updated to reflect the recent planning permission granted on the site | 2026-07-10
53 | Matter 10 Central Issue 2 | Site Allocation Policy C10 Juniper Crescent | Delete MM31 from the schedule of proposed main modifications | 2026-07-10
54 | Matter 10 Central Issue 2 | Site Allocation Policy C16 Shirley House | Move main modification MM38 to the schedule of non-main (additional) modifications | 2026-07-10
55 | Matter 10 Central Issue 2 | Site Allocation Policy C17 Camden Town over station development | Council to review and propose a modification to criteria 15 of the policy | 2026-07-10
56 | Matter 10 Central Issue 2 | Site Allocation Policy C19 Arlington Road former depot site | Move main modification MM99 to the schedule of non-main (additional) modifications | 2026-07-10
57 | Matter 10 Central Issue 2 | Site Allocation Policy C23 Former flats 121 – 129 Bacton, Haverstock Road | Move main modification MM43 to the schedule of non-main (additional) modifications | 2026-07-10
58 | Matter 10 Central Issue 2 | South, Central and West areas | Council to review tables 3, 5 and 7 to insert the wording 'additional homes' under the heading Indicative Housing Capacity | 2026-07-10
59 | Matter 10 Central Issue 2 | Site Allocation Policy C23 Former flats 121 – 129 Bacton, Haverstock Road | Council to propose a modification to insert reference to the nearby Grade I listed church (Church of Saint Martin) in the key considerations column | 2026-07-10
60 | Matter 10 Central Issue 2 | Site Allocation Policy C27 Land adjacent to Constable House, Adelaide Rd | Council to propose a modification to the allocated uses to replace 'Gypsy and Traveller accommodation' with 'Permanent Gypsy and Traveller pitches'. | 2026-07-10
61 | Matter 10 Central Issue 2 | Relevant site allocations | Council to provide the Inspector with a schedule of factual updates to the site allocations to reflect where planning permission has now been granted on a site. Council to also identify whether there are any implications to the plan from the modifications proposed | 2026-07-10
62 | Matter 10 South | Policy S1 South Camden | Council to propose an additional modification to delete reference to 'shopping' at Part S to instead refer to Specialist Areas. Council to review the wording in the Plan to ensure it just refers to Specialist Areas, not Specialist Shopping Areas. | 2026-07-10
63 | Matter 10 South | Policy S1 South Camden | Move main modifications MM01, MM02, MM03, MM101, MM102 and MM103 to the schedule of non-main (additional) modifications | 2026-07-10
64 | Matter 10 South | Policy S2 Euston Area | Move main modification MM104 to the schedule of non-main (additional) modifications | 2026-07-10
65 | Matter 10 South | Policy S2 Euston Area | Amend MM04 to incorporate the changes proposed in MM105. Delete MM105. | 2026-07-10
66 | Matter 10 South | Policy S2 Euston Area | Amend MM05 to incorporate the changes proposed in MM106. Delete MM106. | 2026-07-10
67 | Matter 10 South | Policy S2 Euston Area | Amend NMM01 to incorporate the changes proposed in NMM45. Delete NMM45. Move NMM01 to the schedule of main modifications | 2026-07-10
68 | Matter 10 South | Policy S2 Euston Area | Move NMM44 to the schedule of main modifications | 2026-07-10
69 | Matter 10 South | Site Allocation Policy S5 120 136 Camley Street | Move main modifications MM11, MM12 and MM92 to the schedule of non-main (additional) modifications | 2026-07-10
70 | Matter 10 South | Introduction | Council to propose a modification to paragraph 1.38 of the Plan to state that where sites have planning permission the housing numbers agreed through the permission will be considered to be a minimum. | 2026-07-10
71 | Matter 10 South |  | Council to also review housing numbers in the trajectory on the basis it should reflect the reality of what's being delivered. | 2026-07-10
72 | Matter 10 South | Policy H1 Maximising housing supply | Council to review Part B criteria 5 and para 7.25 and reflect on "the Council will expect the submission of evidence to demonstrate that there is no reasonable prospect of a viable development for permanent self-contained housing coming forward within the Plan period" to consider whether a modification is needed to amend the time period | 2026-07-10
73 | Matter 10 South | Site Allocation Policy S6 104 – 114 Camley Street and Cedar Way Industrial Estate | Move main modification MM107 to the schedule of non-main (additional) modifications | 2026-07-10
74 | Matter 10 South | Site Allocation Policy S7 24 - 86 Royal College Street | Review allocation on the basis of the current planning permission to check the policy is deliverable | 2026-07-10
75 | Matter 10 South | Site Allocation Policy S7 24 - 86 Royal College Street | Move main modification MM93 to the schedule of non-main (additional) modifications | 2026-07-10
76 | Matter 10 South | Site Allocation Policy S8 St. Pancras Hospital | Delete MM16 which relates to criteria 4 of the policy and replace with a new modification to insert another reference to Policy D5 Historic Environment into criteria 4. Consider splitting the criteria into two sentences. | 2026-07-10
77 | Matter 10 South | Site Allocation Policy S8 St. Pancras Hospital | Review criteria 5 of policy S8 and propose a modification to insert reference to the provision of a small amount of retail floorspace for place making. | 2026-07-10
78 | Matter 10 South | Site Allocation Policy S8 St. Pancras Hospital | Propose an additional modification to bullet point 3 of the other considerations to make it clear that part of the site is in a wider setting consultation area rather than a viewing corridor. | 2026-07-10
79 | Matter 10 South |  | Council to review other references to viewing corridors in the Other considerations section of the site allocation policies to make sure they are correct and propose modifications as required | 2026-07-10
80 | Matter 10 South | Site Allocation Policy S10 Bangor Wharf and Eagle Wharf | Council to propose a modification to criteria 13 of the policy to state that we will take account of the condition of the granite setts when considering whether they should be retained / re-used. | 2026-07-10
81 | Matter 10 South | Site Allocation Policy S11 Former Royal National Throat, Nose and Ear Hospital | Council to provide the Inspector with evidence to demonstrate the site's availability. The Council provided this evidence verbally to the Inspector as part of the hearing session for matter 4. | Action complete
82 | Matter 10 South | Site Allocation Policy S11 Former Royal National Throat, Nose and Ear Hospital | Move main modification MM94 to the schedule of non-main (additional) modifications | 2026-07-10
83 | Matter 10 South | Site Allocation Policy S15 Land to rear of British Library | Move main modification MM95 to the schedule of non-main (additional) modifications | 2026-07-10
84 | Matter 10 South | Site Allocation Policy S16 Former Central St Martins College | Council to review when this site will come forward in the housing trajectory | 2026-07-10
85 | Matter 10 South | Site Allocation Policy S20 York Way Depot and adjacent land at Freight Lane | Move main modification MM108 to the schedule of non-main (additional) modifications | 2026-07-10
86 | Matter 10 South | Site Allocation Policy S20 York Way Depot and adjacent land at Freight Lane | Propose a modification to criteria 6 of the policy to insert "including the Aggregates Safeguarded Area" after "generating activities". | 2026-07-10
87 | Matter 10 South | Policy S1 South Camden | Propose to add additional wording to Policy S1 PartQ which states that in assessing any proposals for housing or other sensitive land uses in the vicinity of the Safeguarding Area, the Council will apply the Agent of Change Principle in line with Policy A1 Protecting Amenity. | 2026-07-10
88 | Matter 10 North and West | Site Allocation Policy N2 Mansfield Bowling Club | Move main modification MM46 to the schedule of non-main (additional) modifications | 2026-07-10
89 | Matter 10 North and West | Policy W1 West Camden | Move main modifications MM07, MM08, MM09 and MM10 to the schedule of non-main (additional) modifications. | 2026-07-10
90 | Matter 10 North and West | Policy W1 West Camden | Council to review modifications and just make one modification to Policy W1 the first time site allocation W2 is mentioned to make it clear what the policy relates to. | 2026-07-10
91 | Matter 10 North and West | Site Allocation Policy W2 O2 Centre, carpark and car showroom sites and 14 Blackburn Road | Move main modification MM100 to the schedule of non-main (additional) modifications | 2026-07-10
92 | Matter 10 North and West | Site Allocation Policy W11 Abbey Co-op Housing Site | Delete site allocation W11 from the Plan | 2026-07-10
93 | Matter 10 North and West | Site Allocation Policy W13 551-557 Finchley Road | Delete site allocation W13 from the Plan and delete MM45 | 2026-07-10
94 | Matter 10 North and West | Site Allocation Policy W14 317 Finchley Road | Delete site allocation W14 from the Plan | 2026-07-10
95 | Matter 8 Transport | Policy T1 Safe, Healthy and Sustainable Transport | Council to review and amend MM84 to include reference to HS2. | 2026-07-10
96 | Matter 8 Transport | Policy T2 Prioritising walking, wheeling and cycling | Council to propose a modification to Policy T2 Part C.2 | 2026-07-10
97 | Matter 4 Housing land supply |  | Council to add the notes provided to the Inspector to date to the examination website | Action complete
98 | Matter 4 Housing land supply |  | Council to update the phasing of C7 Morrisons Supermarket to reflect the information provided by Quod on behalf of St George West London | 2026-07-10